SECTION 10.2
RECONSTRUCTION: JULY 2004 TO JULY 2009
Contents
Introduction .................................................................................................................. 198
The transition from Occupation to an Iraqi Government .............................................. 199
Efforts to accelerate the pace of reconstruction ........................................................... 200
Reconstruction in areas regained from insurgent control, and Fallujah ................. 213
Agreement on debt relief for Iraq ........................................................................... 224
Taking the strain in the South, early 2005 .................................................................... 224
DFID reduces its budget for Iraq for 2005/06 ........................................................ 229
Priorities for 2005 ................................................................................................... 231
DFID reviews its Interim Country Assistance Plan ................................................. 241
Preparing for transition to Iraqi control in the South ..................................................... 257
Responding to the new US Clear-Hold-Build strategy ........................................... 259
Preparing for the transfer of security responsibility in Maysan and Muthanna ...... 276
Turning Basra around ............................................................................................ 285
UK plans for 2007, and the US surge .................................................................... 303
Major General Shirreff’s proposal for a military-led UK effort in the South ............ 306
Preparing for Provincial Iraqi Control in Basra ....................................................... 309
Responding to the displacement crisis .................................................................. 319
Reconstruction under Mr Gordon Brown’s Premiership ............................................... 323
Charge of the Knights, March 2008 ............................................................................. 343
Transition to a normal bilateral relationship with Iraq ................................................... 359
Long-Term Strategy for Iraq, February 2009 ......................................................... 364
Resources available for reconstruction ........................................................................ 367
Reflections on the impact of the UK’s reconstruction effort ......................................... 369
Key economic and social indicators ....................................................................... 371
197

---
The Report of the Iraq Inquiry
Introduction
1. Section 10 addresses the UK contribution to humanitarian assistance and
reconstruction in Iraq between 2003 and 2009:
•
Section 10.1 covers the period between March 2003 and the end of the
Occupation of Iraq in June 2004.
Section 10.2 continues the story from July 2004 to July 2009.
2. Sections 10.1 and 10.2 consider:
humanitarian assistance;
the development and implementation of UK reconstruction policy, strategy
and plans;
the UK’s engagement with the US on reconstruction, including with the US-led
Office of Reconstruction and Humanitarian Assistance (ORHA) and the Coalition
Provisional Authority (CPA); and
the UK’s engagement with successive Iraqi governments on reconstruction.
3. Section 10.3 addresses five issues in more detail:
UK policy on Iraq’s oil and oil revenues;
the Government’s support for UK business in securing reconstruction contracts;
debt relief;
asylum; and
reform of the Government’s approach to post-conflict reconstruction and
stabilisation.
4. Those issues are addressed separately from the main reconstruction narrative, in
order to provide a clearer account of the development of the UK’s engagement.
5. This Section does not consider:
planning and preparing to provide humanitarian assistance and reconstruction,
which is addressed in Sections 6.4 and 6.5;
the financial and human resources available for post-conflict reconstruction,
addressed in Sections 13 and 15 respectively;
de-Ba’athification and Security Sector Reform (SSR), addressed in Sections 11
and 12 respectively; and
wider UK policy towards Iraq in the post-conflict period, addressed in Section 9.
198

---
10.2 | Reconstruction: July 2004 to July 2009
The transition from Occupation to an Iraqi Government
6. On 28 June 2004, the Coalition Provisional Authority (CPA) formally handed over to
a sovereign Iraqi Government. In the 11 months that followed, the governance of Iraq
was the responsibility of the Interim Iraqi Government (IIG), headed by Prime Minister
Ayad Allawi.
7. The security situation in Iraq remained difficult.
8. The core UK Ministerial team was unchanged: Mr Brown remained Chancellor
of the Exchequer, Mr Straw Foreign Secretary, Mr Hoon Defence Secretary, and
Mr Benn International Development Secretary.
9. Mr Straw continued to chair the Ad Hoc Ministerial Group on Iraq Rehabilitation
(AHMGIR), which met seven times between July 2004 and February 2005, after which
its business was taken up by the Ad Hoc Ministerial Group on Iraq (AHMGI).
10. Mr David Richmond, the Prime Minister’s Special Representative on Iraq, and
Ambassador Paul Bremer, the CPA Administrator, left Iraq shortly after the handover
ceremony.
1
11. Ambassador John Negroponte, the new US Ambassador to Iraq, presented his
diplomatic credentials to the IIG on 29 June.
2
12. Hard Lessons described how, shortly after arriving in Baghdad and driven by
his concern about worsening security, Ambassador Negroponte put the US$18.4bn
Iraq Relief and Reconstruction Fund (IRRF2) on hold and initiated a “thorough
re-examination” of US priorities.
13. Ambassador Negroponte concluded that implementing economic development
programmes would be fruitless while security remained a serious problem. Three
reallocations of IRRF2 funds took place in September 2004, December 2004 and
March 2005. Those reallocations provided additional funds for security, the political
process and “project sustainment” at the expense of infrastructure projects. The water
and sanitation sector lost nearly half its funding, and the electricity sector almost a
quarter of its funding.
14. Mr Edward Chaplin arrived in Baghdad on 5 July to take up post as the first British
Ambassador to Iraq since 1990.
Annotated Agenda, 1 July 2004, Ad Hoc Group on Iraq Rehabilitation meeting.
1
Bowen SW Jr. Hard Lessons: The Iraq Reconstruction Experience. U.S. Government Printing
2
Office, 2009.
199

---
15. Ms Lindy Cameron, Deputy Head of DFID Baghdad from January to November
2004 (and subsequently Head of DFID Baghdad), described the transition:
“… it’s hard to describe how strange the CPA was. So in a sense this period in
June/July 2004 when we were transitioning from the CPA to … an Iraqi Government
that was then sovereign, was a real transition because it is difficult to imagine how
strange it was to be in a building of thousands and thousands of foreign officials
effectively running a country, and then a very rapid transition from that to an Iraqi
Government which had some of the structures it needed, but then didn’t have some
of the others.”
3
Efforts to accelerate the pace of reconstruction
16. On 1 July, at his request, the Permanent Joint Headquarters (PJHQ) provided
General Sir Michael Walker, Chief of the Defence Staff (CDS), with advice on
post-transition plans for infrastructure reconstruction.
4
17. PJHQ advised that:
The US Project and Contracting Office (PCO) would be the largest source of
funding for reconstruction in the short to medium term, but was still developing
its management structures and procedures and recruiting staff. It was likely that
the PCO would not be fully functioning until September. Concerns had been
expressed about a funding gap over the summer and the consequent potential
for “social unrest”. MND(SE) had explored the possibility of extending CPA
projects or increasing the US Commanders’ Emergency Response Programme
(CERPs) allocation for the South, but neither option appeared possible.
Ambassador Bremer had requested that additional UK resources should be
used to plug the potential gap between CPA and PCO activity.
Since the emphasis in Iraq had shifted from reconstruction to development, the
bulk of the UK’s future contribution clearly fell “within the competence of DFID”.
The Essential Services Plan, which had been due to complete by 30 June
2004 but had now been extended to August, remained the “major vehicle for
infrastructure reconstruction” in MND(SE).
The UK military would continue to implement projects funded by the US CERPs
and UK allocations for Quick Impact Projects (QIPs).
18. The 1 July meeting of the AHMGIR considered three papers on UK priorities for the
period up to the Iraqi elections (scheduled for January 2005), on the political process,
security, and reconstruction and development.
5
Public hearing, 22 June 2010, pages 12-13.
3
Minute CivSec PJHQ to PSO/CDS, 1 July 2004, ‘Infrastructure Reconstruction at Transition’.
4
Annotated Agenda, 1 July 2004, Ad Hoc Group on Iraq Rehabilitation meeting.
5
200

---
10.2 | Reconstruction: July 2004 to July 2009
19. The MOD paper on security assessed that the security situation was unlikely
to improve in the immediate future.
 The key to improving the security situation was
6
achieving “buy-in” to the political process and making progress on reconstruction, at the
same time as developing the capacity of the Iraqi Security Forces (ISF).
20. The paper highlighted the importance of job creation:
“A major Iraqi complaint is the failure to meet expectations on reconstruction. This
has the double negative effect of creating disaffection with the political process and
increasing the pool of unemployed …
“It will therefore be important that the reconstruction programme creates sufficient
jobs to significantly reduce the number of disaffected. In the short term, continuing
difficulties in the delivery of essential services could lead to serious disturbances
during the summer.”
21. The DFID paper on reconstruction and development assessed that the next six
months would be critical for establishing stability.
 Better security would be “central if
7
there is to be sustained progress on reconstruction, effective engagement by the UN
and World Bank, and if the Iraqi economy is to take off as it should”.
22. Other key issues for reconstruction and development were:
minimising any potential slowdown in reconstruction and development in the
South over the summer, in particular as new US structures became established;
building the capacity of Iraqi institutions to manage reconstruction;
helping the IIG conclude debt relief negotiations and setting the foundations for
macro-economic stability;
SSR and access to justice; and
strengthening social cohesion by supporting Iraqi participation in the political
process, strengthening civil society’s ability to advocate for the poor, and
supporting the development of the Iraqi media.
23. At the meeting, Mr Benn welcomed the fact that “Iraqis were clearly in charge and
their voices were being heard”.
 The UK was moving “from a phase of doing things
8
for the Iraqis to supporting them doing it for themselves”. The UK’s focus was now on
engaging the UN and World Bank, plugging any funding gap over the summer, and
supporting Iraqi institutions to manage the reconstruction process and access funds.
Paper MOD, [undated], ‘Security: The Next Six Months’.
6
Paper DFID, [undated], ‘Iraq Reconstruction and Development: UK Priorities for the Period up
7
to the Elections’.
Minutes, 1 July 2004, Ad Hoc Group on Iraq Rehabilitation meeting.
8
201

---
24. The meeting endorsed the three papers, and commissioned the FCO to co-ordinate
an integrated UK strategy covering the period up to the Iraqi elections for discussion at
the meeting of the Defence and Overseas Policy Committee (DOP), a sub-Committee
of the Cabinet, on 15 July.
25. In his first report from Basra on 12 July, Mr Simon Collis, the British Consul
General, reported that no PCO staff had yet arrived in Basra to spend the South’s
US$2.3bn projected share of IRRF2.
 He continued:
9
“… no one here – including my US counterpart – knows yet how the third entirely
new organisation in just over a year
 will organise itself and do business. There
10
must be a high risk that money will be spent slowly, inappropriately, and without
adequate consultation with ourselves or, more importantly, the Iraqis.”
26. Mr Collis also advised that there were still no effective mechanisms in place to
enable Iraqi ministries to release funds to Basra.
27. The strategy paper commissioned by the AHMGIR on 1 July was circulated to
members of DOP on 13 July.
 The introduction to the paper said that it offered:
11
“… a strategic look at the position we want Iraq to be in at the end of January 2005;
risks to our strategy; and priority areas in which the UK can help ensure success.”
28. The paper, which had been produced by the FCO, defined the political, security and
“reconstruction and economic” objectives for the period up to the Iraqi elections. The
three objectives for reconstruction and the economy were:
a functioning Iraqi Government in Baghdad and at governorate level capable of
delivering basic services;
reconstruction programmes funded by the PCO, the UN and World Bank Trust
Funds, bilateral donors and the Iraqi Government which were delivering jobs and
improvements to infrastructure and services; and
a reduction in subsidies and an agreed IMF programme leading to a debt
settlement by December.
29. The paper identified security as the most significant risk to achieving those
objectives, in particular the risk of “a terrorist spectacular” against either the IIG
or the UN. Other risks included infrastructure failures over the summer leading to
popular discontent.
Telegram 76 Basra to FCO London, 12 July 2004, ‘First Impressions of Basra’.
9
The PCO, following the Office of Reconstruction and Humanitarian Assistance (ORHA) and the Coalition
10
Provisional Authority (CPA).
Paper FCO, 13 July 2004, ‘Iraq: The Next Six Months’.
11
202

---
10.2 | Reconstruction: July 2004 to July 2009
30. Based on those objectives and risks, the two “reconstruction and development”
priorities were:
To bridge funding shortfalls over the summer, when CPA and Development Fund
for Iraq (DFI) projects ended, by implementing DFID and MOD job creation
and infrastructure programmes. The UK had to maintain pressure on the US to
spend its money in the South, quickly.
To press the UN and the World Bank to send key staff back to Iraq.
31. The paper identified monthly milestones on the political process, reconstruction,
and SSR tracks between July 2004 and January 2005.
32. At the DOP meeting, chaired by Mr Blair, Ministers reported that:
Progress was being made on reconstruction. Electricity production was at its
highest level so far (at 5,500 megawatts), the UK was providing expert advice
to the IIG, notably to Prime Minister Allawi’s office, and DFID and the MOD had
funds in place to mitigate a possible funding gap over the summer.
Implementation of the main infrastructure contracts was slow.
12
33. DOP agreed the priorities set out in the paper, and commissioned DFID to
produce a note on infrastructure issues which Mr Blair might use in discussions with
President Bush.
34. The FCO paper was not the integrated strategy that Ministers had requested on
1 July.
35. The DFID note that was subsequently sent to No.10 welcomed the anticipated
arrival of the PCO Regional Co-ordinator in Basra, and continued: “But PCO
[Co-ordinator] will need a team to support him. Little sign of Supplemental [IRRF2]
contractors on the ground. Needs impetus.”
13
36. President Bush and Mr Blair spoke by video conference on 22 July. Mr Blair’s
briefing for the discussion, which had been produced by Mr Antony Phillipson, Mr Blair’s
Private Secretary, recalled that Mr Blair had told DOP that he would speak to President
Bush about the pace of reconstruction spending.
 Since then, Sir Nigel Sheinwald,
14
Mr Blair’s Foreign Policy Adviser, had discussed the issue with Dr Condoleezza Rice,
the US National Security Advisor. Mr Phillipson suggested that Mr Blair “might just
mention” UK concerns about the situation in the South.
Minutes, 15 July 2004, DOP meeting.
12
Letter Malik to Quarrey, July 2004, [untitled].
13
Minute Phillipson to Prime Minister, 22 July 2004, ‘VTC with President Bush, 22 July’.
14
203

---
37. The record of the video conference did not include any reference to reconstruction.
15
38. The Annotated Agenda for the 22 July meeting of the AHMGIR stated that the
responsibility for IRRF2 had passed from the US Department of Defense (DoD) to
the US State Department.
 The State Department wanted to review US priorities to
16
ensure they were “developmentally sound” and to shift resources from infrastructure to
governance; the UK had urged quick decisions to avoid delaying disbursements.
39. The Annotated Agenda advised that a PCO Regional Co-ordinator would arrive
in Basra at the end of July and projects would start in September. It appeared that the
US was giving priority to programmes “in ‘their’ areas”; there was therefore a risk of a
reconstruction gap in the South. The need to speed up US reconstruction in the South
had been raised at a recent video conference between Mr Blair and President Bush.
40. The Annotated Agenda set out the action that the UK was taking, in addition
to lobbying the US to speed up their efforts, to address the possible short-term
funding gap:
The MOD was seeking a further £10m from the Treasury for QIPs.
DFID was funding a five-person Project Continuity Team (PCT) based in the
PCO to help implement former CPA(South) projects. The PCT had already
deployed.
DFID was funding a 10-person Technical Advisory Team (TAT) comprising
infrastructure and other specialists to help link Iraqi priorities and PCO plans.
The team was expected to deploy to Iraq in August.
DFID had developed a £16m programme to generate employment opportunities
and provide an emergency response facility to deal with critical failures in
essential services in the South over the next six months. The programme would
start immediately.
41. The Annotated Agenda also stated that the IMF was seeking early agreement on a
Stand-By Arrangement for Iraq (a precondition for a Paris Club deal on debt reduction).
DFID hoped to deploy advisers to support the Iraqi Government in its negotiations with
the IMF.
42. A UK Trade and Investment (UKTI) secondee to the PCO told an official at the
British Embassy Baghdad on 7 August that he was not aware of any PCO policy to
withhold support from Basra in favour of US areas.
 The official described the secondee
17
as “generally very well informed on PCO policies”.
Letter Phillipson to Adams, 22 July 2004, ‘Prime Minister’s VTC with President Bush, 22 July: Iraq
15
and MEPP’.
Annotated Agenda, 22 July 2004, Ad Hoc Group on Iraq Rehabilitation meeting.
16
Email FCO [junior official] to FCO [junior official], 7 August 2004, ‘PCO Manning in Basra’.
17
204

---
10.2 | Reconstruction: July 2004 to July 2009
43. Section 9.3 describes the Sadrist uprising in Najaf in early August, and the
deteriorating security situation across Iraq.
44. Mr Blair concluded at the end of August that Prime Minister Allawi needed “help
now”. That help included accelerating the pace of reconstruction, so that Iraqis saw
improvements before the January 2005 elections.
45. Mr Phillipson wrote to the Cabinet Office on 20 August to commission a:
“… full picture of the situation in Iraq after the National Conference,
 how we are
18
going to get from here to successful elections in January, and the challenges we
will face.”
19
46. Mr Phillipson advised that the request followed a “long discussion” the previous day
with Mr Blair, who had observed that the security situation, the slow rate at which the ISF
was being trained and equipped, and “ongoing difficulties” with reconstruction posed a
real risk to the achievement of the UK’s objectives in Iraq.
47. The British Embassy Office Basra reported by telegram on 24 August that the PCO
Regional Co-ordinator had now arrived.
 The Co-ordinator expected the PCO to “have
20
an impact on the ground” in the last quarter of 2004; the British Embassy Office doubted
that the PCO could meet that timeline.
48. On 27 August, in response to Mr Phillipson’s commission, the IPU provided a paper
for the Cabinet Office.
 Mr Neil Crompton, the Head of the IPU, advised Mr Straw’s
21
Private Office that the paper contained “little new in policy terms”.
49. The IPU paper concluded that the strategy agreed by DOP on 15 July was the right
one, but would require regular fine-tuning.
 Its key judgements included:
22
The IIG had made a good start, but needed to deliver results soon, particularly
on security but also on essential services.
There was growing “disquiet” in the “previously benign” South, reinforced by
a sense that Baghdad and the US were neglecting its interests. Politically,
Basra and Maysan were paralysed by power struggles, hindering work on
reconstruction and security.
Iraq was “awash with reconstruction funds”. The challenge was delivering
quickly on the ground. Security was a major hindrance.
From 15 to 18 August a National Conference was held to select an Iraqi Interim National Council (IINC)
18
of 100 members to oversee the Iraqi Interim Government until the election of the Transitional National
Assembly in January 2005.
Letter Phillipson to Fergusson, 20 August 2004, ‘Iraq: Next Steps’.
19
Telegram 130 Basra to FCO London, 24 August 2004, ‘southern Iraq: PCO and Saudi Development
20
Fund’.
Minute Crompton to Private Secretary [FCO], 27 August 2004, ‘Iraq: Next Steps’ attaching Paper IPU,
21
27 August 2004, ‘Iraq: Next Steps’.
Paper IPU, 27 August 2004, ‘Iraq: Next Steps’.
22
205

---
50. The paper stated that President Bush was letting US officials in Baghdad “make the
running”, and recommended that the UK focus its effort with the President on a few key
areas where Washington could make a difference, including ensuring that the US did not
take reconstruction in the South for granted.
51. The paper retained the three reconstruction objectives that DOP had agreed on
15 July (a functioning Iraqi Government, reconstruction programmes funded by others
delivering quickly and well, and a reduction in subsidies and an agreed IMF programme
leading to debt relief by December 2004).
52. Mr Phillipson passed the IPU paper to Mr Blair, after discussing it with
Sir Nigel Sheinwald.
 Mr Phillipson’s covering minute stated that the IPU paper was
23
“too vague”, did not reflect the “loss of control” in Basra and elsewhere, and did not offer
a clear way forward. He recalled that Mr Blair had asked for the “unvarnished truth so
that we can engage in a frank discussion about how we can help the IIG restore control”.
53. Mr Phillipson recommended that a new paper should be commissioned, broken into
three sections:
how to ensure that the elections took place, on time, in January 2005;
how the Sunni triangle could be brought “back under control”; and
how order could be restored in Basra.
54. Mr Phillipson continued that one aspect of the effort to bring the Sunni triangle back
under control should be “a short-term programme of intensive reconstruction to make a
visible impact to people’s lives – a Sunni outreach programme”.
55. Mr Blair set out his analysis of the issues in a note to Sir Nigel Sheinwald,
Mr Phillipson, Mr Jonathan Powell (No.10 Chief of Staff) and a junior member of his
No.10 staff on 29 August.
 He wrote:
24
“Our strategy is fine in one sense: Iraqiisation of security and support for the
democratic political process. The problem is that the urgency of the situation may
overwhelm us and make our timelines for Iraqiisation naïve.
“The fact is Allawi needs help now; and there has to be a clear sense of our gripping
the situation now.”
56. Mr Blair identified nine immediate actions, including:
providing Prime Minister Allawi with “first-class political, media and strategic
capability … now”, drawing on “the best home-grown Iraqi talent” supported by
“our own people” who should be “hand-picked” immediately;
Minute Phillipson to Prime Minister, 27 August 2004, ‘Iraq: Next Steps’.
23
Minute Prime Minister to Sheinwald, 29 August 2004, ‘Iraq’.
24
206

---
10.2 | Reconstruction: July 2004 to July 2009
examining DFID’s assistance to key Iraqi ministries, in particular defence,
25
“to ensure real robustness and … if necessary, our people put in”; and
unblocking funding for reconstruction, in the Sunni triangle and elsewhere,
as the “key to winning hearts and minds”.
57. Mr Blair concluded:
“When I meet Allawi in September, it should be with a coherent plan to change
the situation.”
58. Mr Benn visited Iraq from 31 August to 1 September, despite significant security
concerns.
 He reported to Mr Blair on 3 September that despite worsening security,
26
some progress was being made:
“But the pace of reconstruction is still too slow …
“DFID’s approach of encouraging the international system to help rebuild Iraq and
working through bilateral programmes at the national level (to build capacity in key
ministries) and in the South (to help create jobs, renew infrastructure and reduce
poverty) is still right. But I will want to see substantial progress on spending and
delivery before committing any more to the [World Bank and UN] Trust Funds.
I have therefore concentrated on new bilateral programmes this financial year.”
27
59. Mr Benn reported that, while in Iraq, he had announced new funding for projects
in the South to respond to critical needs in essential services and create jobs and build
capacity in the four southern Governorates. The MOD had also secured additional
funding for QIPs.
60. Mr Benn concluded: “We will need to stay flexible in responding to changing
circumstances.”
61. The projects referred to by Mr Benn were the £16.5m southern Iraq Employment
and Service Programme (SIESP) and the £20.5m Governorates Capacity Building
Project.
28
62. On 3 September, at the request of the MOD, the Current Intelligence Group (CIG)
assessed the impact of the recent Shia violence on the situation in MND(SE).
29
Support to the Iraqi Ministry of Defence was provided by the MOD.
25
Letter Gibbons to Simpson, 23 August 2004. ‘Ad Hoc RMV – Hilary Benn’s Visit to Iraq’.
26
Letter Benn to Prime Minister, 3 September 2004, ‘My Visit to Iraq’.
27
Paper DFID, 4 November 2009, ‘Iraq – DFID Timeline and Financial Commitments: 2003 – 2009’.
28
CIG Assessment, 3 September 2004, ‘Iraq Security: Shia Violence in Multinational Division
29
(South East)’.
207

---
63. The CIG judged that the situation in MND(SE) remained “fragile” and that there
had been considerable loss of public support for the MNF. Most Shia were likely to
continue to support the political process, but their consent depended on expectations
being met, including elections held on schedule and a government that reflected
their majority status.
64. A continuing failure to improve public order, restore public services or create jobs
would also increase disillusionment, risking renewed unrest.
65. During Mr Benn’s visit to Iraq, officials in the British Embassy Office Basra raised
concerns over the operation of the World Bank and UN Trust Funds.
30
66. DFID responded to those concerns on 6 September:
“Basra are right that getting PCO and Trust Fund programmes moving faster is
critical, but not that our contribution to the Trust Funds is pointless.”
67. The Trust Funds had several purposes:
“
to deliver reconstruction on the ground;
to allow donors to pool resources and streamline procedures. This reduces
their overheads, and gives the Iraqis fewer donors with their own priorities
and procedures to negotiate with; and
to encourage the UN and the World Bank to re-engage”.
68. The World Bank and the UN had now started disbursing money from the Trust
Funds, and the Iraqi Minister for Planning and Development Co-ordination had told
Mr Benn that he was “much happier” with collaboration with the World Bank and UN.
69. DFID concluded the Trust Funds had been set up “to deliver medium-term benefits
to Iraq rather than quick fixes”. The test now was delivery.
70. On 9 September, Sir Nigel Sheinwald and Mr David Quarrey, a Private Secretary to
Mr Blair, sent Mr Blair a minute reporting on their recent visit to Iraq, for use in Mr Blair’s
video conference with President Bush later that day.
31
71. The minute stated that a “joined up programme” was needed, including:
an effective counter-insurgency strategy to “regain control of cities in the
Sunni triangle”;
an IIG strategy for Sunni outreach;
support for Prime Minister Allawi’s office; and
Telegram 1 DFID to FCO Baghdad, 6 September 2004, ‘Southern Iraq: Trust Funds’.
30
Minute Sheinwald and Quarrey to Blair, 9 September 2004, ‘Iraq’.
31
208

---
10.2 | Reconstruction: July 2004 to July 2009
economic development. DFID was making good progress “in helping to get the
economic framework right. But hardly anyone thinks that the ordinary Iraqi will
see a major dividend before the elections in January.”
72. During his visit, Sir Nigel met Prime Minister Allawi, who stated that the political,
economic and capacity-building strands were linked; he hoped for significant progress
in each before November.
 A copy of the record of that meeting was sent to Mr Benn’s
32
Principal Private Secretary.
73. Mr Benn told Cabinet on 9 September that during his visit to Baghdad and Basra, he
had been able to “feel the difference” since the transfer of sovereignty.
 Sunni outreach
33
was needed in the South, where the mood was one of “persistent victimisation”.
Reconstruction activity was continuing, but had been adversely affected by the
security situation.
74. During his video conference with President Bush on 9 September, Mr Blair raised
both the need to accelerate Iraqiisation and for enhanced capacity within the IIG, without
which “too much fell on Allawi himself”.
 The existing timelines for improved security and
34
services were “too long” and risked delaying the election.
75. Mr Quarrey wrote to Mr Benn’s Principal Private Secretary on 14 September,
responding to Mr Benn’s 3 September visit report:
“The Prime Minister believes that we must continue to do all we can on this
[reconstruction], and particularly to make sure that ordinary Iraqis see a more
tangible benefit before the elections. We have a particular responsibility to deliver
in the South. We agree that it is sensible to focus UK resources on bilateral
programmes while the multilateral Trust Funds remain ineffective.”
35
76. Mr Blair chaired a meeting of the Ad Hoc Ministerial Group on Iraq on
16 September.
36
77. Mr Blair’s Chairman’s Brief stated that one purpose of the meeting was to:
“… galvanise the key departments and ensure they give Iraq their full attention
in the next 5 months, in order to achieve the necessary results on the ground
in the run-up to elections”.
37
Letter Quarrey to Owen, 9 September 2004, ‘Iraq: Nigel Sheinwald’s Meeting with Allawi, 8 September’.
32
Cabinet Conclusions, 9 September 2004.
33
Letter Phillipson to Adams, 9 September 2004, ‘Prime Minister’s VTC with President Bush,
34
9 September’.
Letter Quarrey to Malik, 14 September 2004, ‘Iraq: Your Secretary of State’s Visit’.
35
Record, 16 September 2004, Ad Hoc Ministerial Group on Iraq meeting.
36
Briefing Cabinet Office, 16 September 2004, ‘Ad Hoc Ministerial Group on Iraq meeting to be held in the
37
Cabinet Room on Thursday 16 September 2004 at 0830: Chairman’s Brief’.
209

---
78. The Group agreed that the MOD, DFID and the FCO would produce specific
suggestions for how progress could be made in Iraq which Mr Blair could put to
President Bush when they next spoke:
“
MOD to make recommendations on how ISF capacity will develop …
DFID to advise on where blockages can [be] removed to speed up the impact
of reconstruction funding.
FCO to advise on what political strategy Allawi should be pursuing and his
capacity to deliver it.”
38
79. Sir Nigel Sheinwald met Dr Rice during his visit to Washington from 16 to
17 September.
 He reported to Mr Blair that he had raised the continuing criticisms of
39
the pace of the US reconstruction effort. Dr Rice had said that she did not understand
why, after many enquiries, there were still blockages. Sir Nigel commented that “there
was no sense that the NSC [National Security Council] was chasing this down, or that
anyone else was”.
80. Prime Minister Allawi visited London on 19 and 20 September.
40
81. Mr Quarrey’s briefing for Mr Blair advised that he might:
offer whatever support Prime Minister Allawi needed for his office;
encourage him to see reconstruction and development as “integral to his wider
political strategy”;
encourage him to associate the IIG very visibly with successes on the ground;
reassure him of UK support for debt relief. Iraq might not get the 95 percent
relief that the IIG and US were pushing for, but the UK wanted relief to be well
above 80 percent; and
encourage him to press the UN and Member States for a substantial increase
in support.
41
82. During his private meeting with Mr Blair on 19 September, Prime Minister Allawi
outlined his four-point strategy for Iraq covering the political process, the economy,
security (the most important aspect of the strategy and his personal focus) and
institution building.
42
Record, 16 September 2004, Ad Hoc Ministerial Group on Iraq meeting.
38
Minute Sheinwald to Prime Minister, 20 September 2004, ‘Visit to Washington’.
39
Letter Sheinwald to Adams, 19 September 2004, ‘Iraq: Prime Minister’s Meeting with Prime Minister
40
Allawi, Sunday 19 September’.
Minute Quarrey to Prime Minister, 18 September 2004, ‘Iraq: Your Meeting with Allawi’ attaching Briefing
41
Cabinet Office, [undated], ‘Briefing Notes for Allawi Visit’.
Letter Sheinwald to Adams, 19 September 2004, ‘Iraq: Prime Minister’s Meeting with Prime Minister
42
Allawi, Sunday 19 September’.
210

---
10.2 | Reconstruction: July 2004 to July 2009
83. Mr Blair asked Prime Minister Allawi whether he had the “infrastructure” around
him to implement IIG policy. Prime Minister Allawi agreed there was a problem. Mr Blair
said that the UK would send “two or three people” to Baghdad to work on the issue. On
reconstruction, Mr Blair said that each project needed to be properly publicised as an
achievement of the IIG and Prime Minister Allawi.
84. Mr Blair, Prime Minister Allawi and several Iraqi Ministers discussed reconstruction
and the economy over lunch.
 The Iraqi delegation said that there had been good
43
progress on reconstruction in recent months, but the pace of delivery was still far too
slow. Nor were donors delivering on their commitments to the World Bank and UN Trust
Funds. Mr Blair said that there needed to be absolute clarity on where the blockages on
funding were.
85. Prime Minister Allawi stressed the need for a generous debt reduction package that
would encourage foreign investment, and asked the UK to play a major role in the Iraq
Grand Port project on the Faw peninsula.
86. An Iraqi delegation led by Prime Minister Allawi held a roundtable meeting on
reconstruction with Mr Straw, Mr Benn and Mr Hoon on 20 September.
44
87. The FCO reported that Prime Minister Allawi’s main theme had been the importance
of progress on reconstruction and its link to security.
88. Mr Mehdi Hafez, Iraqi Minister of Planning and Development Co-ordination, outlined
progress towards an agreement on debt relief. Mr Benn emphasised the importance of
reducing fuel subsidies if Iraq was to secure an IMF programme. Mr Hafez said that the
IIG was committed to reducing subsidies (which he estimated to account for 50 percent
of government expenditure), but there were political sensitivities.
89. During a discussion of the World Bank and UN Trust Funds, Mr Benn encouraged
Prime Minister Allawi to press the UN to deploy staff to Iraq and to speed up
disbursements from their Trust Fund. The Iraqi delegation said that the reluctance of
the World Bank and IMF to engage raised questions about the value of multilateral (as
opposed to bilateral) assistance. Mr Benn said that “DFID was concentrating on bilateral
projects with 2004/05 money”. Mr Hafez confirmed that the IIG was content with the
DFID programme.
90. DFID sent the note on how to speed up reconstruction funding requested at
the 16 September meeting of the Ad Hoc Ministerial Group on Iraq to No.10 on
23 September, to inform a telephone conversation between Mr Blair and President Bush
the following day.
45
Letter Quarrey to Owen, 19 September 2004, ‘Iraq: Prime Minister’s Lunch with Allawi, 19 September’.
43
Telegram 73 IPU to Baghdad, 20 September 2004, ‘Iraq: Visit of Allawi: Meeting with Foreign Secretary,
44
Mr Benn and Mr Hoon’.
Letter Drummond to Quarrey, 23 September 2004, ‘VTC with President Bush’ attaching Briefing DFID,
45
[undated], ‘Prime Minister’s Video-Conference with President Bush’.
211

---
91. The DFID note advised that:
Iraq’s infrastructure had now been “stabilised” and some improvements had
been made. But Iraqi citizens did not see that; it was vital for security that visible
progress was made fast, and that the IIG told Iraqi citizens what was being
achieved.
There were “very few” PCO staff in the South. Could the US speed up the
deployment of PCO staff, and give USAID a bigger role?
Iraqi systems were not yet working. The US and UK needed to press Prime
Minister Allawi to get Iraqi oil revenues into the provinces, and press the UN and
World Bank to deploy experts.
92. Mr Quarrey’s briefing for Mr Blair suggested that he could refer to Prime Minister
Allawi’s concern about the pace of delivery on reconstruction.
46
93. In a telephone conversation with President Bush on 24 September, Mr Blair set out
three priority issues, as discussed with Prime Minister Allawi:
the need to strengthen Prime Minister Allawi’s office;
accelerating work to show the ISF had capacity to act; and
increasing the pace of development activity.
47
94. On 1 October, in response to a request for advice from Mr Benn’s Private Secretary
on the World Bank and UN Trust Funds, a DFID official advised that:
“… implementation is proceeding, but not as quickly as we would wish or had
anticipated when we decided to contribute to them in February”.
48
95. There was as yet insufficient evidence to decide whether DFID should make
further contributions to the Trust Funds. Equally, withdrawing UK funds from the Trust
Funds would be difficult to justify and would undermine UK efforts to persuade other
donors (especially those not present on the ground in Iraq) to contribute to the
reconstruction effort.
96. Iraqi Deputy Prime Minister Dr Barham Salih presented the IIG’s National
Development Strategy (NDS) at the third meeting of the International Reconstruction
Fund Facility for Iraq (IRFFI) Donor Committee in Tokyo on 14 October.
49
Minute Phillipson to Prime Minister, 23 September 2004, ‘Phonecall with President Bush,
46
24 September’.
Letter Quarrey to Owen, 24 September 2004, ‘Prime Minister’s Phone Conversation with
47
President Bush, 24 September’.
Minute DFID [junior official] to DFID [junior official], 1 October 2004, ‘Iraq Trust Funds: Secretary
48
of State’s Conversation with Ann Clwyd MP’.
Telegram 181 Tokyo to FCO London, 15 October 2004, ‘Iraq: Tokyo Donor Committee Meetings,
49
13-14 October’.
212

---
10.2 | Reconstruction: July 2004 to July 2009
97. The NDS set out the social and economic reforms that the IIG intended to pursue,
but did not prioritise those reforms or include plans for their implementation.
50
98. Dr Salih told the meeting that this was the first time a sovereign Iraqi Government
had presented its own vision of Iraq’s future to the international community.
 Iraq
51
needed a quick agreement on debt relief and faster implementation of pledges made by
donors at the Madrid Donor Conference, in line with the priorities outlined in the NDS.
99. The IMF and World Bank presented a “relatively positive” assessment of Iraq’s
economy, including higher than expected oil revenues.
100. At the meeting, Mr Jim Drummond, DFID Director Iraq, underlined the importance
of Iraqi leadership of the reconstruction process, urged faster disbursement from the
World Bank and UN Trust Funds, and encouraged more donors to contribute to them.
101. The British Embassy Tokyo reported that the international community had come
together behind “a good Iraqi-led strategy”. Germany and France had engaged “more
than previously, but not yet with significant support”. There had been no significant new
pledges, but that was not surprising given the US$32bn pledged at Madrid and rising
Iraqi oil revenues.
102. Mr Quarrey described the meeting to Mr Blair as “important and successful”.
 In
52
response, Mr Blair asked for a DFID paper on how the UK could ensure that the meeting
led to a visible acceleration in the delivery of reconstruction on the ground.
53
103. The IIG’s successor, the Iraqi Transitional Government (ITG), launched a revised
NDS in July 2005.
Reconstruction in areas regained from insurgent control, and Fallujah
104. Section 9.3 describes how, in the autumn of 2004, the IIG and the Multi-National
Force – Iraq (MNF-I) reviewed the possibility of further military action to gain control of
Fallujah from the Sunni insurgency, including the debate between the US and UK on
how and when to take action.
105. A DFID official advised Mr Benn in advance of the 14 October meeting of the
Ad Hoc Ministerial Group on Iraq that the FCO and “UK military” were arguing against
an early clearance operation in Fallujah and for a “hybrid of security (cordon, precision
strikes) and political/economic initiatives … and giving these time to work”.
54
The Iraqi Strategic Review Board, September 2004, National Development Strategy 2005-2007.
50
Telegram 181 Tokyo to FCO London, 15 October 2004, ‘Iraq: Tokyo Donor Committee Meetings,
51
13-14 October’.
Minute Quarrey to Blair, 15 October 2004, ‘Iraq Update’.
52
Letter Quarrey to Naworynsky, 18 October 2004, ‘Iraq’.
53
Minute DFID [junior official] to APS/SoS [DFID], 13 October 2004, ‘Iraq: Ad Hoc Ministerial Group
54
Meeting on 14 October’.
213

---
106. Mr Benn was also advised that there had been a “breakthrough” in the relationship
between the PCO and DFID in the South, with the PCO accepting and welcoming
the Technical Advisory Team (TAT). After many delays, the PCO had begun work
in the South.
107. Following talks in London, DFID was also seeking to work more closely with
MND(SE), to “synchronise” UK reconstruction and security efforts. MND(SE) was
“struggling” to disburse its QIPs and CERPs funds (totalling US$25m), largely because
of a lack of capacity. The TAT might be able to assist. A DFID team would visit Basra to
continue discussions.
108. The 14 October meeting of the Ad Hoc Ministerial Group on Iraq was briefed that
the US military was planning military action in Fallujah.
55
109. The Ad Hoc Ministerial Group on Iraq agreed that an operation to clear Fallujah
was right in principle but the UK should try to persuade the US to give Prime Minister
Allawi time to improve the political environment.
110. Mr Chaplin reported by telegram on the same day that the US planned to spend
US$3.4bn on “rapid reconstruction” in 18 “strategic cities” (defined as major population
or religious centres and real or potential areas of insurgency) in the run-up to the
Iraqi elections, including US$1.4bn in Baghdad and US$316m in Basra.
The US had
56
allocated US$75m for Fallujah, but all work there was currently suspended. The initiative
covered PCO, USAID and CERPs projects.
111. Mr Chaplin’s report prompted Mr Blair to request an update on developments in
Najaf.
 Mr Quarrey directed that request to the Cabinet Office.
57
58
112. Sir Nigel Sheinwald and Dr Rice discussed Iraq on 22 October.
 Sir Nigel reported
59
that they had agreed that not enough was being done in towns where the IIG had
regained control from insurgents. Dr Rice had said that she had (again) asked the NSC
to find out why reconstruction funding was moving so slowly.
113. Mr Blair discussed progress on reconstruction, especially in key cities after military
action, with Prime Minister Allawi by telephone on the same day.
 Prime Minister Allawi
60
said that effective reconstruction would have a positive impact on the security situation.
Mr Blair agreed and said he would mention it to President Bush. Mr Quarrey’s record of
the conversation was copied to Mr Benn’s Principal Private Secretary.
Record, 14 October 2004, Ad Hoc Ministerial Group on Iraq meeting.
55
Telegram 280 Baghdad to FCO London, 14 October 2004, ‘Iraq: Reconstruction Projects in
56
Strategic Cities’.
Letter Quarrey to MOD [junior official], 18 October 2004, ‘Iraq’.
57
Letter Quarrey to MOD [junior official], 18 October 2004, ‘Iraq’.
58
Letter Sheinwald to Adams, 22 October 2004, ‘Conversation with US National Security Adviser,
59
Friday 22 October’.
Letter Quarrey to Wilson, 22 October 2004, ‘Iraq: Prime Minister’s Conversation with Allawi, 22 October’.
60
214

---
10.2 | Reconstruction: July 2004 to July 2009
114. Mr Quarrey passed the Cabinet Office’s paper on reconstruction in Najaf and other
key cities and the DFID paper on how to accelerate reconstruction on the ground in the
wake of the Tokyo Donor Conference to Mr Blair on 22 October.
61
115. The Cabinet Office paper concluded that “the general impression is that, as yet,
there is no systematic or co-ordinated approach to these key cities”.
 It identified a
62
number of lessons, including:
It was possible for political deals to hold long enough for the IIG/PCO to
deliver enough reconstruction to start building public support and discredit the
insurgents.
There needed to be a sufficient continuing ISF presence for the IIG to remain
in control and to facilitate reconstruction.
IIG and to some extent PCO capacity to deliver reconstruction quickly was very
limited. CERPs delivered impact most quickly.
116. The DFID paper on the follow-up to the Tokyo donors meeting advised that while
the procedural obstacles to spending US and Trust Fund allocations had largely been
overcome, the security situation was worse.
 To “get round” that problem, there was
63
now a greater emphasis on using Iraqi systems and contractors. In that context, to
accelerate the pace of reconstruction, the UK needed to:
Persuade the World Bank and UN at the top level to move fast, and to send
development specialists to Iraq. Mr Benn had lobbied the UN Secretary-General
Kofi Annan on 19 October.
Provide funding and security for World Bank and UN liaison staff. DFID funded
and housed one liaison officer for each of the World Bank and UN in Baghdad,
and was considering funding a UN liaison officer in Basra.
Support the PCO. The Head of the US Iraq Reconstruction and Management
Office (IRMO) had told the UK that he wanted to work closely with the UK, but
that he did not want UK staff in the PCO.
117. Mr Quarrey commented on the DFID paper:
“Lots of good points here about the UN and World Bank. But nothing on our bilateral
programme and what more we might be able to do with that …”
64
Minute Quarrey to Prime Minister, 22 October 2004, ‘Iraq Reconstruction’.
61
Paper Cabinet Office, 22 October 2004, ‘Iraq: Developments in Key Cities’.
62
Paper DFID, [undated], ‘Tokyo Follow-up’.
63
Minute Quarrey to Prime Minister, 22 October 2004, ‘Iraq Reconstruction’.
64
215

---
118. Mr Quarrey commented on the Cabinet Office paper:
“Not an encouraging picture … It looks like we are a long way from the sort of
integrated political/security/reconstruction packages for these key cities that we,
the US and Allawi keep talking about.
“We must do better on this. The lack of any reference in the DFID note to this key
issue is striking.”
119. Mr Blair replied: “We need to get tougher with DFID on this. Let me minute
Hilary [Benn]. It’s not good enough.”
65
120. Major General Andrew Farquhar, the British Deputy Commanding General of
Operations in the Multi-National Corps – Iraq (MNC-I), reported on 24 October that the
US had allocated US$7m from CERPs for projects in the immediate aftermath of military
operations in Fallujah.
66
121. Mr Blair wrote to Mr Benn on 26 October:
“I remain concerned that actual delivery of reconstruction on the ground is far
too slow …
“We must accelerate the pace of reconstruction, not least to support the political
process as we head towards the elections. The note [on the Tokyo donors meeting]
includes some good ideas on pressing the UN and World Bank. But we also need
to increase the impact of your bilateral programme in the short term. And we need
to find more effective ways of getting the US to spend their funds more quickly and
with greater impact.
“I am particularly concerned about the lack of follow-through on reconstruction in
those cities and towns where the IIG, with MNF support, has regained control from
insurgents (e.g. Najaf, Samarra, Tal Afar). These are, of course, not in the MND(SE)
region where our spending is concentrated. But DFID has considerable experience
of post-conflict situations which I would like to see us using across Iraq.”
67
122. Mr Hoon briefed the 28 October meeting of the Ad Hoc Ministerial Group on Iraq
on US military plans for a “short, sharp campaign” in Fallujah.
68
123. At the meeting, Mr Benn said that DFID continued to press the PCO, but a recent
proposal to second a UK development adviser to the PCO had been turned down by the
US. It was difficult for the UK to offer additional assistance in cities like Fallujah “as the
US was already engaged and sufficient funds were available”.
Manuscript comment Blair on Minute Quarrey to Prime Minister, 22 October 2004, ‘Iraq Reconstruction’.
65
Telegram 301 Baghdad to FCO London, 24 October 2004, ‘Iraq: Fallujah: Military Preparations:
66
ISF Numbers and Capability’.
Minute Prime Minister to Secretary of State for International Development, 26 October 2004, [untitled].
67
Minutes, 28 October 2004, Ad Hoc Ministerial Group on Iraq meeting.
68
216

---
10.2 | Reconstruction: July 2004 to July 2009
124. Mr Benn reported that he had spoken to UN Secretary-General Annan, and thought
it unlikely the UN would deploy more staff to Iraq before the elections (the UN currently
had two officers in Iraq, one supported by DFID).
125. Mr Benn said that he would be happy to help the MOD with funding for QIPs if it
was better able to implement projects than civilian experts.
126. Cabinet Office, DFID, FCO and MOD officials met on the same day to consider,
at No.10’s request, how to “push forward” PCO reconstruction efforts.
 The meeting
69
agreed that the UK should:
increase efforts to monitor PCO activity across Iraq, although with a focus on
MND(SE); and
make an “open-ended” offer of support to the US for PCO programmes across
Iraq (not just in the South).
127. By 29 October, preliminary airstrikes against targets in the Fallujah area
had begun.
70
128. Mr Quarrey advised Mr Blair on 2 November that “planning for the post-conflict
phase remains inadequate, and the US now seem resigned to this”.
71
129. A DFID official based in Basra advised Mr Drummond on 3 November that PCO
projects in the South remained “almost invisible” to the general public, and that Iraqi
engagement in and influence on PCO operations appeared to be minimal.
72
130. Mr Blair met Prime Minister Allawi in Brussels on 5 November.
131. In preparation for the meeting, Mr Quarrey provided a list of “points that Allawi
needs to cover before he approves any military action” in Fallujah.
 Those included
73
“the follow-up package of political and economic measures”. The US said they had
funding ready, but the IIG’s own preparations looked inadequate. Prime Minister Allawi
had to take responsibility for those preparations.
132. At the meeting, Mr Blair said that:
“… he [Prime Minister Allawi] knew the military commanders were keen to move
now. But it was vital that we balanced the political and military priorities. Unless
there was an argument for an immediate move, then he believed we needed to take
Letter Cabinet Office [junior official] to Drummond, 28 October 2004, ‘Iraq: Monitoring and Accelerating
69
PCO Disbursement’.
Minute Dowse to Sheinwald, 29 October 2004, ‘Iraq Update – 29 October’.
70
Minute Quarrey to Prime Minister, 2 November 2004, ‘Fallujah’.
71
Minute DFID [junior official] to Drummond, 3 November 2004, ‘PCO’.
72
Minute Quarrey to Blair, 4 November 2004, ‘Iraq: Breakfast with Allawi’.
73
217

---
…
the necessary time to exhaust all avenues of dialogue with the Sunnis
 We also
needed to set out a package of reconstruction measures.”
74
133. Following authorisation by Prime Minister Allawi, offensive operations began in
Fallujah on 8 November.
75
134. Mr Chaplin described the UK’s involvement in that decision for the Inquiry:
“Our main involvement and the main thing we emphasised afterwards was that if
there had to be military action, then the [Iraqi] Government needed to organise itself
to ensure there was rapid follow-up, looking after displaced people, returning them
as soon as possible, looking after the humanitarian aspects. And the part of the
DFID team that was working closely with the Ministry of Health was heavily involved
in that …”
76
135. Mr Benn replied to Mr Blair’s letter of 26 October on 10 November.
 He wrote:
77
“I share many of your concerns about the pace of reconstruction and development in
Iraq. However, we should take encouragement from the Iraqi Interim Government’s
National Development Strategy, the extra resources (about US$3bn) that the high oil
price gives them, and the new arrangements that Allawi is making in his own office,
with DFID advice, to lead reconstruction …
“Security is much more difficult than we anticipated and is getting worse around
Baghdad. Many contractors, including those that we regularly use to work in
post-conflict environments such as Crown Agents, are unwilling to send staff outside
Baghdad or Basra at present. This is affecting all donors. But we can do more. Our
£6m employment generation project will start to create jobs this month … I have
also allocated £10m to support essential services – water, sanitation and power – in
South-Eastern Iraq. We will top this up if necessary. We are working closely with UK
forces: DFID’s technical expertise is available to help them implement their Quick
Impact Projects, and military liaison teams will help us to make our projects happen.
We will talk to MOD about resources, as we look for other ways to maximise impact.”
136. Mr Benn also highlighted DFID’s support for the elections, and his decision not to
channel further funds through the UN and World Bank Trust Funds.
Letter Phillipson to Adams, 5 November 2004, ‘Iraq: Prime Minister’s Discussion with Iyad Allawi,
74
5 November 2004’.
CNN World, 9 November 2004, Battle for Falluja under way.
75
Public hearing, 7 December 2010, page 19.
76
Letter Benn to Blair, 10 November 2004, [untitled].
77
218

---
10.2 | Reconstruction: July 2004 to July 2009
137. On Mr Blair’s suggestions that the UK needed to find more effective ways of getting
the US to spend its funds more quickly and with greater impact, and that DFID should
use its experience of post-conflict situations across Iraq (not just in the South), Mr Benn
responded:
“We will get closer to the Project Contracting Office (PCO). Our Basra sector
specialists are working with the PCO there, and the DFID Office in Baghdad has
close relations with PCO counterparts in Baghdad, including the new (good) head,
Bill Taylor. He has declined our offer of a senior reconstruction specialist but we
are offering technical help instead. This could help the PCO implement effective
reconstruction projects in areas where the Iraqi Interim Government regains control
from the insurgents.”
138. Mr Benn’s reply highlighted a number of decisions taken before Mr Blair wrote his
letter:
DFID’s projects to create jobs and provide essential services in the South had
been announced in early September.
The decision not to channel further funds through the UN and World Bank Trust
Funds had also been made in early September.
DFID’s work with MND(SE) to help implement QIPs was under way by
13 October.
139. The FCO advised the British Embassy Baghdad on 15 November that, following
the meeting of officials on 28 October which had agreed that the UK should make an
open-ended offer of support to the PCO, DFID had confirmed that it could provide:
technical expertise (for example a water or health expert); and
expertise on post-conflict reconstruction, to help deliver reconstruction in cities
and towns where the IIG had regained control.
78
140. On 16 November, following a visit to Fallujah, Lieutenant General John Kiszely, the
Senior British Military Representative, Iraq, reported to the MOD and IPU that the scale
of the damage to buildings dramatically outstripped the figures that the US had used in
its press statement.
 Soldiers in Fallujah had told him that between 90 and 95 percent
79
of civilians had left before the fighting had started.
141. General George Casey, MNF-I, had decreed that MNF-I’s main effort should be
humanitarian assistance and reconstruction, and had appointed Lt Gen Kiszely “in
charge of reconstruction”.
Telegram 126 FCO London to Baghdad, 15 November 2004, ‘Iraq Reconstruction: UK Assistance for
78
the PCO’.
Minute Crompton to Private Secretary [FCO], 16 November 2004, ‘Iraq: Fallujah’.
79
219

---
142. Mr Crompton reported to Mr Straw’s Private Secretary that Lt Gen Kiszely was
“calm, but clearly taken aback by the damage he had seen”. The IPU was:
“… in touch with DFID to see whether they can assist with the humanitarian effort,
and are feeding in some ideas to Kiszely on how best to approach the reconstruction
task, using lessons learnt in Kosovo and elsewhere”.
143. The Annotated Agenda for the 18 November meeting of the AHMGIR reported
Lt Gen Kiszely’s conclusions, and that the Red Cross and Red Crescent were being
allowed into the city.
 At least US$58m had been earmarked for reconstruction. The
80
IIG estimated that there were 250,000 Internally Displaced People (IDPs) from Fallujah,
about 95 percent of whom were staying with family or friends. The Iraqi Ministry of
Health reported that there were “no major humanitarian problems”.
144. The Annotated Agenda stated that Prime Minister Allawi had established a Cabinet
Reconstruction Committee, whose first tasks would be to co-ordinate reconstruction
spending in cities won back from insurgent control and to spend US$200m of Iraqi
money for emergency reconstruction in the period up to the elections. DFID advisers
were “linked in well” and assisting the Committee.
145. The Annotated Agenda also stated that the PCO had declined DFID’s offer to
“second a senior reconstruction specialist or more technical help in Baghdad”.
146. Gen Walker told the meeting there had been a slow start to reconstruction in
Fallujah.
 That was a failure of the IIG and, in part, non-military US agencies. There
81
was no indication of an immediate humanitarian crisis.
147. Mr Benn said that he was prepared to provide Lt Gen Kiszely with a reconstruction
adviser, if one was required.
148. Mr Benn reported that more generally, security remained a significant constraint
on reconstruction, but that DFID programmes were progressing relatively well.
149. The AHMGIR agreed that:
DFID and the FCO should press the UN to deploy a senior, full-time
development expert to Baghdad;
DFID and the FCO should keep pressing the PCO for credible information
on reconstruction projects;
Mr Straw and Mr Blair should speak to their French counterparts about the
importance of agreeing a Paris Club debt deal;
Mr Benn should prepare a note on reconstruction activity in MND(SE) and
on wider reconstruction issues; and
the FCO and DFID should prepare a note on why the PCO was proving slow
to deliver reconstruction.
Annotated Agenda, 18 November 2004, Ad Hoc Group on Iraq Rehabilitation meeting.
80
Minutes, 18 November 2004, Ad Hoc Group on Iraq Rehabilitation meeting.
81
220

---
10.2 | Reconstruction: July 2004 to July 2009
150. Sir Nigel Sheinwald spoke to Dr Rice later that day, and expressed his concern that
humanitarian and reconstruction efforts in Fallujah had been slow to get off the ground.
82
He reported that Dr Rice shared that concern, but thought that some humanitarian
assistance was now getting into the city, and “everyone was adamant” that there was
no humanitarian crisis.
151. The FCO advised No.10 on 19 November that there were “plenty of resources
available” for Fallujah’s reconstruction.
 The IIG’s response was poorly co-ordinated.
83
The UK would monitor the IIG’s response, and would feed in advice on the best way to
reconstruct houses damaged in the fighting. The UK had advised Lt Gen Kiszely that the
most effective approach would be to give each family a sum of money “for them to go
and see to the re-building themselves”. That approach, used in Kosovo, would ensure
that the money was ploughed back into the Fallujah economy and secure residents’
“buy-in” to reconstruction.
152. In his weekly report to Gen Walker on 21 November, Lt Gen Kiszely advised
that planning for reconstruction was “well developed” within the US Embassy, led by
IRMO, but almost none had taken place in the IIG.
 Prime Minister Allawi was now
84
“cracking the whip”, which should lead to greater Iraqi Ministerial engagement. With so
few inhabitants in the city, there was no humanitarian crisis, and the “vast majority” of
displaced people had found accommodation with extended family or friends. There were
some small tented camps around Fallujah, to which NGOs were delivering supplies. The
immediate priorities were to clarify the situation and co-ordinate activity; in the absence
of the IIG, that fell to MNF-I.
153. Lt Gen Kiszely also advised that his appointment as “MNF-I co-ordinator for
humanitarian assistance and reconstruction” had been prompted by Gen Casey’s
concern about the scale of the humanitarian and reconstruction challenge.
154. Lt Gen Kiszely told the Inquiry:
“… by the end of November/early December, it was quite clear that this [military]
operation was going to be successful. And the big concern for the Americans
was what was going to happen afterwards: was this going to be a microcosm, if
you like, of the campaign as a whole in which the reconstruction phase was not
properly planned for, or were they going to ensure that it was properly planned
and managed? And they very much focused on getting this right.”
85
Letter Sheinwald to Adams, 18 November 2004, ‘Conversation with US National Security Adviser:
82
18 November 2004’.
Letter Owen to Phillipson, 19 November 2004, ‘Iraq: the Political Process – Prospects for Elections
83
and Sharm El-Sheikh’.
Minute Kiszely to CDS, 21 November 2004, ‘SBMR-I’s Weekly Report (138) of 21 Nov 04’.
84
Public hearing, 14 December 2009, page 16.
85
221

---
155. President Bush and Mr Blair spoke by video conference on 30 November.
Mr Blair’s briefing stated that he should raise Prime Minister Allawi’s concern that
humanitarian and reconstruction assistance was not getting into Fallujah and other key
spots quickly enough.
86
156. During the video conference, Mr Blair said that Fallujah “had gone well” and the
story of what US forces had found there – including evidence of torture chambers –
should be put into the public domain.
 He suggested that the operation had “sent a clear
87
message that the insurgents could not win”.
157. The record of the video conference did not include any reference to the
humanitarian and reconstruction effort in Fallujah or other “key spots”.
158. Ms Margaret Aldred, Deputy Head Overseas and Defence Secretariat in the
Cabinet Office, advised Sir Nigel Sheinwald on 1 December, in the context of a
report on the situation in Fallujah, that she had received reports that a DFID adviser
and a DFID-funded consultant attached to the Cabinet Reconstruction Committee
were beginning to make a difference.
 Those individuals had been re-deployed from
88
within Iraq.
89
159. A second DFID-funded consultant, Dr Gilbert Greenall, had arrived in Iraq that day
to advise Lt Gen Kiszely on the phased return of IDPs to Fallujah.
90
160. Mr Suma Chakrabarti, the DFID Permanent Secretary, and Mr Drummond reported
to Mr Benn on 13 December:
“DFID provides the core of Allawi’s co-ordination team on Fallujah …
“Fallujah demonstrates that neither the IIG nor the US thought through the
humanitarian aspects of military actions, though they had allocated money for
reconstruction. For the next few weeks we need to have immediate post-conflict
expertise in the DFID Office in Baghdad …”
91
161. Mr Benn told the 16 December meeting of the Ad Hoc Ministerial Group on Iraq
that the IIG, with the support of DFID advisers, had put together a package of basic
humanitarian support and funds for the reconstruction of homes in preparation for the
return of IDPs.
 Ministers agreed to follow developments closely.
92
Minute Phillipson to Prime Minister, 29 November 2004, ‘VTC with President Bush, 1220 – 1300
86
30 November’.
Letter Quarrey to Owen, 30 November 2004, ‘Prime Minister’s VTC with President Bush, 30 November:
87
Iraq, Syria and Iran’.
Minute Aldred to Sheinwald, 1 December 2004, ‘Iraq’.
88
Letter Cabinet Office [junior official] to Asquith, 3 December 2004, ‘Iraq Senior Officials Group’.
89
Minute Aldred to Sheinwald, 1 December 2004, ‘Iraq’.
90
Minute Chakrabarti/Drummond to Secretary of State [DFID], 13 December 2004, ‘Iraq Visit,
91
6-8 December’.
Minutes, 16 December 2004, Ad Hoc Ministerial Group on Iraq meeting.
92
222

---
10.2 | Reconstruction: July 2004 to July 2009
162. Section 9.3 describes the impact of operations in Fallujah on security and the
political process.
163. Five months later, on 12 May, the British Embassy Baghdad reported that Embassy
staff had visited Fallujah, hosted by US forces.
 The scale of destruction was apparent,
93
but there was also progress:
Between 90,000 and 150,000 of Fallujah’s estimated 240,000 inhabitants
had returned.
All water treatment plants, tanks and pipes had been restored and two new
pumping facilities had been installed.
Electricity had been restored to between 80 and 100 percent of the main
residential area, but only to between 0 and 40 percent of the “industrial south”.
Of the city’s 69 schools, 38 were open and 15 would open by the end of the
month. “Huge progress” had been made in restoring healthcare.
164. The Embassy commented:
“This may be an over-rosy view of developments in Fallujah, it was a determined
PR [public relations] effort, but the signs of life around the town spoke volumes.
Likewise, the prominence of Iraqis throughout the visit and US willingness to let
them lead was not what we had expected. Congratulations to the US Marines!”
Lessons from Najaf
In late January 2005, Dr Greenall and another DFID-funded consultant visited Najaf to
review progress since the US intervention in August 2004 and to identify lessons for future
operations in Iraq.
94
Their assessment was more positive than the Cabinet Office paper of 22 October 2004.
The consultants reported that although the short conflict had resulted in considerable
damage, there was a “permissive environment” on the streets. That could be attributed
largely to an effective post-conflict assistance strategy: US$48m had been allocated
for projects and “social payments”, with 156 projects being completed in the first
100 days after the uprising. Funding had come from CERPs, PCO funds re-directed
away from large infrastructure projects, and USAID. The impact on the local economy
had been substantial.
A key strength of the US military’s approach had been to engage directly with the
Provincial Governor and the Mayor to ensure local ownership. The Governor remained
frustrated, however, by the level of support from the Iraqi Government.
Telegram 4393/05 Baghdad to FCO London, 12 May 2005, ‘Impressions of Fallujah: 12 May’.
93
Telegram 85 Baghdad to FCO London, 3 February 2005, ‘Iraq: Post-Conflict Reconstruction Lessons
94
from Najaf’.
223

---
Ms Lindy Cameron, the Head of DFID Baghdad, commented on the report that while Najaf
was not typical of “problem cities”:
“Nevertheless, it demonstrates the importance of having in place a clear strategy
for immediate post-conflict support so that the military can help civilian authorities
get instant access to funds, take immediate action, get essential services running
and put money into the local economy, starting a virtuous circle leading in the
longer-term (as in Najaf) to a conducive environment for large infrastructure projects,
re-establishment of normal market mechanisms and a benign force profile.”
There are no indications that Mr Blair or Ministers saw the report.
Agreement on debt relief for Iraq
165. Section 10.3 describes the UK Government’s role in negotiations towards a deal
to reduce Iraq’s debt.
166. On 24 September, as part of those negotiations, the Iraqi Government undertook
to begin to reduce fuel subsidies by the end of the year, and to raise prices to “cost
recovery levels” by the end of 2009.
95
167. On 21 November, Paris Club creditors agreed to reduce Iraq’s official debt by
80 percent (a reduction of US$31.1bn).
 The deal would be delivered in three stages:
96
30 percent immediately; 30 percent on IMF approval of a Stand-By Arrangement
(expected to be in 2005); and 20 percent on completion of the Stand-By Arrangement
(in 2008). Paris Club creditors also agreed generous terms for the repayment of the
residual debt.
168. Under the agreement, the UK wrote off US$1.39bn (£954m) in Iraqi debt
(£337m in UK financial year 2004/05, £337m in 2005/06 and £280m in 2008/09).
97
169. A Treasury briefing produced for Mr Brown stated that the deal represented an
important success for the international community, demonstrating an ability to act
together on an issue as divisive as Iraq.
98
Taking the strain in the South, early 2005
170. Section 9.3 describes the UK’s continuing efforts to support the political process in
Iraq, and in particular ensuring that elections could take place on schedule at the end of
January 2005.
IMF Staff Report, September 2004, Iraq: Use of Funds – Request for Emergency Post-Conflict
95
Assistance.
Briefing Treasury, [undated], ‘Brief: Meeting with Barham Saleh, Deputy Prime Minister of Iraq’
96
Letter Cabinet Office [junior official] to Aldred, 13 September 2011, ‘Iraq Inquiry: Request for Further
97
Information on Funding’.
Briefing Treasury, [undated], ‘Brief: Meeting with Barham Saleh, Deputy Prime Minister of Iraq’.
98
224

---
10.2 | Reconstruction: July 2004 to July 2009
171. At the end of 2004, in response to continuing concerns that the US and the PCO
did not see the South as a priority and that the World Bank and UN Trust Funds were
not yet fully operational, DFID assessed that it would have to “take more of the strain
bilaterally in 2005”, in particular on infrastructure and job creation in the South.
172. On 18 November, in response to a request from the FCO, Mr Collis reported on
the state of reconstruction in the South.
 The IIG was not funding any significant capital
99
projects in the South and the PCO remained a “weak and Baghdad-centric” organisation.
PCO projects would not have a significant impact on service delivery until well into 2005.
173. DFID officials met senior PCO officials in Baghdad on 2 December.
 The British
100
Embassy Baghdad reported that, in response to the security situation, the PCO planned
to focus on “low-hanging fruit” (visible projects such as repairs to schools and clinics)
at the expense of major longer-term reconstruction projects and building Iraqi capacity.
In addition, if the US Congress did not agree further funding for CERPs, the PCO was
likely to reallocate funds from stable to less secure areas.
174. The Embassy concluded: “We need to fight to keep PCO funding in the South.”
175. At the 9 December meeting of the AHMGIR, Ministers commented that the PCO
was “large and unwieldy” and faced a difficult balance between quick fixes and long-term
reconstruction.
 UK influence was limited: the PCO was a US organisation following US
101
rules “though it was sometimes open to UK advice”. Much of its effort was being pulled
.
into Fallujah and away from the South
176. Mr Chakrabarti and Mr Drummond visited Baghdad and Basra from 6 to
8 December to review DFID’s programmes and assess priorities for 2005.
102
177. Their 13 December report to Mr Benn advised that with the PCO “diverted” to
immediate reconstruction work in cities around Baghdad, and the World Bank and
UN Trust Funds not yet fully operational, DFID would “have to take more of the strain
bilaterally in 2005”. DFID’s resources were, however, limited and “must be used to
support Iraqi initiatives and strengthen their capacity”.
178. On PCO activity in the South, the report stated:
“As junior partners in the coalition, our ideas are listened to, but our influence over
US spending will remain limited. We need to face up to the fact: the South will not
be a strategic priority for the US.”
Telegram 200 Basra to FCO London, 18 November 2004, ‘Southern Iraq: Essential Services,
99
Reconstruction’.
Telegram 455, Baghdad to FCO London, 5 December 2004, ‘Iraq: Project Contracting Office (PCO):
100
Changing Priorities’.
Minutes, 9 December 2004, Ad Hoc Group on Iraq Rehabilitation meeting.
101
Minute Chakrabarti/Drummond to Secretary of State, 13 December 2004, ‘Iraq Visit, 6-8 December’.
102
225

---
179. The report identified possible DFID priorities for 2005:
continued support to strengthen Iraq’s public administration, including Prime
Minister Allawi’s office;
continued support for economic reform, including a renewed effort to get the
World Bank and IMF back into Baghdad. Their officials could be accommodated
in the “DFID wing” of the British Embassy;
substantial, additional support for job creation and “emergency infrastructure
works” in the South; and
a further contribution to the UN and World Bank Trust Funds when there was
hard evidence of delivery, and the UN was back on the ground.
180. Copies of the report were sent to the FCO, the MOD, No.10, the Cabinet Office
and officials in Baghdad and Basra.
181. DFID’s intentions were set out in more detail in a minute from Mr Drummond to
a DFID official two days later:
“… we will have to take more of the strain in 2005 on infrastructure. The TAT team
and others should begin thinking now about what can be done with UK resources
(possibly up to £50m) so that there are ideas ready to be appraised.”
103
182. That work would culminate in the agreement by Mr Benn of the £40m Iraq
Infrastructure Services Programme (IISP) in late February 2005.
183. Mr Chaplin reported on 15 December that the US review of IRRF2 had reduced
funding for water and power projects in Basra.
 The reallocations had not been based
104
on Iraqi advice or geographical need, but on a US desire to avoid breaching existing
contracts and the PCO’s belief that larger projects in the South could be more easily
funded by other donors.
184. Major General Jonathon Riley, General Officer Commanding (GOC) MND(SE),
reported on 20 December:
“Wherever I go … I am greeted by Provincial Governors and others with the same
set of complaints: that the promises made to them have been broken, that things are
getting worse not better … The increase in my QIPS delegation is massively helpful,
but the amount of money cannot change the overall situation. DFID is working really
very efficiently, and we have a real partnership here, but this is not natural territory
for them and again, their funds will not change the overall situation. The solution
lies with Central Government in Baghdad and the PCO, which together have raided
major projects in the South, such as the electricity programme, in order to fund
security. I have tried to point out that investing in the South now, where the security
Minute Drummond to DFID [junior official], 15 December 2004, ‘Iraq: Visit Follow-up’.
103
Telegram 475 Baghdad to FCO London, 15 December 2004, ‘Iraq: PCO Water and Power Sectors’.
104
226

---
10.2 | Reconstruction: July 2004 to July 2009
situation is benign will do two things: first, reward good behaviour and encourage
further progress … and secondly, benefit the whole of the country …
“I am not responsible for economic regeneration, and I do not intend to become
a bore about it – so I mention it now – once, and once only. But since I am not
responsible, I cannot be made accountable for the failures of others.”
105
185. Mr Blair visited Baghdad on 21 December.
106
186. Mr Chaplin’s briefing for Mr Blair described an Iraqi Government that was
struggling to maintain supplies of power and fuel as the insurgency took hold, and that
had abandoned hope of visible progress on reconstruction before the elections.
107
187. During his visit, Mr Blair asked Gen Riley for advice on “big-ticket” items that might
make a difference to the economy and essential services of southern Iraq.
108
188. Mr Quarrey’s report on the visit recorded that “Iraqiisation and political outreach
were key themes”.
 Mr Blair remained “very concerned about the slow pace of
109
reconstruction spending, especially in the South” and about the funding available for
Iraqiisation, and wanted the UK to make a major effort to secure greater funding for
both, in particular from the US. A copy of the report was sent to Mr Benn’s Principal
Private Secretary.
189. Gen Riley responded to Mr Blair’s request for big-ticket projects on 3 January
2005, in his weekly report to Gen Walker.
 He proposed that, at a minimum, the UK
110
should aim to build a 200 megawatt (MW) gas turbine plant in the South at a cost of up
to US$100m.
USAID estimated that up to four additional power stations needed to be
constructed in Iraq each year to 2020, but only one was currently planned in the South,
which would be funded by Japan. A new power plant would be a visible contribution
to the South and to Iraq, would boost long-term investment and would provide a more
reliable power supply to the oil sector, essential services and Iraqi citizens.
190. The MOD sent Gen Riley’s report to No.10 on 4 January.
 It was not included in
111
Mr Quarrey’s weekly round-up on Iraq for Mr Blair (which issued on 7 January), and the
Inquiry has seen no evidence that the report was passed to Mr Blair.
112
191. Gen Riley’s proposal was addressed in a DFID review of infrastructure
requirements in the South the following month.
Report Riley, 20 December 2004, ‘GOC MND(SE) – southern Iraq Update – 20 December 04’.
105
BBC News, 21 December 2004, Blair’s statement in Baghdad.
106
Telegram 494 Baghdad to FCO London, 21 December 2004, ‘Prime Minister’s Visit to Iraq,
107
21 December: Scenesetter’.
Report Riley, 3 January 2005, ‘GOC MND(SE) – southern Iraq Update – 3 January 2005’.
108
Letter Quarrey to Owen, 23 December 2004, ‘Prime Minister’s Visit to Iraq: Follow-up’.
109
Report Riley, 3 January 2005, ‘GOC MND(SE) – southern Iraq Update – 3 January 2005’.
110
Letter Naworynsky to Quarrey, 4 January 2005, ‘Iraq: Update’ attaching Report Riley, 3 January 2005,
111
‘GOC MND(SE) – southern Iraq Update – 3 January 2005’.
Minute Quarrey to Prime Minister, 7 January 2005, ‘Iraq: Weekly Round-up’.
112
227

---
Basra International Airport reopens to commercial traffic
UK forces continued to provide air traffic control and certain other services at Basra
International Airport (BIA) after the transition from the CPA to the IIG on 28 June 2004.
During the Occupation, the UK considered but rejected opening BIA to commercial flights,
due to the potential liability for the UK (see Section 10.1).
On 14 December, the UK and IIG signed a Memorandum of Understanding indemnifying
the UK Government and its agents against all claims arising from the provision of services
by UK personnel at BIA.
113
Following that agreement, BIA reopened to commercial traffic on 1 January 2005.
114
UK forces continued to provide support.
192. In a video conference with President Bush on 4 January, Mr Blair said that the US
and the UK should support Prime Minister Allawi’s new security plan (see Section 9.3).
115
A key issue would be funding. Reconstruction would not be a problem once the security
situation improved. Mr Blair asked if the US could, in the short term, redirect some US
reconstruction funding to security.
193. Sir Nigel Sheinwald sent Mr Stephen Hadley, US Deputy National Security
Advisor, a Note by Mr Blair on 10 January, and asked him to show it to President Bush
before their video conference the following day.
 Mr Blair’s Note covered “our most
116
pressing problems”.
194. On Iraq, he judged:
“All the problems go back to security. Without it the politics are difficult, the
reconstruction shackled and the faith of Iraqis in the future undermined.”
195. Mr Blair considered that four actions were necessary:
the Iraqiisation of security forces;
spending money more quickly on reconstruction, especially of essential services;
being “very tough indeed on the election”, including by ensuring it went ahead
on schedule and encouraging participation; and
signalling a timetable for the withdrawal of US and UK forces “when and only
when, we can point to real indigenous Iraqi strength”.
Telegram 474 Baghdad to FCO London, 15 December 2004, ‘Iraq: Basra Airport’.
113
Minute Allardice to DTI [junior official], 12 January 2005, ‘Ad Hoc Ministerial Group on Iraq
114
Reconstruction, 13 January 2005’ attaching Briefing, [undated], ‘Ad Hoc Ministerial Group on Iraq
Reconstruction’.
Letter Quarrey to Owen, 4 January 2005, ‘Prime Minister’s VTC with President Bush, 4 January 2005;
115
Iraq, Iran and MEPP’.
Letter Sheinwald to Hadley, 10 January 2005, [untitled], attaching Note Prime Minister to
116
President Bush, 10 January 2005, ‘Note’. Mr Hadley succeeded Dr Rice as US National Security Advisor
later that month.
228

---
10.2 | Reconstruction: July 2004 to July 2009
196. Mr Blair wrote: “If we had security, the blunt truth is Iraq wouldn’t need much help
for reconstruction.” However, in those parts of Iraq where security was reasonable,
reconstruction funds should be spent more quickly. This would have a powerful
demonstrative effect. Mr Blair suggested to President Bush that they should get a report
on the speed and priorities of the reconstruction programme.
197. The record of the video conference did not include any reference to
reconstruction.
117
DFID reduces its budget for Iraq for 2005/06
198. At the end of December, DFID’s Europe Middle East and Americas Division
(EMAD) submitted its Delivery Plan for 2005 to 2008 to the DFID Management Board,
for approval.
199. DFID provided the Inquiry with a version of the Delivery Plan marked “Draft”,
but informed the Inquiry that this version could be the one that was submitted to
Management Board.
118
200. In relation to Iraq, the draft Delivery Plan stated that DFID was seeking to “strike
a sensible balance between short-term fixes and longer-term development”.
 DFID
119
planned to scale down its assistance over the following three years, shifting from
“post-conflict reconstruction” towards targeted technical assistance.
201. Limiting EMAD expenditure on Middle Income Countries (MICs), including
Iraq, would be a “key factor” in ensuring that DFID met its target of spending at least
90 percent of country programme resources on Lower Income Countries (LICs) in each
year from 2005/06 to 2007/08. Attaining the target for 2005/06 would require some
£20m of in-year savings from MIC budgets.
202. The draft Delivery Plan stated that the current, agreed DFID budget for Iraq for
2005/06 was £86m (reducing to £45m and £30m in the subsequent financial years).
However:
“It has been agreed that £20m savings in MIC programmes should be found through
in-year and between-year management of spending. We expect the bulk of these
savings will be found from underspending on the Iraq budget; bringing the expected
spend on Iraq to closer to £66m than the full aid framework allocation of £86m …”
203. EMAD invited the Management Board to agree that those savings should be
retained within EMAD, and used for its non-MIC programmes.
Letter Quarrey to Owen, 11 January 2005, ‘Prime Minister’s VTC with President Bush, 11 January’.
117
Email DFID [junior official] to Iraq Inquiry [junior official], 20 January 2016, ‘DFID docs on reduction
118
in Iraq’s budget for 2005/06’.
Paper DFID, 22 December 2004, ‘Draft: Europe Middle East and Americas Division (EMAD): Director’s
119
Delivery Plan [draft] for 2005 – 2008’.
229

---
204. The 25 and 26 January 2005 meeting of DFID’s Management Board “noted that
the anticipated reduction (£20m) of programme spend in Iraq should enable … LIC
commitments to be met in 2005/06”.
120
205. A junior DFID official advised colleagues the following week that the Management
Board had imposed a “cap” on Iraq expenditure for 2005/06 of £65m.
She commented
121
that the decision was “largely to ensure that we do not undermine the agreed MIC/LIC
targets”.
206. The official also advised that DFID’s overall budget was “running very hot” and that
DFID’s Finance Department had “both eyes” on the £40m of Iraq’s 2004/05 budget that
had not yet been allocated.
207. The £65m budget for Iraq for 2005/06 was formally confirmed on 14 March.
122
208. DFID’s Iraq Directorate undertook internal exercises in February and March to
prioritise expenditure against the new, lower budget.
123
209. The March exercise estimated that “commitments and plans” for Iraq for 2005/06
totalled £123m (against the budget of £65m), of which:
£59m was “firm”;
£55m was high priority (including £40m for the planned Iraq Infrastructure
Services Programme);
£8.5m was medium priority; and
less than £1m was low priority.
124
DFID’s budget for and expenditure in 2005/06
Following the 25 and 26 January 2005 meeting of DFID’s Management Board, DFID
reduced its budget for Iraq for 2005/06 from £86m to £65m.
125
DFID expenditure in 2005/06 was £82m. That comprised:
£38m for “life support costs” (accommodation, security, medical services and other
services) provided by the FCO and charged to DFID (and other departments and
agencies) under a Service Level Agreement. Approximately half of that charge
related to services used in 2004/05 and half to services used in 2005/06;
£35m for infrastructure projects; and
£10m for governance projects.
126
Minutes, 25/26 January 2005, DFID Management Board meeting.
120
Email DFID [junior official] to DFID [junior official], 31 January 2005, ‘Iraq: FINSTATS 3’.
121
Minute Calvert to [DFID] Directors, 14 March 2005, ‘Resource Allocation Round: 2005-08’.
122
Email DFID [junior official] to DFID [junior official], 14 February 2005, ‘Iraq: Forecast 2005/06’;
123
Email DFID [junior official] to Anderson, 11 March 2005, ‘2005/06 Commitments’.
Email DFID [junior official] to Anderson, 11 March 2005, ‘2005/06 Commitments’.
124
Minute Calvert to [DFID] Directors, 14 March 2005, ‘Resource Allocation Round: 2005-08’.
125
Letter Cabinet Office [junior official] to Aldred, 1 July 2011, ‘Iraq Inquiry: request for further information
126
on funding’; Paper DFID, 21 December 2011, ‘A Note on DFID Iraq Programme Admin Spend for the
Iraq Inquiry’.
230

---
10.2 | Reconstruction: July 2004 to July 2009
The apparent overspend against DFID’s 2005/06 budget was caused by the FCO charge
for life support costs.
DFID’s expenditure on infrastructure projects peaked in 2005/06. Of the £45m spent on
non-life support costs in 2005/06, £35m – over 75 percent – was spent on infrastructure.
127
In comparison, DFID spent £15m on infrastructure in 2004/05 and £14m in 2006/07.
Priorities for 2005
210. In February, Ministers agreed UK priorities for 2005, including “reviewing
reconstruction to find ways to make a difference quickly”.
211. On 21 January, No.10 commissioned the Cabinet Office to produce a paper on
Iraqiisation, the UK’s military options and a game plan for engaging the US, to support
a discussion on UK strategy after the Iraqi elections.
128
212. The 28 January meeting of the Iraq Strategy Group (ISG) discussed a draft of that
paper.
 Sir Nigel Sheinwald said that Mr Blair would also want the paper to consider
129
“what could be done to achieve quick and labour-creating results on reconstruction
including outside MND(SE)”.
213. Sir Nigel asked that the paper also consider the involvement of the wider
international community in military, police and civil administrative capacity-building.
214. The elections to the Transitional National Assembly (TNA) and Provincial
Assemblies took place across Iraq on 30 January 2005. The TNA did not convene until
16 March, after which negotiations to form the Iraqi Transitional Government (ITG)
continued into late April (see Section 9.3).
215. On 1 February, Mr Blair suggested to President Bush that they should focus on
four areas in order to exploit post-election momentum:
Iraqiisation;
political outreach, including “whittling away at the opposition, so that the hard
core were left isolated”;
drawing in the international community; and
reconstruction, including areas in which there could be a quick impact
(eg power generation).
130
Letter Cabinet Office [junior official] to Aldred, 1 July 2011, ‘Iraq Inquiry: request for further information
127
on funding’.
Letter Phillipson to Baker, 21 January 2005, ‘Iraq: Future Strategy’.
128
Minute Ferguson to Sheinwald, 1 February 2005, ‘Iraq Strategy Meeting – 28 January 2005’.
129
Letter Quarrey to Owen, 1 February 2005, ‘Prime Minister’s VTC with President Bush, 1 February’.
130
231

---
216. Mr Blair proposed that these areas should be drawn into a plan by the ITG, which
the UK and US could then support.
217. On 3 February, just before the announcement of the election results, the Joint
Intelligence Committee (JIC) assessed the nature and strength of the insurgency.
131
Despite operational successes in Sunni areas:
“… the military campaign is not effectively containing the insurgency in Sunni areas.
Law and order, the pace of economic reconstruction, the availability of jobs and
general quality of life have not matched [Sunni] expectations. Most Sunnis perceive
themselves to be worse off economically, and in security terms than under Saddam.
Sunni ‘hearts and minds’ are being lost.”
218. The JIC assessed that the election results were likely to be less important in
determining Sunni support for the insurgency than the degree to which credible Sunnis
could be brought into the political process, “the speed at which reconstruction is taken
forward” and the duration of the coalition’s presence in Iraq.
219. A revised Cabinet Office strategy, drawing on the JIC assessment, was submitted
to the 9 February Ad Hoc Ministerial Group on Iraq, chaired by Mr Blair.
 The key
132
elements of the strategy for the coming year were:
building the capability of the ISF;
outreach by the ITG to bring in those currently supporting the insurgency;
drawing in the international community and giving it a new sense of purpose
(including getting the UN to do more on reconstruction); and
“reviewing reconstruction to find ways to make a difference quickly”.
220. The strategy identified key “governance and reconstruction” challenges in 2005,
including:
the weak capacity of Iraqi Government institutions to drive reconstruction;
sustained improvements in the availability of fuel and electricity needing difficult
reforms and a crackdown on corruption and sabotage;
the limited presence on the ground of international agencies and NGOs; and
ensuring all Iraq benefited (“the South is not a strategic priority for the US”).
221. The six “governance and reconstruction” actions for the UK before the ITG was
formed were:
preparing key messages to the new government on reconstruction priorities,
focusing on developing a stronger relationship between Baghdad and the
governorates;
working with the US to make its reconstruction effort more effective. The US
should focus on rapid job creation, and directly fund Iraqi ministries;
JIC Assessment, 3 February 2005, ‘Iraq: Insurgency and Counter-Insurgency’.
131
Paper Cabinet Office, 7 February 2005, ‘Iraq Strategy for 2005’.
132
232

---
10.2 | Reconstruction: July 2004 to July 2009
supporting the handover of power to the new government, through the
DFID-funded consultancy team;
133
pressing the UN, IMF and other donors to engage;
completing the design of DFID’s new £40m power and infrastructure programme
for the South; and
deciding on ways to expand visible job creation work in the South.
222. ITG ownership of governance and reconstruction would be crucial. The UK would
strengthen the ITG’s strategic communications capacity, to ensure that successes were
promulgated.
223. The strategy also identified a number of economic priorities:
ensuring the UK “plays its part” in achieving a “fair and sustainable” solution to
Iraq’s debt problems. Iraq would need to secure comparable debt relief from
non-Paris Club debtors;
encouraging Iraq to complete its IMF programme;
continuing to support economic reform;
promoting an “efficient, outward looking and transparent” oil and energy industry
and the transparent management of Iraq’s oil reserves; and
advising on an effective response to inflationary risks.
224. The strategy stated that the UK’s current posture in Iraq was costing around
£1bn a year, but did not comment on whether this amount was appropriate or sufficient.
225. In discussion, Ministers commented that it was essential that the security,
political and reconstruction tracks were synchronised if the UK was to achieve its
objectives in Iraq.
 If necessary, the UK should push ahead with plans for security and
134
reconstruction in MND(SE), in advance of developments in the rest of the country.
226. The Group approved the strategy and agreed that No.10 should pass an updated
version to the US, raising the issue of diversion of US funding for reconstruction projects
from the South to other parts of the country.
227. The Group also agreed that Mr Blair and Mr Benn should press Mr Annan and
Mr James Wolfensohn, President of the World Bank, to deploy staff to Basra.
228. Sir Nigel Sheinwald sent a revised version of the strategy to Mr Stephen Hadley,
US National Security Advisor, on 11 February.
135
A reference to DFID’s £4.2m Emergency Public Administration Programme, which was developed
133
to help establish the Prime Minister’s Office and the Cabinet and committee system.
Minutes, 9 February 2005, Ad Hoc Ministerial Group on Iraq meeting.
134
Letter Sheinwald to Hadley, 11 February 2005, ‘Iraq’ attaching Paper, ‘Iraq: Strategy for 2005’.
135
233

---
229. At the meeting of the ISG on the same day, Mr Martin Dinham, DFID Director
Europe, Middle East and Americas, set out what DFID would do “in response to
the renewed Ministerial mandate to press ahead with reconstruction, particularly in
MND(SE)”.
 The £40m Iraq Infrastructure Services Programme (IISP) would be
136
approved in the next few weeks. More money was available for job creation if required.
But it was also key to get other donors engaged. Mr Benn and DFID officials were
lobbying the UN, World Bank and IMF. Officials in Basra were conducting a review of
infrastructure requirements to identify gaps.
230. Mr Blair wrote to Mr Wolfensohn on 16 February, highlighting the slow pace of
delivery on Trust Fund projects and the value of having core World Bank staff (rather
than a contracted liaison officer) in Iraq, and offering to provide accommodation and
security for World Bank staff in Baghdad and Basra.
137
231. Mr Benn wrote to Mr Wolfensohn the following day:
“We need to seek innovative ways of managing the difficulties and risks associated
with working in present-day Iraq. The [World] Bank might need to reallocate funding
to new projects that can be delivered … One way to do this might be to channel
funding directly through provincial government systems to their priority projects.”
138
232. Mr Benn repeated Mr Blair’s offer to provide support for World Bank staff in Iraq,
and highlighted the need for a strong World Bank presence in the power sector.
233. Mr Dinham followed up those proposals in meetings with World Bank officials
during a visit to New York and Washington from 21 to 24 February.
139
234. During the meetings, World Bank officials argued that:
Bank officials could achieve a lot from the Bank’s office in Amman, Jordan;
there were presentational difficulties in being too closely associated with one
particular Member State; and
operating in Iraq was expensive and difficult.
235. Mr Dinham rejected those arguments, pointing out that the UN was now
establishing a presence in Iraq with two permanent development specialists and a large
number of staff supporting the election process.
236. Mr Dinham also pressed the Bank to accelerate disbursement from its Trust Fund.
The UN was now performing better than the Bank. Mr Dinham suggested that the Bank
Minute Cabinet Office [junior official] to Sheinwald, 11 February 2005, ‘Iraq: Strategy Group’.
136
Letter Blair to Wolfensohn, 16 February 2005, [untitled].
137
Letter Benn to Wolfensohn, 17 February 2005, ‘Iraq Reconstruction’.
138
Minute Dinham to Shafik, 28 February 2005, ‘Visit to Washington and New York, 21-24 February 2005:
139
Discussion of Iraq Issues’.
234

---
10.2 | Reconstruction: July 2004 to July 2009
might redirect some Trust Fund money into co-financing DFID’s IISP, or through the
provincial governments which DFID was supporting.
237. In a meeting with IMF officials, Mr Dinham offered DFID support to help establish
an IMF presence in Iraq. He reported that the IMF was “more responsive” to the offer
than the World Bank.
238. In Washington, US State Department officials briefed Mr Dinham on US plans
to re-programme some reconstruction funds to fund security in areas where no
reconstruction could take place, and to increase funding for projects that would have
more immediate impact on the ground. That meant cutting some larger infrastructure
projects, including in the South. The US objective was to encourage other donors, in
particular Japan, Arab states and possibly the European Commission (EC), to take on
longer-term infrastructure projects.
239. In meetings with UN officials, Mr Dinham welcomed progress in implementing UN
Trust Fund projects (although he felt that it could be faster) and the news that two UN
senior development officials were now permanently based in Baghdad.
240. The DFID review of infrastructure requirements in the South referred to by
Mr Dinham at the 11 February meeting of the ISG was submitted to the 24 February
meeting of the AHMGIR.
140
241. The paper stated that a DFID team had recently assessed how DFID could help
improve infrastructure in southern Iraq. As a result, Mr Benn had “approved work to bring
forward quickly” DFID’s £40m IISP.
242. The majority of IISP funds would be used to undertake repairs and improvements
to existing infrastructure. To ensure a visible impact on the ground, the programme
would fund larger projects (with a value of more than £500,000). Priority would be given
to projects which would have an impact within six to 12 months and generate significant
employment. 75 percent of the budget was earmarked for power, the rest to improve
water supplies and the fuel distribution network.
243. The paper stated that an “alternative approach” would be to invest available
resources in new power generation. That would take several years to come on line and
would be “a drop in the ocean” of Iraq’s power needs. Substantially greater and quicker
impact could be achieved by well-targeted repairs and rehabilitation, and building
Iraqi capacity.
244. The paper also stated that: “Taken with existing commitments, this new programme
[the IISP] means that there will be little scope for additional DFID initiatives in Iraq that
involve expenditure in 2005/06.”
Paper DFID, 21 February 2005, ‘Reconstruction – outcome of DFID mission on infrastructure in the
140
South; and involvement of other major players’.
235

---
245. The Inquiry concludes that the (brief) consideration of investment in new power
generation may have been prompted by Gen Riley’s 3 February proposal, in response
to Mr Blair’s request for advice on “big-ticket” items, that the UK should aim to build a
200MW gas turbine plant in the South at a cost of up to US$100m.
246. Mr Hoon wrote to Mr Benn on 25 February, highlighting the need to ensure that
the UK did all it could to alleviate power shortages in the South over the summer (before
projects under the IISP would begin to come on stream).
 Plans for a US$10m project
141
to provide point power generation throughout MND(SE), funded by CERPs, were well
advanced. Mr Benn’s offer to consider whether DFID could fund the project if CERPs
funding was not released was very welcome.
247. Mr Blair wrote a note to Mr Quarrey on 25 February instructing that Mr Straw be
“put in charge” of the Ad Hoc Ministerial Group on Iraq and asking him to report each
week with actions on “eg reconstruction in the South; Sunni outreach; progress on
security plan”.
142
248. Mr Benn discussed the World Bank’s engagement in Iraq with Mr Wolfensohn on
1 March in the margins of the Palestine Conference.
143
249. Following a meeting with Mr Benn on 8 March, Mr Michael Anderson, Head of
DFID’s Middle East and North Africa Department, advised officials in the UK Delegation
to the World Bank that Mr Benn had “very little patience” with the Bank:
“The SoS [Mr Benn] is very clear in his view that the slow disbursement by the Bank
under the IRFFI [Trust Fund] is unacceptable …
“… if the Bank is not able to show a significant increase in its engagement in Iraq by
the end of March, we will be writing to the Bank to seek refund of the funds to the
UK for disbursement through our bilateral programme …
“His commitment to this line is strong, and we will need to find a way to carry forward
his views despite the legal and reputational risks that may arise.”
144
Letter Hoon to Benn, 25 February 2005, ‘Iraq: Reconstruction Priorities in MND(SE)’.
141
Manuscript comment Blair on Minute Quarrey to Prime Minister, 25 February 2005, ‘Iraq Update’.
142
Letter Dinham to Tulu, 2 March 2005, ‘Iraq’.
143
Email Anderson to Scholar, 8 March 2005, ‘World Bank and Iraq’.
144
236

---
10.2 | Reconstruction: July 2004 to July 2009
Mr Benn’s evidence to the
International Development Committee, 10 March 2005
Mr Benn gave evidence to the International Development Committee (IDC) on
10 March 2005, as part of its inquiry into development assistance to Iraq.
 His hearing
145
followed a visit by three members of the IDC (Mr Quentin Davies, Mr Tony Colman and
Ms Ann Clwyd) to Iraq.
Mr Davies reported that he had been struck by the progress made in reconstruction and
building Iraqi capacity, and by the “very good” co-operation between DFID and the military
on the ground. He challenged Mr Benn on two issues. First, that the separate budgets
held by DFID and the MOD for reconstruction could lead to “some muddle”. Second, that
some of DFID’s work to build the capacity of the Iraqi Government was inconsistent with
the 2002 International Development Act.
Mr Benn welcomed the IDC’s observation that DFID and the MOD were working well
together on the ground. He commented:
“DFID has come into Iraq and done things that traditionally we would not do … Why?
Because that was what was required in the circumstances. We had to dust down
some skills and the Post-Conflict Reconstruction Unit [PCRU] is one of the lessons
from this …”
The PCRU and its role in Iraq is described in Section 10.3.
Mr Benn strongly rejected the charge that some of DFID’s work was inconsistent with
the 2002 International Development Act, arguing that capacity-building was crucial for
poverty reduction:
“… having states that work … governments that can do their job, is absolutely
fundamental to improving services and the lives of poor people.”
The imminent dissolution of Parliament brought the inquiry to a close. The IDC did not
publish a report, but did publish the evidence it had gathered as part of its inquiry.
The IDC did not undertake another inquiry into the UK’s reconstruction effort in Iraq.
250. Gen Riley reported on 16 March that he was “still worried” about providing
sufficient power across MND(SE) over the summer.
 Temperatures were already
146
creeping up, and he remembered the “near-disaster” in summer 2003 caused by the
failure of essential services.
147
Seventh Report from the International Development Committee, Session 2004-2005, Development
145
assistance in Iraq: Interim Report, HC244.
Report Riley, 16 March 2005, ‘GOC MND(SE) – southern Iraq Update – 16 March 2005’.
146
A reference to the riots in Basra on 10/11 August 2003, which the UK assessed were triggered by fuel
147
shortages and power blackouts.
237

---
251. While he waited for approval of the point power generation project, he had ordered
MND(SE) to search for additional sources of energy and funding. They had identified
131 generators across the region, of which only 22 were working. Most of the inoperable
generators had never been installed. MND(SE) had completed the installation of 32 of
those generators.
252. Mr Quarrey passed Gen Riley’s update to Mr Blair on 18 March, with the comment:
“The situation is bleak, with generation levels this summer unlikely on current
predictions to be significantly higher than last year – and almost certainly matched
by higher demand.”
148
253. Mr Quarrey advised that funding for the point power generation project (which
would become Operation AMPERE) had now been approved.
254. The funding was provided by DFID.
149
255. Mr Quarrey also advised that officials were working on a new strategy paper on
electricity, but it focused too much on the medium term and not enough on what the
UK could do to improve the situation over the summer. He recommended that the next
AHMGIR should focus on producing a short-term action plan.
256. Mr Blair indicated that he agreed with Mr Quarrey’s proposal, and that he would
raise the issue of power generation with President Bush.
150
257. A report on a visit to Iraq by senior DFID officials alerted other departments to
pressures on DFID’s budget.
258. Mr Dinham and Mr Anderson visited Iraq from 14 to 19 March.
151
259. Mr Dinham’s report to Dr Nemat Shafik, DFID Director General Programmes,
characterised the DFID programme as “a balance of capacity building and visible,
quick impact reconstruction activity, particularly in the South”. There was “accelerated
progress” on both capacity building and reconstruction, helped by “excellent
collaboration” with the FCO and MOD.
260. Mr Dinham warned that:
“One side effect of the good progress we are making … is that our Iraq budget
allocation for 2005/06 is under extreme pressure. If activities to which we are already
committed plus extensions of existing high priority capacity building programmes
proceed at the current pace, we will exceed our existing budget ceiling, without any
new proposals already in the pipeline being taken into account.”
Minute Quarrey to Prime Minister, 18 March 2005, ‘Iraq Update’ attaching Report Riley, 16 March 2005,
148
‘GOC MND(SE) – southern Iraq Update – 16 March 2005’.
Paper FCO/DFID, 22 March 2005, ‘Iraq: Electricity’.
149
Manuscript comment Blair on Minute Quarrey to Prime Minister, 18 March 2005, ‘Iraq Update’.
150
Minute Dinham to Shafik, 21 March 2005, ‘Visit to Iraq’.
151
238

---
10.2 | Reconstruction: July 2004 to July 2009
261. He continued:
“The need to cut back our budget [for Iraq] in 2004/05 to help meet internal DFID
financial pressures related to the estimating adjustment; plus the MIC ceiling
constraint in 2005/06; plus escalating cost relating to security … have all contributed
to the pressures.”
262. DFID would seek to deal with those pressures through “a variety of careful financial
management techniques” and an “active search for co-financing” with partners including
the World Bank and the EC. However:
“… the scope for new activity in 2005/06 is nil and we will have to delay until 2006/07
some of the proposals in the pipeline with which we hoped to proceed in 2005/06.”
263. Mr Dinham also reported that Iraqi governorates did not yet have the capacity to
receive supplementary funding from sources such as the World Bank and the US, as
DFID had hoped.
264. Copies of Mr Dinham’s report were sent to Mr Benn’s Private Secretary,
Mr Chakrabarti’s Private Secretary, other DFID officials, and officials in No.10, the
Cabinet Office, the FCO, and the MOD.
265. Mr Quarrey marked Mr Dinham’s report to Sir Nigel Sheinwald with the comment:
“This is worrying – we need to have some flexibility in 05/06, including to support
ITG ideas/priorities.”
152
266. Mr Straw made his first report to Mr Blair on the work of the Ad Hoc Ministerial
Group on Iraq on 24 March.
 He attached a number of reports, included a joint
153
FCO/DFID paper describing the state of the electricity sector, which he described as
a focus for the Group’s work.
267. The FCO/DFID paper stated that the Iraqi Government was struggling to sustain
production at more than 4,000MW per day and was unlikely to meet its target of
producing 6,000MW per day by the summer. Demand had soared as the economy had
grown, and was now estimated to be 8,000MW per day (that figure would increase over
the summer). Power cuts would continue.
268. The paper identified four factors behind the failure to increase power production
above May 2003 levels:
continued sabotage;
the unreliability and inefficiency of existing power infrastructure;
Manuscript comment Quarrey on Minute Dinham to Shafik, 21 March 2005, ‘Visit to Iraq’.
152
Letter Straw to Blair, 24 March 2005, ‘Iraq: Ad Hoc Ministerial Meetings’ attaching Paper FCO/DFID,
153
22 March 2005, ‘Iraq: Electricity’.
239

---
poor management by the Iraqi Government; and
a lack of “strategic focus” by the CPA in the immediate post-conflict period.
269. The paper advised that the Iraqi Government needed to develop a long-term
energy strategy which addressed subsidy and charging issues (power was free). The
World Bank had agreed to advise on strategy and co-ordination “with DFID facilitating”.
270. Given limited UK funds, the UK was focusing on:
meeting key short-term needs. The US$10m provided to Gen Riley should
produce 25MW and £10m provided under the SIESP a further 50MW. In the
longer-term, the IISP should produce 160MW by April 2006;
leveraging engagement from others, and;
providing strategic advice to the Iraqi Government.
271. The FCO/IPU concluded that planned work was unlikely to solve Iraq’s power
generation problem in time for the summer. The UK should encourage the Iraqi
Government to plan now for next summer and the longer term, through the development
of a coherent strategy for the energy sector.
272. In his covering letter to Mr Blair, Mr Straw stated that 55 percent of DFID’s budget
for Iraq for 2005/06 would be spent in the power sector.
154
273. Mr Blair indicated that he had seen the letter, but did not comment on it.
155
274. MND(SE) and the DFID Basra Office reported on 30 March that they had reached
agreement on how to use the US$10m provided by DFID for power generation in the
South.
 MND(SE) had initially favoured diesel generators, DFID gas turbines. A “hybrid
156
proposal” had emerged, involving the purchase of diesel generators for fewer sites than
originally proposed and the refurbishment of existing gas turbines. MND(SE) estimated
that the project – Operation AMPERE – would produce an additional 16.5MW by 1 July.
It would only be a temporary solution. DFID’s IISP would help to maintain existing
capacity, but substantive improvement would only come through long-term restructuring,
institutional reform and major capital investment. That agenda would be pursued with
the ITG.
275. The effect of Op AMPERE is considered later in this Section.
Letter Straw to Blair, 24 March 2005, ‘Iraq: Ad Hoc Ministerial Meetings’.
154
Manuscript comment Blair on Note Quarrey to Prime Minister, 30 March 2005, ‘Iraq’.
155
Telegram 47 Basra to FCO London, 30 March 2005, ‘Iraq: Meeting Peak Power Demands in the South
156
this Summer’.
240

---
10.2 | Reconstruction: July 2004 to July 2009
276. Gen Riley reported on 5 April that a fire had completely shut down the main power
station in Nasiriyah, which supplied 50 percent of the electricity to the MND(SE) area.
157
He commented:
“This simply serves to point up the fragility of the national supply and to illustrate
that DFID and MND(SE) alone are never going to solve the electricity problem
in southern Iraq. While I still believe that DFID’s US$10m will make a small
difference this summer the symbolic nature of the money is as important as the
power it will produce.”
277. Gen Riley concluded that “more drastic action” was needed to prevent an even
bigger problem in summer 2006.
DFID reviews its Interim Country Assistance Plan
278. DFID had published its Interim Country Assistance Plan for Iraq (I-CAP) in
February 2004, at a time when the UK was a joint Occupying Power in Iraq and security
was improving.
158
279. The I-CAP re-stated DFID guidance that progress against a CAP should be
assessed annually, and that a CAP should be subject to a “major review” every three or
four years. The I-CAP stated that, given the rapidly changing situation in Iraq, it would
need a “substantial” review after one year.
280. Mr Anderson circulated a note on the programme management issues identified
during his 14 to 19 March visit to Iraq to DFID colleagues only on 4 April 2005.
159
281. Mr Anderson highlighted the next 12 months as a critical period for DFID’s Iraq
programme and a “key window for donor impact”. US and UK development spending
was set to reduce after 2006 and the UK military presence, upon which donor activities
in the South relied, might draw down.
282. Mr Anderson also highlighted two DFID policy papers with implications for DFID’s
programme in Iraq. The first, on fragile states, emphasised the importance of realistic
expectations of host government capacity and of prioritising and sequencing activities
to avoid overwhelming it. The second, on security and development, highlighted the
importance of personal safety and security for the poor, and emphasised that activities
to promote effective security systems were integral to development work. The DFID Iraq
team would meet to consider the implications of the papers in the next few months.
283. Mr Anderson detailed the work required to bring DFID’s programme for 2005/06
within the new budget. Current commitments exceeded the new budget “by several tens
of millions of pounds”.
Report Riley, 5 April 2005, ‘GOC MND(SE) southern Iraq Update – 5 April 2005’.
157
Department for International Development, Iraq: Interim Country Assistance Plan, February 2004.
158
Minute Anderson to DFID [junior official], 4 April 2005, ‘Iraq Programme Management Issues’.
159
241

---
284. A review of DFID’s I-CAP was under way. It was unlikely to result in major changes,
but existing activities would need to be “more focused” on the four UK objectives set out
in the UK paper ‘Iraq: Strategy for 2005’, which had been agreed on 9 February.
285. On 6 April, the JIC assessed the state of the insurgency in Iraq following the
January election.
 It judged that a significant Sunni insurgency would continue through
160
2005, but that there now appeared to be greater opportunities for reducing it. The ITG’s
early actions would be critical in changing Sunni perceptions and eroding support for
the insurgency. Sunni expectations included the direction of reconstruction money
to Sunni areas.
286. Mr Blair met President Bush on 8 April. Mr Blair’s briefing for the meeting
suggested that he might raise four operational points with President Bush, including
power supply.
 It would be very damaging for the ITG if there was no improvement in
161
electricity supply that summer. The UK was looking to boost supply in the short term in
the South through a DFID/MOD programme; the US needed to do more quick-impact
work across Iraq.
287. The record of the meeting did not include any reference to a discussion on
improving power supply, or reconstruction more broadly.
162
288. Lt Gen Kiszely completed his tour as the Senior British Military Representative,
Iraq and sent his “hauldown” report to Gen Walker on 16 April.
 Lt Gen Kiszely
163
assessed that progress in MND(SE) had been good, with all four provinces likely to
be under Provincial Iraqi Security Control by March 2006, offering “the potential for
considerable reductions in UK force levels”.
289. The I-CAP review process was discussed in a meeting of DFID officials chaired by
Mr Anderson on 21 April 2005.
 The meeting concluded that:
164
“The starting point is that the I-CAP remains valid, but priorities within that
have moved on in the light of the substantially changed situation in Iraq since
last February [when the I-CAP was agreed], the 2005 Strategy and our budget
constraints.”
JIC Assessment, 6 April 2005, ‘Iraq: the State of the Insurgency’.
160
Minute Phillipson to Prime Minister, 7 April 2005, ‘Bilateral with President Bush: 0800-0845, 8 April’.
161
Letter Sheinwald to Adams, 8 April 2005, ‘Prime Minister’s Meeting with President Bush, Rome, 8 April’.
162
Minute Kiszely to CDS, 16 April 2005, ‘SBMR-I’s Hauldown Report’.
163
Minute DFID [junior official] to Anderson, 22 April 2005, ‘Iraq: ICAP Review and 2005/06 Programming’.
164
242

---
10.2 | Reconstruction: July 2004 to July 2009
The Iraqi Transitional Government
The Iraqi Transitional Government (ITG), led by Prime Minister Dr Ibrahim al-Ja’afari,
formally took power in early May.
 The ITG was mandated to govern Iraq until a
165
government could be elected according to a new constitution in December 2005.
In his account of the Occupation of Iraq and the transition to democracy, Dr Ali A Allawi,
ITG Minister of Finance and former IIG Minister of Defence, described Iraqi people’s
expectations of the ITG:
“The public expected that the Transitional Government would immediately start to
remedy the services and security situations, and the message [delivered by Prime
Minister al-Ja’afari in the National Assembly] was that conditions would rapidly
improve. A realistic and cold-blooded assessment … would have led to a different
conclusion, one that might have been difficult for politicians to admit to, but which
was nevertheless necessary to make if the expectations of the public were not to be
raised too high.”
166
Dr Allawi wrote that problems with the power supply added to the feeling of “a country
under siege”.
 Those problems “could not have possibly been resolved in the time-frame
167
of the Transitional Government” and the fact that the entire sector did not collapse “was
actually a sign of success”.
290. DFID officials in London, Baghdad and Basra held a video conference on 17 May
to discuss the I-CAP review.
 The presentation made to the video conference by a
168
DFID official set out a number of “conclusions”:
A “de-facto” review had already been completed, in the form of the exchange
between Mr Blair and Mr Benn in October 2004, Mr Chakrabarti’s visit to Iraq in
December 2004, the 2005 UK Strategy, the “smaller than expected” budget for
Iraq, and increased life support costs.
The process could have been much better. There should be a better process for
next year’s review.
291. The official subsequently reported to Mr Anderson that the video conference had
agreed that the I-CAP review had “essentially been completed”. Work was now in hand
to produce a text for publication, after agreement by Mr Benn. The process had been
driven by events and had not been ideal. The official set out in detail the better review
process that should be undertaken the following year.
292. Mr Blair and President Bush spoke by video conference on 19 May. Mr Blair’s brief
for the conversation advised that the electricity situation in Iraq was “parlous” (six hours
Daily Telegraph, 3 May 2005, Iraq’s new government sworn in.
165
Allawi AA. The Occupation of Iraq: winning the war, losing the peace. Yale University Press, 2007.
166
Allawi AA. The Occupation of Iraq: winning the war, losing the peace. Yale University Press, 2007.
167
Minute DFID [junior official] to Anderson, 19 May 2005, ‘ICAP Review’
168
243

---
a day or less). It would be very damaging for the ITG if electricity supply that summer
was worse than the last.
169
293. The record of the video conference did not include any reference to a discussion
on improving power supply, or reconstruction more broadly.
170
294. Mr Blair spoke to Prime Minister Ja’afari for the first time on 26 May and said that
“we stood ready to help in any way we could”, in particular on developing the ISF.
171
295. The newly formed Sub-Committee of the Ministerial Committee on Defence and
Overseas Policy on Iraq (DOP (I)) met for the first time on 26 May, chaired by Mr Blair.
172
Mr Benn attended the meeting.
296. Mr Benn’s briefing for the meeting advised that, following his decision in December
2004 on priorities for 2005, DFID’s programme was now “substantially re-orientated
towards bilateral infrastructure support in the South”.
173
297. It also advised that in response to a larger-than-expected charge from the FCO for
life support costs and a “smaller-than-expected” budget allocation for Iraq for 2005/06:
“… we have trimmed back some work, notably consultancy, and are planning
25 percent slippage on the £40m infrastructure work [DFID’s Iraq Infrastructure
Services Programme – IISP]. We are also seeking co-financing, with US$20m
agreed in principle with the World Bank …”
298. Even after that trimming, planned expenditure for 2005/06 exceeded the budget;
DFID would need to monitor spending very closely. It was, however, reasonable to
“over-programme” given the (unspecified) “uncertainties” and the potential military
drawdown in the second half of 2005/06, which might significantly affect what DFID
could do in the South.
299. The Inquiry has seen no indications that other departments were informed of or
consulted on the decision to slip expenditure on the IISP.
300. Mr Blair’s briefing for the meeting, which was produced by the Cabinet Office,
recommended that he focus on three issues:
combating the insurgency;
improving the effectiveness of international assistance; and
getting media messages right, both within and outside Iraq.
174
Minute Phillipson to Prime Minister, 19 May 2005, ‘VTC with President Bush, 1220 19 May’.
169
Letter Quarrey to Siddiq, 19 May 2005, ‘Prime Minister’s Video-Conference with Bush, 19 May’.
170
Letter Quarrey to Siddiq, 26 May 2005, ‘Prime Minister’s Conversation with Ja’afari’.
171
Minutes, 26 May 2005, DOP(I) meeting.
172
Minute DFID [junior official] to Private Secretary [DFID], 24 May 2005, ‘Iraq Update, 25 May’ attaching
173
Briefing MENAD, 24 May 2005, ‘Iraq Update 25 May Background Note’.
Briefing Cabinet Office, 25 May 2005, ‘Chairman’s Brief (DOP(I))’.
174
244

---
10.2 | Reconstruction: July 2004 to July 2009
301. On the second point, the Cabinet Office briefing advised that:
the pace of reconstruction was still too slow and therefore the “political dividend”
was small;
power supply was “parlous”; and
UK funding for 2005/06 was almost all committed, requiring “tough Ministerial
decisions” after further work by officials.
302. The Annotated Agenda for the meeting invited Ministers to consider:
What impact was US and international funding for reconstruction having on the
ground? Disbursement lagged behind stated international commitments. The
US was focusing on short-term impact. The UN was re-establishing a presence
in Iraq and was starting to “take on the role we would expect of them”. Donor
efforts had lacked focus; better donor co-ordination behind an Iraqi figure was
one of the planned outcomes of the Brussels International Conference in June.
What more the UK could do, to further improve UN, World Bank and
international bilateral reconstruction efforts?
What “concrete outputs” did the UK want from the Brussels International
Conference and the next donor meeting in Amman in July?
Was the funding available for reconstruction across Government adequate?
Was the UK investing at a level that supported its objective of creating stability
such that there could be troop withdrawals?
Was the UK delivering a short-term return which would boost the political
process?
What more the UK could do, to improve power supply over the summer and
boost investment in infrastructure?
Was the UK offering the necessary support to the ITG’s media effort?
175
303. On funding, the Annotated Agenda stated that DFID’s allocation for Iraq was
£65m for 2005/06, but that it had already “programmed” £84.3m (£63m of which would
be spent in southern Iraq). The tri-departmental Global Conflict Prevention Pool (see
Section 12.1) was expected to allocate £25m for Iraq in 2005/06, of which £22m had
already been programmed. The MOD would be bidding to the Treasury for additional
funding for QIPs, having spent £27m on QIPs since 2003. The MOD’s budget for military
activity in Iraq in 2005/06 was £927m.
304. In discussion, Ministers commented that the power situation was serious and
would get worse over the summer, but the UK was “doing what it could”.
176
Annotated Agenda, 26 May 2005, DOP(I) meeting.
175
Minutes, 26 May 2005, DOP(I) meeting.
176
245

---
305. Summarising the outcome of the discussion, Mr Blair asked for more advice on
several issues, including a “short strategy” from DFID on engaging key donors.
306. DFID sent its donor engagement strategy to the Cabinet Office on 3 June.
 The
177
DFID strategy advised that a significant portion of the US$32bn pledged at the Madrid
Conference in October 2003 remained unspent. Some donors had spread their money
over several years, some had offered soft loans that could only be activated after an
agreement on debt relief, some had been waiting for an elected Iraqi Government, and
many had experienced difficulties in implementing reconstruction projects in Iraq. One
or two donors were “simply back-sliding”. The paper identified 16 countries that the UK
should lobby to secure outstanding pledges.
307. DFID advised that the US was committed to disbursing its funds as quickly as
possible. The UK had limited influence over US policy and did not question its “current
thrust”, but should seek to:
join up US and UK work in southern Iraq;
encourage the US to participate in donor co-ordination processes in Baghdad;
and
work with the US to encourage other donors and the multilateral agencies to
contribute more effectively.
308. The UK was lobbying Japan to allocate the bulk of its soft loans (up to US$3.5bn)
to the power sector and exploring with Australia, Denmark and Canada the possibility of
co-funding DFID projects in southern Iraq.
309. France and Germany remained the “two missing donors”, although France had
taken a constructive approach on donor co-ordination and the Brussels International
Conference, and Germany was contributing to police training outside Iraq.
310. Implementation of reconstruction projects by UN agencies had improved and the
UN was playing a valuable role supporting Iraqi-led donor co-ordination. DFID continued
to press for further improvements to UN Trust Fund operations.
311. DFID also continued to press:
the World Bank urgently to establish a presence on the ground in Iraq, and to
find ways of implementing its projects; and
the EC to open a permanent office in Baghdad. The EC was already making
use of UK life support
 and security facilities for its increasingly frequent visits
178
to Iraq.
Email DFID [junior official] to DFID [junior official], 3 June 2005, ‘Iraq donor coordination paper’
177
attaching Paper DFID, 2 June 2005, ‘Iraq Reconstruction: Engaging USA and Other Key Donors’.
Life support includes accommodation, medical services, catering, laundry and cleaning.
178
246

---
10.2 | Reconstruction: July 2004 to July 2009
312. Mr Quarrey commented to Mr Blair: “… this is OK on what we want the US to do
with others, but DFID seem to have given up on influencing how the US spends its own
money – still by far the most important funding source”.
179
313. Mr Blair saw Mr Quarrey’s note, but did not respond.
180
314. On 7 June, Mr Blair and President Bush held talks on a range of foreign policy
issues in the White House.
 In their discussion on Iraq, Mr Blair judged that:
181
“Ultimately, without an improvement in security, little progress could be made.”
315. Sir Nigel Sheinwald and Sir David Manning met Dr Rice and Mr Hadley on the
same day.
 Sir Nigel and Mr Hadley agreed that:
182
“ … there was scope for a major US/EU/UN initiative on developing the ability of the
international community to build capacity (governance, judiciary etc) in failing states
and post-conflict situations. This was the lesson of the Balkans and Iraq, and we still
did not have the means to deal with this. Some sort of international co-ordination
was necessary.”
316. Mr Straw visited Iraq on 9 June with the EU Troika – Mr Jean Asselborn
(Presidency), Mr Javier Solana (EU Common Foreign and Security Policy High
Representative) and Ms Benita Ferrero Waldner (EU External Affairs Commissioner).
The British Embassy Baghdad reported that the Troika had brought three main
messages:
support for the political process, and the need for inclusion;
the importance of the Brussels International Conference, as an opportunity for
Iraq to engage with the EU and wider donor community; and
a shift in Europe. Europe had been divided over the war but was now united
in its desire to help the Iraqi people.
183
317. The Embassy reported that, under pressure from Mr Straw, Mr Waldner had told
the Iraqi Government and the media that the Commission would open an office in Iraq
“in months rather than weeks”.
Minute Quarrey to Prime Minister, 3 June 2005, ‘Iraq Update’.
179
Manuscript comment Blair on Minute Quarrey to Prime Minister, 3 June 2005, ‘Iraq Update’.
180
Letter Phillipson to Adams, 7 June 2005, ‘Prime Minister’s Talks with President Bush, 7 June’.
181
Letter Sheinwald to Adams, 7 June 2005, ‘Dinner with US Secretary of State and National Security
182
Adviser: 7 June’.
eGram 65/2005 Baghdad to FCO London, 10 June 2005, ‘Visit of the Foreign Secretary and the EU
183
Troika, 9 June 2005’.
247

---
Fraud in the Southern Iraq Employment
and Services Programme
DFID’s Southern Iraq Employment and Services Programme (SIESP) was approved
in July 2004, providing £10m for infrastructure services and £6m for employment
generation.
 £0.5m was allocated for programme administration.
184
In May 2005, the DFID Office in Basra closed the employment generation component
of the SIESP after an assessment identified “worrying issues”. The Office asked DFID’s
Internal Audit Department (IAD) to visit Basra to review the SIESP and identify lessons, in
particular for the implementation of DFID’s Iraq Infrastructure Services Programme (IISP).
The IAD identified several flaws in the design of the component. It concluded that:
A “key driver” of the SIESP had been “political (and consequent senior
management) pressure in Whitehall and beyond to achieve visible results …
In retrospect, these pressures appear unreasonable but at the time were generally
irresistible.” Warnings against proceeding with a programme of “such high
fiduciary risk and intangible benefit” had not been heeded.
There had been limited advisory input from DFID headquarters.
The initial decision to work through the newly formed (and unelected) Iraqi
Provincial Councils (PCs) had been a misjudgement. They had limited capacity
and there was evidence of widespread corruption in their operation.
A later decision to work through local NGOs had not improved performance. Many
NGOs had been set up solely to secure funding from donors. They had limited
capacity, lacked local knowledge, and had proved to be “largely unreliable
and/or corrupt”.
The lack of physical monitoring had undermined implementation. The security
situation meant that there was little chance of DFID staff visiting projects funded
under the SIESP. In Maysan, where the security situation was particularly difficult,
the UK military had managed the employment generation component of the
SIESP directly (bypassing the PC). The military had undertaken some monitoring
as part of routine patrolling, but that had not been “adequate”. The IAD concluded
that the inability to monitor progress indicated that Iraq “was not ready for this type
of development intervention”.
Weaknesses in the DFID Office in Basra had contributed to the problems within
the SIESP. The Office had been set up “hastily under pressure from UK and
locally to show a DFID presence”. It had proved very difficult to recruit staff for
Iraq, leading to the appointment of staff with “little or no experience in managing
programmes or staff”.
The DFID Office in Basra had established “good controls” over SIESP finances.
The Office’s decision to close the employment generation component immediately
after its initial assessment had saved £3m (the amount remaining in the
employment generation budget).
Report DFID Internal Audit Department, 11 August 2005, ‘Visit Report: Basra, Iraq 26
 – 31
 July 2005’.
184
th
st
248

---
10.2 | Reconstruction: July 2004 to July 2009
Of the £3m that had been spent, the IAD estimated that over £2m had been
spent in a way “that did not meet [the SIESP’s] objectives”. The lack of physical
monitoring made it difficult to be more precise.
The IAD assessed that the incident had soured the relationship between DFID and the
PCs and adversely affected DFID’s reputation and credibility with Iraqi interlocutors, the
UK military, other donors and “bona fide NGOs”.
The IAD report detailed a number of lessons for the IISP.
In May 2006, DFID conducted an internal review in order to determine the extent of the
loss from the SIESP employment component.
The review concluded that:
185
£254,105 had been spent on projects where there was clear evidence of full or
partial misuse of money, based on monitoring by DFID staff.
£296,187 had been spent on projects where there was “no clear evidence
of either good use or misuse of money (because there was no monitoring
information on file) but where anecdotal evidence from interviews suggested that
some percentage of the projects were not successfully completed”.
£1,021,223 had been spent on projects which DFID was “reasonably confident”
had been successfully completed, based on information on file (in the form of
photographs or visit reports) or anecdotal evidence.
The review stated that even those projects where there was evidence of misuse had
“added economic value to Iraq, though less than was originally intended”.
The review set out the methodology it had used to categorise projects, including that in the
absence of information to the contrary, the existence of monitoring information on a project
was taken as evidence that the project had been successfully completed:
“For the remaining project … we have no monitoring reports in the file. However, there
is a CD [compact disc] in the file which shows a street with sewage and garbage,
and provides a commentary (in Arabic) which explains what work needs to be done.
Because we have no other information, and no reason to believe that funds were not
used according to the purposes intended, we assume that this project was successful.”
Dr Nemat Shafik, DFID Permanent Secretary from March 2008, told the Inquiry how DFID
had reacted to the fraud within the SIESP:
“We have a zero tolerance policy on corruption and we act on it immediately. The
then Provincial Council was very unhappy with us as a result … But on that, we don’t
compromise.
“That [the SIESP] is … the only case that we are aware of, where we had a
significant fraud, which, given the scale of the funds that we were disbursing, and
given the context, is, I think, a pretty good track record.
“In the case of the Iraq portfolio … we actually had a higher level of scrutiny than our
normal portfolio because of the risks involved. So we would get monthly reporting on
risks, security risk, staff risk, risks to our money …”
186
Minute Hendrie to Dinham, 19 May 2006, ‘SIESP Employment Generation Project’.
185
Public hearing, 13 January 2010, pages 54-55.
186
249

---
318. A draft Cabinet Office paper entitled ‘Funding for Iraq 2005/06’ was circulated with
the record of the 3 June meeting of the ISG.
 The draft paper stated that:
187
“The UK now has a realistic prospect of reducing troop numbers over the next
nine months – and should benefit from a reduction in costs in Iraq as a result.
Both to ensure Iraqi capacity and consent during this process, and to meet Iraq’s
development needs, reconstruction on the ground needs to continue … However,
[the UK’s] resources for Iraq are already overstretched. Ministers will therefore need
either to agree a strict prioritisation of assistance, or consider whether additional
funds should be made available.”
319. The Cabinet Office draft paper set out the funding currently available for Iraq
for 2005/06:
DFID had £65m available and had commitments of £86.6m.
The GCPP had £23.3m available (an accurate figure for commitments was not
yet available).
The MOD forecast “military operational” costs of £927m (a figure for QIPs was
not yet available).
320. An Annex to the draft paper advised that DFID would need to manage its
programme very carefully in order to come within the £65m budget. Some (unspecified)
spending could be delayed, and DFID was urgently seeking co-financing for projects
from other donors, including the World Bank. An improvement in the security situation
would help: £28m of the £86.6m was expected to be spent on security and life support.
321. Of the £86.6m committed to existing high-priority activities:
£63.8m (74 percent ) was committed to projects in southern Iraq.
£14.6m (17 percent) was committed to projects supporting central Government.
£7.2m (8 percent) was committed to projects supporting political participation
(“elections, media, support to civil society groups”).
£1m was committed to multilateral organisations.
322. Ms Aldred told the 10 June meeting of the Iraq Senior Officials Group (ISOG) that
Ministers needed to consider funding for Iraq “in the round”, and alongside funding for
Afghanistan.
 A Treasury official agreed, and said that any submission to Ministers on
188
funding needed to make the link between activity and the UK’s objectives.
323. The ISOG agreed that officials would finalise the draft paper “to coincide with” the
14 July meeting of DOP.
Minute Cabinet Office [junior official] to Sheinwald, 7 June 2005, ‘Iraq: Strategy Group’ attaching draft
187
Paper, [undated], ‘Funding for Iraq 2005/06’.
Letter Cabinet Office [junior official] to Asquith, 13 June 2005, ‘Iraq: Senior Officials’.
188
250

---
10.2 | Reconstruction: July 2004 to July 2009
324. A DFID official briefed the ISOG on the impact of the US reconstruction effort.
He advised that “the US was well aware of its failings … and there was little we could
tell them that they didn’t already realise and were actively trying to change”. The most
significant impact DFID could have on the US was by working jointly with them in
the South.
325. The Cabinet Office paper on funding for Iraq was finalised for the 21 July meeting
of DOP, chaired by Mr Blair, which considered whether or not the UK Provincial
Reconstruction Team (PRT) in Afghanistan should move from the north to Helmand
and what, if any, additional force package should be deployed to support it (see
Section 9.4).
189
326. The Cabinet Office paper, which was presented as an appendix to the main MOD
paper, set out the estimates of financial pressures associated with the Iraq campaign for
2005/06, 2006/07 and 2007/08.
327. On 17 June, a junior DFID official invited Mr Benn to endorse the “annual review”
of DFID’s Interim Country Assistance Plan (I-CAP).
190
328. In his covering minute, the official advised that the I-CAP (which had been
published in February 2004) had been expected to remain in place for two years, and
contained a commitment to undertake a “substantial review” after one year.
329. However, events had “pre-empted a pro-active review”. Those events were:
the exchange between Mr Blair and Mr Benn in October 2004 on the need to
accelerate the pace of reconstruction and increase the impact of DFID’s bilateral
programme in the short term;
Mr Chakrabarti’s and Mr Drummond’s visit to Iraq in December 2004 to review
DFID programmes and assess priorities for 2005;
Mr Benn’s agreement in December 2004 to priorities for 2005;
the agreement in February 2005 of the 2005 UK Iraq Strategy. That Strategy
included “most of the items that we suggested”, and was in line with priorities
agreed by Mr Benn; and
subsequently, “unexpected and significant funding constraints” arising from a
smaller than expected budget for 2005/06 and an increase in life support costs
levelled by the FCO.
Paper MOD Officials, 19 July 2005, ‘Afghanistan: Resources and Strategic Planning’.
189
Minute DFID [junior official] to Private Secretary [DFID], 17 June 2005, ‘Iraq: Interim Country
190
Assistance Plan: Annual Review’ attaching Paper DFID, [undated], ‘DFID: Iraq Country Assistance
Plan Review 2004/5’.
251

---
330. The official also advised that:
“A major constraint to DFID’s programme, not highlighted in the I-CAP review, is the
limited capacity of Iraqi institutions to drive forward reform and reconstruction. This is
exacerbated by the short political horizons inherent in the Transitional Administrative
Law (TAL), which militate against far-reaching reform. Corruption is also becoming
increasingly apparent and might become the main constraint on reconstruction and
development if security were to improve significantly.”
331. The I-CAP review comprised short reports on:
political and economic progress in Iraq;
progress on reconstruction. Deteriorating security – identified as a key risk in the
I-CAP – was a major constraint. Projected costs of UK staff working in Iraq for
2005/06 were more than £500,000 per person-year;
the activities of other donors;
key challenges for reconstruction in 2005/06. Those included the limited
life-span of the IIG and the ITG, which affected their ability to implement major
reforms; and
examples of the impact of DFID projects in 2004/05.
332. The I-CAP review stated that:
“DFID’s work programme has evolved to take account of the difficult security
situation and the absence of some traditional donors. The objectives and approach
set out in our I-CAP remained valid.”
333. DFID would:
continue to promote broader and more effective international support;
continue and deepen work at the national level to build Iraqi capacity and
encourage greater Iraqi leadership of reconstruction; and
“expand and accelerate” DFID’s programme in the South, where high levels
of poverty persisted.
334. There are no indications that other government departments or international
partners contributed to the production of the I-CAP review.
335. The I-CAP review submitted to Mr Benn was not the “substantial review” promised
in the I-CAP. In particular, it did not:
provide a comprehensive assessment of the political, economic and social
context in Iraq, reflecting the major changes since the I-CAP had been
produced, including the existence of a sovereign Iraqi Government (with its own
priorities and constraints) and the profound impacts of growing insecurity;
252

---
10.2 | Reconstruction: July 2004 to July 2009
consider the lessons that DFID had identified since the I-CAP was produced,
and how it would respond to them;
consider how the reconstruction effort could and should contribute to broader
UK objectives; and
consider whether the level of resources available to achieve DFID’s objectives
in Iraq was right, and whether DFID was working in the most effective way.
336. In the absence of that analysis, the I-CAP review could not (and did not) test the
position that DFID had reached.
337. Mr Anderson visited Iraq from 13 to 18 June.
191
338. In his report to Mr Dinham, copies of which were sent to officials in DFID, the
FCO and the MOD, Mr Anderson identified a number of “strategic issues”, including
the expected decline in the amount of aid going to Iraq. US funding would decline from
US$18.4bn over two years (the current IRFF2 package) to around US$1bn in 2006/07.
Japanese grants were “now exhausted” and DFID’s programme would decline in
2006/07. There might be “modest increases” in UN and World Bank programmes but
“even in the most optimistic scenario, there will be a dramatic decline in aid levels due
to the changing US position”.
339. That rapid decline raised three strategic issues:
What impact would declining aid have on security?
Was this the right time for donors to be reducing aid? Research showed that
aid during or immediately following conflict tended to be wasted. It was most
effective between four and seven years after a conflict.
Was DFID right to treat Iraq as a MIC? The planned decline in DFID’s
programme was based on the “premise” that Iraq had adequate resources to
fund its own development. But did that hold true when security was poor and
oil revenues difficult to obtain?
340. DFID has not been able to provide the Inquiry with any response from Mr Dinham,
or any record of a discussion of aid volumes.
192
341. Dr John Reid, the Defence Secretary, circulated a paper on the options for future
UK force posture in Iraq to DOP(I) on 16 June (see Section 9.4).
193
342. The paper stated that there was a “clear UK military aspiration” to transfer security
responsibilities to Iraqi forces in Muthanna and Maysan in October 2005, with the
remaining MND(SE) provinces (Basra and Dhi Qar) following in April 2006. That was
Minute Anderson to Dinham, 19 June 2005, ‘Back to Office Report: Iraq 13 – 18 June’.
191
Email DFID [junior official] to Iraq Inquiry [junior official], 19 June 2013, ‘Iraq Inquiry New Queries’.
192
Paper Reid, 14 June 2005, ‘Options for Future UK Force Posture in Iraq’.
193
253

---
expected to lead to a significant reduction in the overall level of UK troops in Iraq from
around 8,500 to around 3,000 personnel.
343. On 22 June, over 80 countries and organisations participated in the International
Conference in Brussels.
 The Conference was co-hosted by the EU and US.
194
Mr Straw led the UK delegation. The Box below describes the UK’s engagement in the
development of the Conference.
344. The UK Permanent Representation to the EU in Brussels (UKRep) reported that,
at the Conference, the ITG had set out its vision for the future and asked the
international community to provide more support. Iraq had received many promises
in return; both the Iraqi and the US delegations had emphasised the need to translate
those into action on the ground.
345. UKRep commented that the Conference had been “a further successful step” in
enhancing EU (and wider) engagement in Iraq, following the visit of the EU Troika to Iraq
earlier that month. UKRep had taken the opportunity to brief the EC on the help it could
expect from the UK in opening an office in Baghdad; UKRep would keep pushing to
achieve that by the end of the year.
The International Conference on Iraq, 22 June 2005
Planning began in early 2005 for an International Conference on Iraq, to be co-hosted
by the EU and US.
Mr Straw advised Mr Blair on 24 March that the UK was working closely with the US to
define the scope and objectives of the Conference.
 Key objectives included:
195
ensuring an inclusive process to build a wide base of international support for the
Iraqi political process; and
a reformed approach to donor co-ordination.
US and UK officials discussed the Conference on 31 March.
 The US saw the ITG
196
being in the lead, and using the Conference to set out their “broad direction” and secure
international support for it. Mr Crompton said that the UK agreed with that approach, and
suggested that “deliverables” from the Conference should include:
agreement on an improved mechanism for international assistance; and
securing EU support for the rule of law.
An FCO official advised the 6 May meeting of the Iraq Strategy Group that the EU and US
were not working towards the “outcome orientated” Conference that the UK had hoped
for.
 Sir Nigel Sheinwald said that the UK should not invest enormous effort into shaping
197
the Conference as it was not “mission critical”.
Telegram 7391/05 UKRep Brussels to FCO London, 23 June 2005, ‘Iraq International Conference,
194
Brussels 22 June’.
Minute Straw to Prime Minister, 24 March 2005, ‘Iraq: Ad Hoc Ministerial Meeting’.
195
Minute Cabinet Office [junior official] to Sheinwald, 1 April 2005, ‘Iraq: VTC with US Inter-Agency Team’.
196
Minute Cabinet Office [junior official] to Sheinwald, 9 May 2006, ‘Iraq: Strategy Group’.
197
254

---
10.2 | Reconstruction: July 2004 to July 2009
346. Mr Blair met Prime Minister Ja’afari on 27 June.
198
347. Mr Quarrey’s briefing for Mr Blair suggested that the main points to cover included:
The International Conference. The UK judged that the Conference had been
a success, even if concrete outcomes had been thin.
Reconstruction. The UK was constantly pressing for the better use of
reconstruction funds “so that we get a political dividend”. The UK should
encourage Prime Minister Ja’afari to take a similarly close interest.
348. Mr Quarrey’s record of the meeting indicates that the discussion focused on
security and the constitutional process, and that reconstruction was not raised.
199
349. On 5 July, the British Embassy Baghdad provided an assessment on progress
on donor co-ordination.
 Some progress had been made before and during the
200
International Conference, but a gap was emerging between Iraqi expectations (more
money) and what was needed (better Iraqi strategy and clearer priorities). The ITG
had advised donors to “do anything, because everything is a priority”.
350. Mr Blair met President Bush in the margins of the G8 Summit on 7 July (see
Section 9.4).
 Mr Blair said that the US and UK objective must be to divide Sunni
201
insurgents from foreign jihadists.
351. At its meeting on 13 July, the JIC reviewed the effectiveness of efforts to bring
Sunni Arabs into the political process.
 It judged that:
202
“Winning over Iraq’s Sunni Arab population is key to reducing the insurgency
over time …”
352. Sunni political and insurgent groups did not have a unified strategy. There was a
range of Sunni political objectives: demand for a timetable for MNF withdrawal and the
release of detainees featured strongly. The JIC continued:
“Sunnis also want to ensure they benefit economically from Iraq’s natural resources
(held in predominately Shia and Kurd areas), gain access to jobs and markets, and
see greater evidence of reconstruction – so far efforts to rebuild Sunni areas have
been disproportionally hampered by the security situation.”
Minute Quarrey to Blair, 24 June 2005, ‘Iraq: Your meeting with Prime Minister Ja’afari, 27 July [sic]’.
198
Letter Quarrey to Siddiq, 27 June 2005, ‘Iraq: Prime Minister’s Meeting with Jaafari’.
199
eGram 8254/05 Baghdad to FCO London, 5 July 2005, ‘Iraq: Donor Coordination Sitrep and Prospects
200
for Amman Donor Conference’.
Letter Sheinwald to Adams, 8 July 2005, ‘Prime Minister’s Meeting with President Bush, 7 July’.
201
JIC Assessment, 14 July 2005, ‘Iraq: Outreach to Sunni Arabs’.
202
255

---
353. Mr Straw sent an Iraq Oil and Gas Strategy to Mr Blair on 12 July.
 The strategy,
203
which had been developed by FCO, Department of Trade and Industry (DTI) and DFID
officials over the previous month, defined three UK objectives:
“The development of an efficient, outward-looking and transparent oil and
gas industry, capable of delivering sustainable export revenues to meet the
development needs of the people of Iraq and meeting domestic needs for
energy in an efficient, equitable and secure manner.
Increasing involvement of the private sector, leading to sustained investment
over the next five to 10 years and substantial business for UK companies …
To promote Iraq’s role in international oil and gas markets and as a constructive
influence within OPEC.”
354. Mr Quarrey marked the strategy to Sir Nigel Sheinwald with the comment: “I do not
intend to put in the box! Looks OK.”
 Sir Nigel agreed.
204
205
355. The UK revisited the strategy in March 2006, and retained those objectives.
206
356. The strategy and the UK’s engagement on oil and gas issues are considered in
Section 10.3.
357. Deputy Prime Minister Salih launched the ITG’s National Development Strategy
(NDS) at the fourth meeting of the IRFFI Donor Committee in Amman on 18 and
19 July.
 The IIG had launched an earlier national strategy in Tokyo in 2004.
207
358. In his introductory remarks, Mr Salih said that the high level of unemployment in
Iraq was fuelling economic despair and insecurity. The reconstruction effort had focused
on large-scale, capital-intensive infrastructure projects. Those “mega-projects”, though
appropriate and essential, had not succeeded in providing Iraq’s basic needs quickly
enough. The answer was to complement them with “community-level” projects that
demonstrably changed people’s lives for the better.
359. Mr Salih highlighted the shortfall in funding for electricity supply. The October
2003 World Bank/UN Joint Needs Assessment had estimated that US$20bn would be
required to restore power to 1990 levels. Less than half that amount had been allocated.
Production averaged around 5,000MW against a demand of 20,000MW.
Letter Straw to Blair, 12 July 2005, ‘ Iraq: Oil and Gas Strategy’ attaching Paper FCO/DTI/DFID,
203
[undated], ‘Iraq: Oil and Gas Strategy’.
Manuscript comment Quarrey to Sheinwald, 13 July 2005, on Letter Straw to Blair, 12 July 2005,
204
‘Iraq: Oil and Gas strategy’.
Manuscript comment Sheinwald to Quarrey on Letter Straw to Blair, 12 July 2005, ‘Iraq: Oil and Gas
205
Strategy’.
Paper IPU/FCO, 28 February 2006, ‘UK Objectives for Iraq’s Oil and Gas Sector’.
206
International Reconstruction Fund Facility for Iraq, 18 July 2005, Speech by H E Barham Salih Minister
207
of Planning and Development Cooperation to the International Reconstruction Fund Facility Committee
Meeting, Dead Sea, Jordan,18-19 July 2005.
256

---
10.2 | Reconstruction: July 2004 to July 2009
360. The NDS was organised around four “key drivers of prosperity”:
strengthening the foundation for economic growth;
revitalising the private sector;
improving quality of life; and
strengthening good governance and improving security.
208
361. DFID officials in Iraq commented on the NDS: “Better than before (Tokyo) but
still weak on identification of priorities and objectives. No understanding that resource
constraints will force ITG and donors to make tough choices.”
209
Preparing for transition to Iraqi control in the South
362. The 15 July meeting of the ISG considered a draft version of a paper
from Dr John Reid, the Defence Secretary, on operational transition in Iraq (see
Section 9.4).
210
363. Dr Reid described a process in which Iraqi Security Forces would take primacy
province by province. The MNF would take on a reserve role as they did so. So long
as Iraqi capacity continued to increase and the security situation did not deteriorate
seriously, the transfer would be implemented from October in Maysan and Muthanna.
Basra and Dhi Qar would follow in spring 2006. This would lead to a reduced profile for
UK forces, and reductions in numbers to around 3,000 by summer 2006.
364. The ISG made a number of recommendations for improving the paper, including
that it needed to cover more clearly the implications for other government departments
and international actors.
211
365. DOP(I) met on 21 July, chaired by Mr Blair, and considered Dr Reid’s paper on
operational transition.
212
366. The revised paper stated:
“It is … possible that other (FCO and DFID) activity in Iraq aimed at developing the
Iraqi Police Service and reconstruction will need to be curtailed or reduced, with
consequent implications for HMG’s wider effort, because of the difficulties of running
projects without UK military support and protection. This will need to be looked at in
more detail with Other Government Departments.”
213
Iraqi Strategic Review Board, 30 June 2005, National Development Strategy 2005 – 2007.
208
Report DFID, 11 July 2005, ‘DFID Iraq Weekly Summary, 11 July’.
209
Letter Cabinet Office [junior official] to Iraq Senior Officials, 15 July 2005, ‘MOD Paper on Operational
210
Transition in Iraq’ attaching Paper MOD, [undated],‘Operational Transition in Iraq’.
Letter Cabinet Office [junior official] to Sheinwald, 15 July 2005, ‘Iraq Strategy Group’.
211
Minutes, 21 July 2005, DOP(I).
212
Paper Secretary of State for Defence, 18 July 2005, ‘Operational Transition in Iraq’.
213
257

---
367. The section on “handling” in the previous draft had been expanded to include
“NGOs”:
“The announcement [of] any drawdown of UK forces in the South will have to
be carefully managed to ensure that there is no loss of confidence by NGOs
(in particular the UN agencies and the World Bank), which might lead them to
postpone plans for greater engagement in Iraq.”
368. The section on resources had also been expanded:
“Other Government Departments operating in Iraq may … face increased security
costs as they are forced to seek commercial alternatives to military force protection.”
369. DOP(I) agreed Dr Reid’s recommendation that, subject to the continuation of
current trends in the capacity of the Iraqi security forces and to there being no major
deterioration in the security situation, the UK should plan to implement transition to Iraqi
control in Maysan and Muthanna from around October 2005, and in Dhi Qar and Basra
from around March 2006.
214
370. DOP(I) commented that too much of the money allocated for reconstruction had
been spent on foreign contractors and security.
 The UK should now be focusing on
215
delivering through Iraqi structures.
371. DOP(I) also considered an FCO paper entitled ‘Splitting the Jihadists from the
National Opposition’.
 The FCO recommended action on eight “lines”, the last of which
216
was reconstruction:
“Rapid implementation of reconstruction projects, specifically following large scale
anti-insurgency operations or local cease-fires:
“Aims: Demonstrate ITG/MNF ability to rebuild and compensate following
operations/cease-fires. Quick support to Iraqi capacity to deliver. Installation of basic
services. Establishment of political and security structures. Employment creation.
Deny opportunity to insurgency to work up dissatisfaction.
“Means: … Key donors and ITG to review how to reprogramme/redefine donor
assistance to make available rapidly disbursable aid (eg. creation of a special fund
for quick impact projects in politically sensitive areas), including from the private
sector. Media (foreign and Iraq) coverage of successful redevelopment projects.”
372. DOP(I) agreed the “broad approach” set out in the FCO paper.
217
Minutes, 21 July 2005, DOP(I) meeting; Paper Secretary of State for Defence, 18 July 2005,
214
‘Operational Transition in Iraq’.
Minutes, 21 July 2005, DOP(I) meeting.
215
Paper FCO, 18 July 2005, ‘Iraq: Splitting the Jihadists from the National Opposition’; Minutes,
216
21 July 2005, DOP(I) meeting.
Minutes, 21 July 2005, DOP(I) meeting.
217
258

---
10.2 | Reconstruction: July 2004 to July 2009
Responding to the new US Clear-Hold-Build strategy
373. Ambassador Zalmay Khalilzad succeeded Ambassador John Negroponte as the
US Ambassador to Iraq in June 2005.
218
374. To assess the situation and propose a way forward, Ambassador Khalilzad
established a Joint Civil-Military Strategic Planning Group, generally known as the Red
Cell or Red Team. The Red Team was tasked to devise a plan that would break the back
of the insurgency within one year and defeat it within three.
375. Before Ambassador Khalilzad’s his arrival in Iraq, the DoD and the State
Department had initiated independent reviews of reconstruction strategy (led by General
Gary Luck and Ambassador Richard Jones respectively). Those reviews informed the
new approach developed by Ambassador Khalilzad.
376. A key issue was the amount of US funding that remained available. After a slow
start, the US reconstruction effort was “in high gear”. Of the US$18.4bn appropriated for
IRRF2, three-quarters had been obligated and one-third disbursed.
377. Ambassador Khalilzad met Mr Adam Ingram, Minister of State for the Armed
Forces, on 20 July.
 The Ambassador raised the subject of Provincial Reconstruction
219
Teams (PRTs), some of which had worked well in Afghanistan, and asked whether there
was a role for them in Iraq. Mr Ingram wondered whether PRTs would, in many parts of
Iraq, be too exposed. He also commented that “one of the problems of even considering
such fresh approaches … was the risk that they could be leaked”.
378. Ambassador Khalilzad offered to share US thinking on PRTs with the UK,
including on whether projects should be driven by “operational security” or longer-term
development goals.
379. Mr William Patey, Mr Chaplin’s successor as British Ambassador to Iraq, reported
on 27 July that the availability of electricity and fuel was barely different from a year
earlier.
 Progress was being made, but it would be “a long haul” and managing Iraqi
220
expectations would be key. He commented:
“Ordinary Iraqis are becoming increasingly frustrated that, over two years after
Saddam’s fall, there has been little discernible improvement to essential services …
“Ultimately, the Iraqis need to plan much longer term … There needs to be an
integrated energy strategy … The current focus – including from US advisers – is
short-term. DFID is funding two advisers to help the Ministry of Electricity (and
Ministry of Oil) develop a coherent longer-term strategy, including creating the legal
Bowen SW Jr. Hard Lessons: The Iraq Reconstruction Experience. U.S. Government Printing
218
Office, 2009.
Minute Johnson to DJC DD Iraq, 22 July 2005, ‘Minister(AF) Meeting with Ambassador Khalizad’.
219
Telegram 9933/05 Baghdad to FCO London, 27 July 2005, ‘Iraq: Oil and Electricity: Are Things
220
Getting Better?’.
259

---
and regulatory framework to encourage investment. We should continue to support
this as the only means of creating a sustainable electricity network in Iraq.”
380. Mr Quarrey passed the report to Mr Blair, with the comment:
“The conclusion that the only solution is a long-term plan is consistent with
DFID’s approach but fails to address the damage done in the meantime to the
political process.”
221
381. Lieutenant General Robin Brims, the Senior British Military Representative, Iraq,
reported to Gen Walker on 31 July that “the US with ourselves” were establishing a
“Red Cell” to examine critically counter-insurgency strategy.
222
382. Mr Anderson advised Mr Benn’s Private Secretary on 12 August that, despite
intensive efforts by DFID and MND(SE), Op AMPERE (the US$10m point power
generation project developed by MND(SE) and DFID and approved in March 2005) had
not met its objective of providing additional power during the summer months.
 The
223
failure had been due primarily to inexperienced suppliers, poor security and a lack of
access. Six of the planned 10 generators had now been commissioned; work continued
to commission the remaining four.
383. The Red Team reported on 31 August.
 Section 9.4 describes the report and the
224
UK’s response in detail.
384. The Red Team assessed that the coalition’s current strategy – based on
transitioning security responsibilities to the Iraqi Government – would enable coalition
forces to disengage from Iraq but would leave Iraqi Security Forces that would not be
able to defeat the insurgency in the foreseeable future.
385. The Red Team proposed an alternative strategy, based on what it described
as the “classic ‘ink spot’ counter-insurgency model”, which sought to create success
in small areas and then steadily expand outwards until the areas flowed together
to form larger regions of security.
 Military operations were to be more closely
225
co-ordinated with “political-economic actions” tailored to the specific needs of local
communities. Action was also needed at the national level, to set the conditions for
the counter-insurgency campaign.
386. The report proposed that a Joint Inter-Agency Counter-Insurgency Task Force
should be established to plan, co-ordinate and implement governance reform and
economic sector development work in support of the counter-insurgency campaign.
Minute Quarrey to Prime Minister, 29 July 2005, ‘Iraq Update’.
221
Minute Brims to CDS, 31 July 2005, ‘SBMR-I Weekly Report (172) 31 July 2005’.
222
Minute Anderson to Private Secretary [Benn], 12 August 2005, ‘Iraq Situation Update’ attaching Report
223
DFID, [undated], ‘Iraq Situation Report: 12 August’.
Red Team Report, 31 August 2005, ‘An integrated Counterinsurgency Strategy for Iraq’.
224
Red Team Report, 31 August 2005, ‘An integrated Counterinsurgency Strategy for Iraq’.
225
260

---
10.2 | Reconstruction: July 2004 to July 2009
387. Sir Nigel Sheinwald’s advice to Mr Blair on the Red Team report focused on
political and security aspects of the proposed strategy.
 On the economic aspect of
226
the proposed strategy, he commented:
“There is nothing new to say here. There will be no serious reconstruction effort for
as long as the security situation remains bad, and political engagement at national
and local levels remains poor …
“There is little point in talking about a new surge of economic reconstruction until
we see the shape of the next Iraqi Government.”
388. Hard Lessons identified the Red Team report as one important element of the US
strategy review and development process initiated by Ambassador Khalilzad which, by
the autumn of 2005, had produced a new approach comprising:
A renewed focus on broadening Sunni participation in the political process.
Defeating the insurgency using the “ink-spot” model (articulated by the Red
Team and others). That required closer integration of military and civilian
resources and the use of civilian reconstruction resources as part of a
military-led campaign, and a shift away from large infrastructure projects towards
smaller, Iraqi-led projects designed to deliver jobs and services to the most
vulnerable, violent and politically significant neighbourhoods.
Increased support for provincial governments, including through the deployment
of PRTs into provinces.
Increased support for central government institutions, including by embedding
civilian advisers. The increased support for provincial and central government
reflected US analysis that their strategy of “pulling back to let the Iraqis
do it themselves” had failed; provincial governments remained weak and
disconnected from central government.
227
389. The new strategy would become known as “Clear-Hold-Build”.
390. On 19 September, two UK soldiers were arrested by the Iraqi Police Service in
Basra, following an incident in which they killed one Iraqi police officer and wounded
another (see Section 9.4). The soldiers, and six negotiators who had attempted to
secure their release and who had also been detained, were subsequently released
in an armed operation undertaken by MND(SE). The episode became known as the
Jameat incident.
Minute Sheinwald to Prime Minister, 19 September 2005, ‘Iraq: UK Strategy’.
226
Bowen SW Jr. Hard Lessons: The Iraq Reconstruction Experience. U.S. Government Printing
227
Office, 2009.
261

---
391. Mr James Tansley, the British Consul General in Basra from September 2005 to
April 2006, told the Inquiry:
“The Jameat incident effectively destroyed working relationships between ourselves
and Basra Council and the governorate. Although we patched things up, there was
still an underlying suspicion, and it was difficult to build … particularly constructive
relations with the officialdom or the government in Basra province throughout
my time.”
228
392. Mr Tansley commented that the combination of deteriorating security and,
following the Jameat incident, political constraints limited the progress that the UK could
make on reconstruction, SSR and preparing for the transfer of provincial control to the
Iraqi authorities.
393. Against a background of increasing insecurity, DFID continued to press the World
Bank to accelerate disbursement from its Trust Fund and to establish a presence in Iraq.
394. Dr Shafik met Mr Chrik Poortman, World Bank Vice-President for the Middle East,
on 20 September.
 Mr Poortman argued that the rate of disbursement from the Bank’s
229
Trust Fund was comparable with other post-conflict countries and expressed concern
that faster disbursement could increase the risk of corruption. He also regretted the UK’s
“continual public criticism” of the rate of disbursement, which was damaging the Bank’s
ability to attract donor support.
395. The report of the meeting was copied to DFID and Treasury officials. Mr Anderson
commented:
“Chrik’s arguments about disbursement rates are technically correct …
“That the Bank’s disbursement in Iraq is comparable to other … countries is beside
the point – aid to Iraq is not business as usual. That Iraq requires a different
approach … is the core point that Chrik does not accept.”
230
396. Mr Chakrabarti met Mr Poortman a few days later.
231
397. Mr Chakrabarti’s briefing for the meeting stated that the Bank’s presence in Iraq
comprised one international consultant (now funded by the Bank, formerly by DFID)
and seven local staff. Of the US$400m committed to the World Bank Trust Fund, only
US$31m had been disbursed by July. DFID still saw the Trust Fund “as an emergency
fund to be disbursed quickly”.
Public hearing, 22 June 2010, page 57.
228
Email DFID [junior official] to Dinham and Anderson, 20 September 2005, ‘Read-out from
229
Minouche/Rain Meeting with Chrik’.
Email Anderson to Newton-Smith, 21 September 2005, ‘Chrik’s Views’.
230
Briefing DFID, [undated], ‘Chrik Poortman Meeting – Washington, 24-25 September 2005’.
231
262

---
10.2 | Reconstruction: July 2004 to July 2009
398. The briefing also stated that the World Bank had agreed to channel US$21m from
its Trust Fund to a power project in Najibiyah, through DFID’s IISP. The Najibiyah project
had, however, floundered in the absence of Iraqi Government support; DFID was
exploring “all possible alternative options” for the funding.
399. On 30 September, Mr Dinham sent Sir Nigel Sheinwald a paper providing an
“honest assessment” of progress on reconstruction, following a discussion between
Mr Dinham and Sir Nigel earlier that month.
232
400. The DFID paper listed the achievements that had been made in re-establishing
the economy, electricity generation, water and sanitation, employment, education,
health, and transport and communications. DFID also listed factors which had hindered
reconstruction:
insecurity, which meant that few other donors had a presence on the ground
in Iraq;
poor co-ordination and little buy-in from the Iraqi Government and local
authorities;
limited capacity of Iraqi institutions and rapid turnover of political figures;
“large additional funds … are unlikely to accelerate progress on reconstruction
without corresponding policy and institutional reform and capacity building”;
security costs had “eaten into” reconstruction funds;
the US had been “distracted by hotspot cities” at the expense of a “strategic
reconstruction programme”. Significant amounts of US funding had been
re-allocated from basic services to tackle security and oil;
problems with the sustainability of large-scale projects; and
unrealistic Iraqi and international expectations. In other countries, DFID allowed
between five and 15 years for “the first phase of governance projects”, to allow
time for institutional culture to change. In Iraq, international partners were trying
to reform institutions in less than two years.
401. DFID concluded:
“A carefully balanced approach is needed: on the one hand, an acceptance of the
realistic pace of reconstruction will help to manage expectations and encourage
more sustainable, long-term projects; on the other hand, some continuation of
high-profile, short-term activity will be needed to provide signs of visible progress
while longer-term activity is under way.”
Letter Dinham to Sheinwald, 30 September 2005, ‘Iraq: Reconstruction Situation’ attaching Paper
232
DFID, [undated], ‘DFID Information Note on Reconstruction Progress in Iraq’.
263

---
402. Mr Quarrey passed the DFID paper to Sir Nigel with the comment:
“This has more detail than we’ve seen for a while, and in some areas looks
reasonably encouraging. But overall the picture is still pretty bleak. What the paper
does not give is (a) much sense of what is happening now (eg what’s getting better
or worse); and (b) whether there is much we can do about it. I think we have other,
more immediate priorities for No.10 effort in the short term. Do you want to do
anything with this?”
233
403. Sir Nigel was more critical:
“I take a less positive view. I see it as a lot of useless, mostly input, statistics. But
there’s little on outputs, no comparison of pre-invasion and now, no case studies,
no sense of Najaf then and now. ie not what I asked for.”
234
404. The Inquiry has seen no indication that the paper was passed to Mr Blair, or that
No.10 or Sir Nigel responded to DFID.
405. Also on 30 September, Mr Straw’s Principal Private Secretary sent Mr Quarrey a
paper containing the joint advice of FCO, MOD and DFID officials on the implications
of the Jameat incident.
 Mr Straw had not yet seen and agreed their advice.
235
The FCO/MOD/DFID paper advised:
“The … incident … highlights what was previously more opaque, that we face acute
challenges in achieving our objectives in the south-east region. Stability in the
south-east is being threatened by intense rivalry among political parties and their
militias. Criminality, jockeying for patronage and leaders’ differing political visions
are being exacerbated by tribalism and increasing religiosity.”
406. The paper concluded that “alternative options to our current policy are limited”:
“Our only realistic option is to maintain our course and see the job through.
But we need to make adjustments to our policy, while sticking to our strategic
approach of ensuring in due course successful transition of responsibility for rule
of law in the south-east to the Iraqis.”
407. An immediate problem was the threat of reprisal attacks. DFID and FCO staff were
“essentially locked down”.
Manuscript comment Quarrey to Sheinwald, 4 October 2005, on Letter Dinham to Sheinwald,
233
30 September 2005, ‘Iraq: Reconstruction Situation’.
Manuscript comment Sheinwald to Quarrey, 6 October 2005, on Letter Dinham to Sheinwald,
234
30 September 2005, ‘Iraq: Reconstruction Situation’.
Letter Hayes to Quarrey, 30 September 2005, ‘Iraq: Basra’ attaching Paper FCO/MOD/DFID,
235
30 September 2005, ‘South-East Iraq: Impact of Security Incident in Basra’.
264

---
10.2 | Reconstruction: July 2004 to July 2009
408. The authors identified a number of “longer-term challenges” including:
“We may not be able to deliver, by next year, the minimum standards
required in rule of law and governance.” The UK should consider whether
its aspiration to draw down troops by the middle of 2006 would be premature,
and how its response to a more challenging security environment might deter
organisations such as the UN and World Bank from establishing a presence in
the South.
“We will need to allocate more resources, which might include military
resources, to security.”
409. Over the weekend of 1 and 2 October, Mr Blair considered separate pieces of
advice from Sir Nigel Sheinwald and Mr Powell on the implications of the Red Team
report, the FCO/MOD/DFID paper on the implications of the Jameat incident, and a
28 September JIC Assessment.
236
410. Mr Blair set out his conclusions in a Note to No.10 staff on 2 October:
“I don’t think the Red Team report is advocating a different strategy; just a means of
implementing the existing one …
“The ‘ink spot’ strategy is right. It isn’t what we have done so far. What we’ve done is
take a city, give it back to the Iraqis and hope. The ‘ink spot’ strategy is to take it and
then only when the Iraqi civilian capability of governance is properly established with
the necessary military back-up, do we withdraw.”
237
411. Sir Nigel Sheinwald wrote to Mr Straw’s Principal Private Secretary on 4 October,
in response to the 30 September FCO/MOD/DFID paper on the implications of the
Jameat incident.
 Copies of the letter were sent to Cabinet Office, MOD, DFID, FCO,
238
Home Office and Treasury officials.
412. Sir Nigel wrote:
“The Prime Minister agrees that we do not need to change our overall strategy.
He is convinced, however, that we need a major and sustained push over the next
few months on the political and security lines of operation if we are to get what
we need – the political process moving ahead on time and producing an effective
and moderate Iraqi Government after the elections, with visible progress on the
Iraqiisation of security.”
Minute Quarrey to Prime Minister, 30 September 2005, ‘Iraq Update’.
236
Note Blair, 2 October 2005, [untitled].
237
Letter Sheinwald to Hayes, 4 October 2005, ‘Iraq Strategy’.
238
265

---
413. Sir Nigel went on to set out in detail Mr Blair’s views in relation to policy on the
political process and security. The single paragraph on reconstruction read:
“It is unlikely that we will be able to enhance significantly the impact of reconstruction
activities in the period before elections. But he [Mr Blair] would be grateful if
Hilary Benn could work hard with the World Bank and UN in particular – their future
engagement is critical. We also need a more effective link-up between DFID and the
US agencies involved.”
414. Sir Nigel reported that Mr Blair planned to chair a meeting of DOP(I) every fortnight
if possible. Sir Nigel would chair weekly meetings of senior officials. Mr Straw and
Dr Reid were also to chair regular Ministerial meetings in their areas.
415. Mr Chakrabarti and Mr Dinham visited Iraq from 4 to 6 October to review DFID’s
programme and consider future plans in the light of the forthcoming Iraqi elections and
UK military transition planning.
239
416. Their report to Mr Benn, copies of which were sent to Sir Nigel Sheinwald,
senior officials in the Cabinet Office, MOD, FCO and the Treasury, and UK military
commanders and officials in Iraq, recommended that DFID should shift its focus from
the South and infrastructure projects to building institutional capacity in Baghdad. That
recommendation reflected “remarkable unanimity of advice from a range of interlocutors,
including our political and military colleagues in both Baghdad and Basra” on where
DFID’s comparative advantage lay in a “uniquely difficult environment”.
417. Mr Chakrabarti and Mr Dinham reported that UN staff were back in Iraq and
playing a key role in donor co-ordination. The EC was “visible, albeit with a small and
focused presence”. A key gap remained the absence of a permanent World Bank or IMF
representative.
418. The Iraqi Government remained unenthusiastic on the Najibiyah power plant
project (for which DFID had hoped to secure US$21m in funding from the World Bank
Trust Fund); there was no value in pressing this further.
419. On funding, the US was now looking for other donors to “pick up the tab” for
reconstruction; none had yet stepped forward:
“A[n] … immediate worry for the first year of an incoming Government is the
likelihood of a funding crisis as US money thins out and the multilaterals are not
yet on stream.”
420. If DFID was to focus on building institutional capacity in Baghdad, it would need
to consider whether its current model – using international consultants, with their
attendant high security costs – remained “fit for purpose”. The Iraqi Government was
Minute Chakrabarti and Dinham to Secretary of State [DFID], 7 October 2005, ‘Iraq Visit,
239
4 – 6 October 2005’.
266

---
10.2 | Reconstruction: July 2004 to July 2009
starting to turn down offers of assistance, primarily on cost grounds. Mr Chakrabarti and
Mr Dinham reported that their initial feeling was that alternative models now needed to
be explored, including:
a greater use of consultants drawn from the Iraqi diaspora;
the use of current or former senior UK civil servants on short visits; and
deployment of additional DFID advisers to Baghdad and Basra.
421. Mr Chakrabarti and Mr Dinham concluded that DFID should produce a new
Country Assistance Plan (CAP) for Iraq, setting out its intentions.
422. DFID told the Inquiry that it could not find any evidence of a response from
Mr Benn or of any documents relating to a consequent discussion of aid modalities,
and that work to produce a new CAP was not taken forward.
240
423. On 10 October, the Joint Committee to Transfer Security Responsibility (JCTSR)
produced its “Conditions for Provincial Transfer”, which set the framework for MNF-I
to transfer security responsibility to an Iraqi civilian authority (see Section 9.4).
241
The document set out a series of standards in four areas:
the insurgency threat,
ISF capability,
governance capacity, and
residual support from coalition forces.
424. General Mike Jackson, Chief of the General Staff, visited Iraq from 10 to
13 October.
 His report to Gen Walker, copies of which were sent to senior military
242
officers only, welcomed the US proposal to deploy PRTs as they would address the
critical need to build the capacity of the Iraqi Government. The UK would be expected
to share “the PRT burden” in the South.
425. Gen Jackson agreed with the Red Team’s argument that the insurgency would only
be defeated by a co-ordinated effort across all lines of operation, but cautioned that the
“ink spot” concept sounded similar to the “seven cities” and “Strategic Cities” initiatives
which had floundered in 2004:
“I am increasingly hearing the same strategic principles (undoubtedly sound
ones) being dressed up in different initiatives, but without ever being implemented
effectively on the ground. I suspect there are several reasons for this: certainly
a lack of resources for non-military LOO [lines of operation], but also, perhaps,
entrusting responsibility for delivering these lines of operation to the wrong type of
Email DFID [junior official] to Iraq Inquiry [junior official], 19 June 2013, ‘Iraq Inquiry New Queries’.
240
International Mandate Republic of Iraq National Security Council, 10 October 2005, ‘Joint Committee
241
to Transfer Security Responsibility’.
Minute Jackson to CDS, 18 October 2005, ‘CGS Visit to Iraq: 10-13 October 05’.
242
267

---
people. There are many capable diplomats in both the UK and US Embassies, but
are they the best people to deliver predominately ‘non-diplomatic’ objectives?”
426. The referendum on Iraq’s draft Constitution took place on 15 October.
243
427. The day after the referendum, President Talabani issued a decree announcing
that Parliamentary elections would take place on 15 December, in accordance with
the TAL.
244
428. Mr Patey reported by telegram on 18 October that the new US approach to
reconstruction and building Iraqi Government capacity had two strands:
capacity-development programmes in 10 national ministries; and
15 PRTs and one Regional Reconstruction Team (RRT), to cover the provinces
under the Kurdish Regional Government.
245
429. MND(SE) and DFID had fed in concerns over the introduction of PRTs, centred on
the lack of consultation with the Iraqi Government, coalition members and the UN.
430. The first three PRTs would be established on 1 November. The US expected all the
PRTs and the RRT to be established by March/April 2006.
431. Mr Patey advised that the US expected coalition partners to bear the running costs
of PRTs in their areas. Those costs would be significant.
432. Dr Rice told the US Senate Foreign Relations Committee on 19 October that the
US strategy to “assure victory” in Iraq, working with the Iraqi Government, was to “clear,
hold, and build”.
 She described the US strategy:
246
“With our Iraqi allies, we are working to:
Clear the toughest places – no sanctuaries to the enemy – and disrupt
foreign support for the insurgents.
Hold and steadily enlarge the secure areas, integrating political and
economic outreach with our military operations.
Build truly national institutions working with more capable provincial and
local authorities. Embodying a national compact – not tools of a particular
sect or ethnic group – these Iraqi institutions must sustain security forces,
bring rule of law, visibly deliver essential services, and offer the Iraqi people
hope for a better economic future.”
eGram 15692/05 Baghdad to FCO London, 16 October 2005, ‘Iraq: Constitution: Referendum Day
243
Passes Peacefully’.
eGram 15761/05 Baghdad to FCO London, 17 October 2005, ‘Iraq: Elections’.
244
eGram 15865/05 Baghdad to FCO London, 18 October 2005, ‘Iraq: Provincial Reconstruction Teams’.
245
US Department of State Archive, 19 October 2005, Iraq and US Policy: Secretary Condoleezza Rice,
246
Opening Remarks Before the Senate Foreign Relations Committee, Washington, DC, October 19 2005.
268

---
10.2 | Reconstruction: July 2004 to July 2009
433. The strategy required deeper integration of civilian and military activities, including
by restructuring part of the US Mission in Iraq as PRTs:
“These will be civil-military teams … training police, setting up courts, and helping
local governments with essential services like sewerage treatment or irrigation.
The first of these PRTs will take the field next month.”
434. Hard Lessons described the difficulties the US experienced in establishing PRTs:
“Coaxing the Departments of State and Defense to set the terms of their first
major operational collaboration in Iraq required a Herculean effort … A patchwork
quilt of memoranda of agreement, cables, and military orders – many of them at
cross-purposes – evolved to codify policy for PRTs. More than a year elapsed
before basic issues of budgets, the provision of security, and command and control
relationships were resolved, delaying full deployment of the PRTs and limiting their
early effectiveness in the field.”
247
435. The 3 November meeting of DOP(I) considered an IPU discussion paper on how
PRTs could be configured to “add value to current arrangements”.
248
436. The IPU paper set out lessons from Afghanistan, and concluded that there was no
“fixed template” for a PRT. PRTs were most effective when:
they contained an appropriately resourced, integrated military and civilian team;
they had the support of local authorities, a close working relationship with
international organisations and NGOs, and sought to extend the reach of central
authorities; and
they operated in relatively benign security environments where they could seek
to contain rather than confront conflict.
437. The IPU identified three major risks to the implementation of the US proposal:
a lack of Iraqi “buy-in” at local and national level;
a perception among “local Iraqis” that PRTs represented a failure to deliver a
transfer of control to Iraqis; and
a lack of resources. The success of the PRTs would be commensurate, to
some degree, with the financial resources available to them. The US planned
to fund the three pilot PRTs from within existing resources. The UK would
need to consider whether further PRTs could be established on that basis:
“In particular, we would need to ensure that PRTs did not divert … effort from
essential capacity-building efforts elsewhere. In MND(SE) existing military/
Bowen SW Jr. Hard Lessons: The Iraq Reconstruction Experience. U.S. Government Printing
247
Office, 2009.
Paper IPU, October 2005, ‘Provincial Reconstruction Teams (PRTs) in Iraq: Discussion Paper’.
248
269

---
civilian teams … could form the basis for the [PRT] teams, together with the
DFID-funded single Public Administration Adviser per province.”
438. DFID briefing for Mr Benn for the DOP(I) meeting stated:
“We and MOD are both concerned about the risks of this approach. It is expensive,
will divert funding from other priorities, and we do not believe it will make a dramatic
difference in outcomes. It may slow military transition … The agreed Whitehall
approach is that we will be constructive; find out more and try and influence the US
approach; and that we will repackage our effort in the South as a PRT but not do
very much differently.”
249
439. At DOP(I), Ministers commented that PRTs should be tailored to their environment,
and that Iraqi ownership and the involvement of international donors were essential.
250
440. The British Embassy Baghdad reported on 8 November that the US Embassy
was happy to allow the UK time to develop its own ideas for PRTs in the South, and
to be fully engaged in planning.
 The strong preference of the US, however, was for
251
individual PRTs to be established in each of the four southern provinces (in line with the
US approach in the rest of Iraq). The Embassy had argued that the UK would need to
take account of existing governance arrangements in the South, and the effect of PRTs
on the transfer of security responsibility.
441. An MOD briefing for Gen Walker described that effect:
“The [US] proposal sees the establishment of a … PRT in every Province for at least
two years. This would almost certainly undermine MND(SE) transition plans, with
a significant risk that UK forces would be fixed in Maysan and Muthanna into the
medium term.”
252
442. Dr Rice inaugurated the first PRT in Iraq on 11 November during a visit to Mosul.
253
443. Dr Reid told the 15 November meeting of DOP(I) that the UK’s exit from Muthanna
and Maysan had been delayed from February until May 2006, reflecting the UK’s
commitment to the Japanese.
 Dr Reid hoped it would be possible to complete the
254
handover within this timescale in order to start reducing the UK’s troop commitment in
Iraq during 2006.
Minute DFID [junior official] to Private Secretary [DFID], 1 November 2005, ‘Iraq: Oral Briefing in
249
Preparation for DOP(I), 3 November’.
Minutes, 3 November 2005, DOP(I) meeting.
250
eGram 17627/05 Baghdad to FCO London, 8 November 2005, ‘Iraq: Provincial Reconstruction Teams
251
(PRTs)’.
Minute DCJO(Ops) to PSO/CDS, 14 November 2005, ‘Provincial Reconstruction Teams in MND(SE) –
252
Implementation’.
US Institute of Peace, 20 March 2013, Provincial Reconstruction Teams in Iraq.
253
Minutes, 15 November 2005, DOP(I) meeting.
254
270

---
10.2 | Reconstruction: July 2004 to July 2009
444. The British Embassy Baghdad provided further advice on US views on
22 November.
 US Ambassador Dan Speckhard (Head of the IRMO) had told them that
255
Ambassador Khalilzad had no intention of running Iraq, but would not allow the mission
to fail because the Iraqi Government could not swiftly establish effective institutions at
national or local level. The UK should see PRTs as providing a “one-off structural shot
in the arm” to establish those institutions while international military forces remained to
support civilian activities.
445. Ambassador Speckhard had said that the US remained content for the UK to offer
a way forward in the South, but there were “clear red lines”:
Civilian and military operations must be integrated.
“[T]here must be a ‘genuine’ PRT in each province – satellite PRTs served by
resources located in another Governorate would not be an adequate option for
substantive not just political reasons.”
PRTs must be a “new venture”, supported by additional resources. “Rebadging”
existing efforts under a PRT banner would not be well received.
446. The Embassy commented that it should be possible to present a proposal for four
PRTs transitioning to two as consistent with US objectives.
447. Following a visit to Iraq from 22 to 23 November, Gen Walker advised Dr Reid:
“The jury is out on the pilot PRTs – both amongst the military and the diplomats.
Whatever the outcome, I recommend an early bid to run them in the four
MND(SE) provinces to save us heartache later. If we don’t, they have the potential
to fix us through force protection requirements at places and for periods not
of our choosing.”
256
448. The DOP(I) meeting on 1 December considered an IPU paper on how the UK
should respond to the US proposal on PRTs.
257
449. Mr Benn’s briefing for the meeting stated that, while the US wanted to see PRTs in
all of Iraq’s Provinces, financial constraints made it unlikely it would be able to establish
its own PRTs in the South.
258
450. The IPU paper identified three options for the UK:
Support four PRTs in the four southern provinces until 2008 (the US envisaged
that PRTs would operate for two years with international staff, and then for a
further two years with Iraqi staff only). That would “match” the US initiative, but
eGram Baghdad to FCO London, 22 November 2005, ‘Iraq: Update PRTs’.
255
Minute CDS to SofS [MOD], 25 November 2005, ‘CDS’s Visit to Iraq 22-23 Nov 05’.
256
Minutes, 1 December 2005, DOP(I) meeting.
257
Minute DFID [junior official] to Private Secretary [DFID], 29 November 2005, ‘Briefing for DOP(I),
258
1 December 2005 Meeting’ attaching Briefing DFID, 30 November 2005, ‘Flag B: Background Briefing’.
271

---
would mean extending the UK military presence in the South beyond current
planned dates for transition (PRTs would require appropriate force protection
and Quick Response Forces), and require significant additional resources for
programmes and security.
Establish one PRT in Basra to cover all of MND(SE). That would not affect UK
plans for transition in the other three southern provinces. The US might want to
establish its own PRTs in those provinces, increasing Iraqi resentment of the US
presence and raising presentational difficulties in the UK if the US was seen to
take over from the UK in the UK’s area.
Transition from “(mini) PRTs” in four provinces towards a single “super-PRT” in
Basra. That would ensure coverage across MND(SE) but would not affect UK
plans for transition.
259
451. The IPU assessed that while none of the options was “satisfactory”, the third option
was best. It would permit continued governance and capacity-building work in all four
provinces, would not affect UK military transition planning, and would minimise security
risks to civilian staff.
452. The IPU recommended that DOP(I):
Agree that the UK establish a PRT structure in southern Iraq, with Iraqi buy-in.
Agree that the focus of the PRT should be on improving co-ordination and
delivery of UK assistance, strengthening the links between the central authorities
and Governorates, and improving the UK’s “strategic oversight” of southern Iraq.
Accept that while there were “presentational advantages” in establishing a PRT
in MND(SE), improvements in the effectiveness of the UK’s engagement would
be “marginal”.
Note that while the PRT models might encourage other coalition partners to
engage in reconstruction in the South (early indications were that Germany and
Japan might supply experts or funding), multilateral donors were known to be
sceptical about the PRT model and were unlikely to engage fully.
Adapt the US PRT model to suit local circumstances in the four southern
provinces:
In Basra, the current effort should be “re-organised along PRT lines”,
{
{
with the addition of a UK senior civil servant as its head. This regional
“super-PRT” would comprise around 30 civilian staff, 21 military officers,
and between 20 and 30 locally engaged staff.
In Dhi Qar, the current effort should also be “re-organised along PRT lines”,
{
{
possibly staffed and led by Italy until transition.
In Maysan and Muthanna, the current effort should continue “under a
{
{
PRT banner” until UK military transition, at which time Iraqi teams could
Paper IPU, 28 November 2005, ‘Iraq: Provincial Reconstruction Teams’.
259
272

---
10.2 | Reconstruction: July 2004 to July 2009
be supported by surge capacity from Dhi Qar and Basra (and eventually
just Basra).
453. The IPU described this as the “4-2-1” model, as four PRTs reduced to two (Basra
and Dhi Qar) and then one (Basra) over time.
454. The IPU advised that the US would need to agree the UK model, which might
require Ministerial-level discussions with US counterparts.
455. At the meeting, Mr Straw said that the IPU paper “proposed that we went along
with the United States’ proposal but without disrupting our own plans for military
transition”.
 Dr Reid agreed that the UK response should be positive, but stressed the
260
need to keep control of and tailor developing PRT plans in the provinces where the UK
was directly involved.
456. DOP(I) agreed the paper.
261
457. Officials revisited the decision to adopt a 4-2-1 model in January 2006.
458. Mr Straw wrote to Mr Benn at the end of November, reporting that the Deputy
Governor of Basra and members of the Basra Provincial Council had pressed for more
visible UK development projects, and had drawn attention to a number of DFID projects
that had recently been closed.
262
459. Mr Straw understood that those projects had been funded from the employment
generation component of the southern Iraq Employment and Services Programme
(SIESP), which DFID had closed down in August 2005. Mr Straw recognised the security
constraints and the need to ensure funds were properly used, but asked that DFID
officials look for some way to respond to the Councillors’ request for “highly visible,
‘flagship’ projects”.
460. Mr Benn replied on 9 December, highlighting the work DFID was doing in Basra
and with the Provincial Council.
 He did not offer new proposals and cautioned that
263
DFID had to be “extremely careful” about publicising reconstruction projects, in case
such publicity made workers and projects more attractive targets for insurgents.
461. The Iraqi elections took place on 15 December.
 Mr Patey reported that the day
264
had passed off peacefully with no major security events.
Minutes, 1 December 2005, DOP(I) meeting.
260
Minutes, 1 December 2005, DOP(I) meeting.
261
Letter Straw to Benn, 28 November 2005, ‘Basra Development Projects: My Meeting with Basra
262
Provincial Council, 11 November’.
Letter Benn to Straw, 9 December 2005, ‘Basra Development Projects: Your Meeting with Basra
263
Provincial Council, 11 November’.
eGram 20961/05 Baghdad to FCO London, 16 December 2005, ‘Iraq: Elections: Election Day’.
264
273

---
462. Papers for the final DOP(I) meeting of 2005, on 20 December, included a
post-election work plan by the IPU, an update on progress with Iraqiisation and a note
on the handover of security responsibility.
265
463. The IPU work plan described the UK’s immediate objectives post election as:
“
A short and well-managed interregnum between Transitional Government and
the next Government, leading to;
Rapid formation of a competent and representative Government, legitimate in
the eyes of all Iraq’s communities, followed by;
A limited number of key decisions (which serve the Iraqi people and partnership
between Iraq and the Coalition) taken quickly and visibly, in parallel with;
Increasing Sunni Arab political participation and;
Smooth progress in the South-East towards transition
Visible international commitment, in context of 2006 partnership with Iraq.”
266
464. The IPU hoped that it might be possible for an Iraqi government to be formed by
the end of January, six weeks after the election.
465. Negotiations to form a new government continued into spring 2006. Section 9.4
describes UK efforts to encourage the formation of a broad and inclusive government of
national unity.
466. One month after the DOP(I) decision to adopt a 4-2-1 model for PRTs in the South,
the UK adopted a new model which focused on Basra and Dhi Qar only.
467. Air Chief Marshal Glenn Torpy, the Chief of Joint Operations, advised Lt Gen Fry
on 21 December that the 4-2-1 model appeared to satisfy the US.
 The UK now
267
needed to press ahead quickly to keep the initiative. First indications were that neither
the FCO nor DFID could find additional financial resources; the MOD would have to
“bridge the gap”. Initial funding requirements might be “modest” and could be generated
by making savings elsewhere in MND(SE). The MOD would also need to push the other
departments to deploy the staff necessary to get the PRTs off the ground quickly.
468. The 29 December IPU update for DOP(I) members stated that, faced with logistical
and financial difficulties, US enthusiasm for the PRT model was waning and their roll-out
timetable was slipping.
 US officials were “increasingly flexible” about UK plans for the
268
PRT structure in the South and would “not look too closely at implementation (especially
in Maysan and Muthanna)”. That provided the UK with an opportunity to establish the
Paper Cabinet Office, 19 December 2005, ‘DOP(I) Meeting: Agenda’.
265
Paper IPU, 16 December 2005, ‘Iraq: Post-Election: UK Work Plan’.
266
Minute CJO to DCDS(C), 21 December 2005, ‘Key Operational Issues for Early 2006’.
267
Letter Siddiq to Quarrey, 29 December 2005, ‘Iraq: Update as at 29 December’ attaching Paper IPU,
268
29 December 2005, ‘Iraq: Update as at 29 December’.
274

---
10.2 | Reconstruction: July 2004 to July 2009
PRT structure which best fitted the situation in the South and to ensure that the PRTs
assisted rather than hindered “our main transition effort”.
469. The Cabinet Office chaired a video conference of officials in London, PJHQ, Basra
and Baghdad on 5 January 2006 to discuss how to establish PRTs in the South.
 The
269
record of the meeting stated that:
“With the US in disarray over PRTs, and following further UK scoping work in
theatre, a 4-2-1 approach to PRTs no longer appears to be either a necessary
or best solution.”
470. There was a fundamental mismatch between:
the timelines for UK military transition in Maysan and Muthanna (planned for
May 2006, only five months away);
the civilian and military resources available; and
the time needed to recruit, train, deploy and get value from staff posted into
a new PRT.
471. A focus on Basra and Dhi Qar was likely to be “sellable to the US”.
472. The meeting concluded that Ministers should be invited to agree a revised
approach that focused on Basra and Dhi Qar.
473. Ministers approved the new approach, comprising a UK-led PRT in Basra and
an Italian-led PRT in Dhi Qar, later that month.
270
474. A DFID official briefed Mr Benn on 31 January that:
“We [DFID] are working to ensure that management mechanisms and funding
remain shared responsibilities between the three departments [MOD, FCO and
DFID]. We would welcome a discussion with you about our ideas on how to remain
helpful and engaged, while avoiding being asked to lead on PRTs.”
271
475. The UK-led PRT in Basra was established in May 2006.
476. In her evidence to the Inquiry, Ms Cameron, who had visited Iraq over Christmas
2005 to help develop the UK’s response to the US PRT proposal, suggested that the
need to see off the “bad ideas” encapsulated in the proposal, and the need to develop
a response which did not undermine the UK’s plans for transition in the South, had
meant that the UK had not had the time to stand back and think through what it needed
to deliver in Basra.
 She concluded that the PRT model was an improvement on the
272
Minute Cabinet Office [junior official] to Cabinet Office [junior official] 5 January 2006, ‘Iraq: PRTs’.
269
Paper DFID, 10 January 2006, ‘Iraq Update’.
270
Paper DFID, 10 January 2006, ‘Iraq Update’.
271
Public hearing, 22 June 2010, pages 100-101.
272
275

---
previous, more fragmented, arrangement, but less of a “step-change” than it might
have been.
477. Mr Tansley agreed with that assessment.
273
Preparing for the transfer of security responsibility in Maysan
and Muthanna
478. Section 9.4 describes planning and preparations for the transfer of lead
responsibility for security in Muthanna and Maysan to the Iraqi authorities (scheduled
for May 2006).
479. Mr Patey issued his annual review of the state of Iraq on 10 January.
 He
274
characterised 2005 as a “year of democracy”, despite the persistent violence. The
development of the Constitution and elections had diverted attention from establishing
“effective governance”, and in a number of areas Iraq had regressed:
“The year ended with Baghdad on three hours of power a day and falls in oil exports.
The Government did just enough (courtesy of a high degree of flexibility from the
IMF and much help from us) to achieve an interim SBA [Stand-By Arrangement] that
keeps the debt relief programme in track but there is not much else to report by way
of achievements.”
480. Mr Straw visited Iraq on 6 and 7 January. His report to Mr Blair focused on
progress in forming a new Iraqi Government but also highlighted the need to consider
how to increase international engagement.
275
481. The key would be to persuade the UN to play a more active role. The UK and US
were working on the problem of providing the UN with air assets and security. The UK
also needed to persuade the US “to take the UN more seriously into its confidence”:
the US had been receptive at official level but the message needed to be reinforced
at a political level.
482. In discussion with President Bush on 10 January, Mr Blair said that it would
help to unlock outstanding aid pledges if the new Iraqi Government set out a “forward
programme” covering security, coalition posture and reconstruction, which the UN and
coalition could get behind.
276
483. The 12 January meeting of DOP(I) discussed Mr Straw’s report.
277
Public hearing, 22 June 2010, page 101.
273
eGram 384/06 Patey to FCO London, 10 January 2006, ‘Iraq: Annual Review’.
274
Letter Straw to Prime Minister, 11 January 2006, ‘Iraq: Post-Elections and Government Formation’.
275
Letter Quarrey to Siddiq, 10 January 2006, ‘Prime Minister’s VTC with President Bush: Middle
276
East Issues’.
Minutes, 12 January 2006, DOP(I) meeting.
277
276

---
10.2 | Reconstruction: July 2004 to July 2009
484. Mr Straw’s briefing for the meeting stated that the obstacles to deeper UN
engagement were “acute scepticism” within UN headquarters about Iraq and “justifiable”
UN concern that it lacked the transport and security assets it needed to do a decent
job.
 On the latter point, only the US had sufficient resources to help. The UK was
278
lobbying the US to engage with and support the UN, using the argument that an
empowered UN leading international engagement in 2006 offered the US (and the UK)
a way of gradually reducing their commitment.
485. At the DOP(I) meeting, Ministers commented that a “new effort” was needed to
increase UN engagement in Iraq in 2006.
279
486. Mr Blair’s Private Secretary advised him on 17 January that the power situation
in Baghdad was “dire”, with only two hours of electricity a day.
280
487. In discussion with President Bush on 17 January, Mr Blair suggested that there
should be a big push on the UN.
The UN had to show leadership.
281
488. The Italian Government announced on 19 January that it hoped to withdraw Italian
troops from Dhi Qar by the end of the year.
282
489. The Cabinet agreed on 26 January to deploy UK troops to Helmand province,
Afghanistan (see Section 9.4).
490. Mr Straw sent two IPU papers to Mr Blair on 7 February.
 Copies of Mr Straw’s
283
letter and the IPU papers were sent to DOP(I) members and Sir Gus O’Donnell, the
Cabinet Secretary.
491. The first paper considered how the UN should transform its role in Iraq.
 The UK
284
wanted the UN to:
contribute to the new international partnership that the UK envisaged;
act as an honest broker between Iraqi communities, before and after
government formation;
support provincial elections and the constitutional review;
help reduce the risk of conflict in Kirkuk; and
scale up their reconstruction and development presence.
FCO [junior official] to Foreign Secretary, 10 January 2006, ‘Iraq: DOP-I Meeting, 12 January’.
278
Minutes, 12 January 2006, DOP(I) meeting.
279
Minute Phillipson to Prime Minister, 17 January 2006, ‘VTC with President Bush, 1220 17 January
280
2006’.
Letter Quarrey to Siddiq, 17 January 2006, ‘Prime Minister’s VTC with President Bush: Middle
281
East Issues’.
BBC News, 19 January 2006, Italy to pull out of Iraq in 2006.
282
Letter Straw to Prime Minister, 7 February 2006, ‘Iraq: International Partnership and the UN’s Role in
283
2006’ attaching Paper IPU, 3 February 2006, ‘Iraq: UN Role in 2006’ and Paper IPU, 1 February 2006,
‘Iraq: Implementing the Concept from Security Coalition to International Partnership’.
Paper IPU, 3 February 2006, ‘Iraq: UN Role in 2006’.
284
277

---
492. On reconstruction and development, the UN was now a “key player”. UN
development agencies wanted to increase their presence in Iraq, but with a UN ceiling of
125 staff and priority consistently given to constitutional and political specialists, the UN
could “at best” accommodate only three development or humanitarian specialists at any
one time. The UK also wanted the UN to do more to help improve Iraqi observance of
human rights; at present, the UN appeared reluctant to engage.
493. The UK would help secure increased UN engagement through Ministerial
and official level lobbying of the UN (to encourage them to play a greater role), the
US (to underline the value of the UN), and the EC, Japan and European countries
(to get them to lobby the UN to play a greater role, and to fund it to do so).
494. In his letter to Mr Blair, Mr Straw described a transformed UN effort as “a catalyst
to broader and deeper international engagement”.
285
495. The second paper considered how the UK could support transition in Iraq from a
“primarily security based coalition” to a broader international partnership.
 The UK’s
286
strategic objective would be to enable the Iraqi Government to assume more effective
control over Iraqi territory and the security, political and economic agendas. The UK
would seek to develop a broader international partnership, which would require improved
security and an increased UN presence.
496. Mr Tansley reported from Basra on 20 January that the situation in Maysan and
Muthanna was likely to allow a transfer of security responsibilities in May.
 Muthanna
287
was the poorest province in Iraq but essential services were “adequate” and “basic
governance structures” were functioning. Maysan had a weak economy but enjoyed
better essential services and more effective governance than Muthanna. Securing
effective links with central Government would be critical for both provinces.
497. Mr Tansley commented on the decision not to establish PRTs in those provinces:
“The situation … in Maysan and Al-Muthanna underlines why PRTs in those
provinces are not required. Military transition will mean no international staff will
be stationed in Maysan and Muthanna, and travel there by them is likely to be only
possible with military escort (it would likely require a battle group). This will also
affect our international partners including the UN … and USAID … (this will need to
be factored into our discussions with the Americans on the 2-1 PRT formula).”
498. The DOP(I) meeting on 2 February discussed transfer of security responsibility for
Maysan and Muthanna.
288
Letter Straw to Prime Minister, 7 February 2006, ‘Iraq: International Partnership and the UN’s Role
285
in 2006’.
Paper IPU, 1 February 2006, ‘Iraq: Implementing the Concept from Security Coalition to International
286
Partnership’.
eGram 1266/06 Basra to FCO London, 20 January 2006, ‘Iraq: Military Transition in Maysan and
287
Muthanna’.
Minutes, 2 February 2006, DOP(I) meeting.
288
278

---
10.2 | Reconstruction: July 2004 to July 2009
499. Ministers commented that the UK needed to consider transition in the wider context
of the legacy that the UK would leave behind in those provinces.
500. Ministers also commented that it would not be possible to retain DFID international
staff in Maysan and Muthanna after transition. In practice, their contribution was “useful
but not vital” and infrastructure projects would continue. Civilian control of both provinces
had been in the hands of the Iraqis since the dissolution of the Coalition Provisional
Authority (CPA) and even without the transition, the intention was to focus the
reconstruction effort in the South on Basra and Dhi Qar. The security challenges posed
by the transition have a significant impact on other donors, including the UN.
501. DOP(I) commissioned the MOD to produce a paper on the transition reflecting
cross-departmental concerns about the transition, “based on a robust assessment of the
conditions in the two provinces”.
502. Dr Reid presented that paper to DOP(I) on 15 February (see Section 9.4).
289
503. The MOD paper recommended that both provinces should transition as soon as
possible, with the end of May as a target date.
504. The MOD stated that the withdrawal of coalition forces would reduce the amount
of development assistance that could be provided to Muthanna and Maysan by the UK
and other donors, and confirmed that DFID was “content with this, recognising that their
existing support is useful, but not essential, to provincial stability”. The MOD continued:
“DFID will encourage other donors (e.g. the Japanese) to ensure that any
unfinished … projects are completed before closure of permanent bases or able
to be completed by local staff and contractors in slower time, and that plans for
operation and maintenance of completed projects have been made … DFID will
encourage donors with large numbers of local staff (USAID, the UN) to consider how
best they could deploy these in Maysan and Muthanna to continue capacity building
and governance support.”
505. Commanders in MND(SE) were confident that they could facilitate travel by FCO,
DFID and international personnel into the provinces after transition.
506. The MOD assessed that the UK’s legacy would be “considerable”. ISF
development was on track and would complete in October 2006. In addition:
“UK support has also helped Provincial Governments get on their feet. Working
with ministries in Baghdad, Provincial Councils are able to take decisions, deliver
services, manage budgets and work with donors at a basic level. They are
functioning, but fragile. Increased capacity and recent reforms may not survive
political rivalries and reduced levels of donor support. But in both Provinces we have
Paper Secretary of State [Defence], 14 February 2006, ‘Iraq: Handover of Security in Maysan and
289
al Muthanna Provinces’.
279

---
reached a point where we will achieve diminishing returns if we stay much longer.
The Iraqis are in a position to assume the mantle.”
507. At the meeting, Dr Reid said that the political and developmental issues associated
with the transfer of security responsibility in Muthanna in May had been resolved.
290
508. DOP(I) agreed the approach set out in the paper.
509. Also on 15 February, at the request of the ISOG, the JIC assessed Iraq’s expected
development in 2006.
 The JIC concluded that the new Iraqi Government would be
291
judged largely by its ability to deliver security, fuel, electricity, jobs and a timeline for
MNF withdrawal, but that there would be little progress on the first four issues over the
next 12 months. The main obstacles to progress were:
“The security situation is the greatest immediate obstacle to economic recovery …
“The new government will be no more competent or united than its predecessor, at
least initially. The new Prime Minister … will have to develop policy within a more
complex political landscape … The tendency of new Ministers to replace the top tier
of officials with friends, family or tribal members will add to the difficulties.
“The Iraqi civil service lacks the ability to deliver at all levels … Although there are
talented individuals, institutional capacity was effectively destroyed under Saddam’s
dictatorship and in the aftermath of his overthrow: de-Ba’athification, which removed
many experienced bureaucrats, has been especially damaging … Endemic
corruption is a significant brake on economic development, pervading the highest
levels of government, but also reaching into provincial and local levels.”
510. The JIC concluded that:
The new government would come under international pressure to revitalise
its oil sector and push ahead with economic reforms (including the reduction
of domestic fuel and food subsidies), but would proceed cautiously given the
potential for public discontent.
The fragile state of Iraq’s energy infrastructure and continuing insurgent
and criminal attacks would preclude any early progress on energy supplies.
Electricity production currently met only about 45 percent of demand.
There could be no “international solution” to improving essential services in Iraq.
The Iraqi government needed to adopt a strategy to increase growth and invest
in services and infrastructure. Bilateral and multilateral donors could play a
supporting role, for example by strengthening the budget process and providing
technical advice.
Minutes, 15 February 2006, DOP(I) meeting.
290
JIC Assessment, 15 February 2006, ‘Iraq’s Development: Expectations and Delivery in 2006’.
291
280

---
10.2 | Reconstruction: July 2004 to July 2009
511. On 22 February, the al-Askari mosque in Samarra, the fourth most revered
shrine in Shia Islam and the only major Shia shrine under sole Sunni protection,
was bombed.
292
512. Section 9.4 describes increasing concerns within the UK Government on the level
of sectarian violence in Iraq and the possibility of civil war.
513. On 15 March, at the request of the FCO and MOD, the JIC assessed the security
situation in southern Iraq.
293
514. Key Judgements included:
“I. Levels of violence in southern Iraq are much lower than in Baghdad and Sunni
areas in the centre and north …
…
“III. Across the South, there is no strong administrative machinery to promote
security and stability. Government structures and capacity are fragile. The
lack of central authority has encouraged protracted, and occasionally violent,
local squabbles over power. Multiple sources of authority persist and carry
equal weight …”
DFID’s Portfolio Quality Review, March 2006
DFID undertook an internal review of the performance and “value-for-money” of its
projects in Iraq in March 2006.
294
The review’s main conclusions were:
71 percent of current, large (over £4m) projects in Iraq were “high risk”, compared
with just over 10 percent of DFID projects globally. Most projects were subject to
the same (political and security) risks, so scope to balance risk was limited.
295
Of the 14 current, large projects, nine were likely to completely or largely achieve
their objectives and five were likely to partly achieve their objectives or to achieve
their objectives only to a very limited extent.
44 percent of all DFID projects in Iraq had achieved or were likely to completely
or largely achieve their objectives, compared with 68 percent of DFID projects
globally.
Many projects had benefits beyond their stated objectives, for example in terms
of setting policy agendas, leveraging in other donors’ resources, and “giving DFID
credibility to influence Whitehall”.
Minute Banner to Prime Minister, 23 February 2006, ‘Samarra Shrine Bombing – Background
292
and Update’.
JIC Assessment, 15 March 2006, ‘Iraq: the Security Situation in the South’.
293
Minute Hendrie to PS/Secretary of State [DFID], 27 March 2006, ‘Iraq: Portfolio Quality Review’.
294
Not all the figures used in the text of the Portfolio Quality Review are consistent with the information
295
presented in the supporting graphs and table. Where there is inconsistency, the Inquiry has drawn
information directly from the supporting graphs and table.
281

---
The review identified the strategies that DFID had pursued to improve project
performance:
constant monitoring and management (though that was hampered by insecurity);
using innovative techniques to deliver projects, such as working through local
Iraqi engineers and helping the Ministry of Finance to set up an office inside the
International Zone (within which international consultants could work);
using the fragile states analysis to focus on a few immediate priorities. In Iraq,
DFID had focused on strengthening central Government and getting economic
reform on track;
systematically tracking poor performance;
adapting delivery methods to inside fiduciary risk;
building clear exit strategies into projects, including dedicating significant effort to
leveraging in other donors; and
working closely with Whitehall.
515. Mr Asquith advised the 7 April meeting of the ISG that following rocket attacks
on Basra Palace on 4 April, and given the continuing non-co-operation by the local
authorities in Basra with UK officials following the Jameat incident, some UK civilian
staff were unable to operate.
 The FCO and DFID planned to recommend to their
296
Ministers a drawdown of civilian staff from Basra Palace until conditions on the
ground had improved.
516. Mr Benn was briefed on 19 April that significant numbers of Shia were moving
south and Sunnis moving north.
 MND(SE) was providing some (unspecified)
297
short-term support to Internally Displaced People (IDPs).
517. Mr Benn was also briefed that running costs for the Basra PRT continued to be
a “major sticking point”. No government department (or other country) had a budget
for this. The Post-Conflict Reconstruction Unit (PCRU) was “holding the fort”, and
departments were exploring whether they might be able to continue leading in the
longer term.
518. Late on 21 April, four months after the December 2005 elections, the United Iraqi
Alliance announced the selection of Mr Nuri al-Maliki as its candidate for Prime Minister
(see Section 9.4).
298
519. The British Embassy Baghdad reported on 22 April that the new Government
had produced a “100-day plan”, focusing on urgent measures to improve security, oil,
electricity, employment, agriculture and housing.
299
Letter Cabinet Office [junior official] to Sheinwald, 10 April 2006, ‘Iraq Strategy Group: 7 April 2006’.
296
Minute DFID [junior official] to PS [DFID], 19 April 2006, ‘DOP(I) Briefing 19 April 2006’.
297
eGram 13011/06 Baghdad to FCO London, 24 April 2006, ‘Iraq: Formation of the New Government:
298
Al-Maliki Nominated by UIA as Prime Minister’.
eGram 13036/06 Baghdad to FCO London, 22 April 2006, ‘Iraq: Preparations for Government’.
299
282

---
10.2 | Reconstruction: July 2004 to July 2009
520. The Embassy commented that on both security and electricity, the plan adopted
a “Baghdad-first” approach (Baghdad had a third of the country’s population and was
suffering more than other areas).
521. The Embassy reported that the Iraqi Government had discussed the 100-day plan
with the British and US Embassies. As a result of those discussions, the Minister of
Planning had agreed:
a UK recommendation to include Iraqi signature to the Extractive Industries
Transparency Initiative (EITI) in the plan; and
to “play up” the monetarisation of the food subsidy, bank restructuring and civil
service reform as priorities for the new Government.
522. Sir Nigel Sheinwald met Mr Maliki in Baghdad on 24 April.
 Mr Maliki said that his
300
priorities were security, the economy and services. There would have to be the toughest
possible penalties for corruption.
523. Sir Nigel said that the UK’s ability to help with reconstruction in Basra was
hampered by the security situation. Mr Maliki said that he knew little of the detail of the
situation in Basra, but had heard that the population felt the UK had achieved very little
for them, even before security deteriorated. He advocated patience, waiting for local
elections that might bring change, and doing what the UK could to improve the economy.
Employment would reduce the security threat.
524. Sir Nigel’s report of his visit to Mr Blair focused on government formation (see
Section 9.4).
 Sir Nigel confirmed that, as Mr Blair had suggested, the UK and US
301
had offered to help Mr Maliki establish his Government. The UK’s main contributions
would be:
two officials (one FCO, one DFID) in the British Embassy working on the
substance of the Iraqi Government’s programme;
one official to advise the British Ambassador and the Iraqi Government on media
and political strategy;
No.10, FCO and MOD press officers to help with communications in key
ministries;
three Adam Smith Institute Ltd consultants to advise on the structure and
operation of the Prime Minister’s Office and other key institutions; and
a substantial MOD advisory team for the new Defence Minister.
525. Mr Blair commented: “[W]e must make sure this team is strong enough.”
302
Telegram 13126/06 Baghdad to FCO London, 24 April 2006, ‘Iraq: Government Formation:
300
Maliki’s Views’.
Minute Sheinwald to Prime Minister, 27 April 2006, ‘Visit to Iraq’.
301
Manuscript comment Blair to Sheinwald on Minute Sheinwald to Prime Minister, 27 April 2006,
302
‘Visit to Iraq’.
283

---
526. Mr Blair spoke to Mr Maliki on 28 April, to congratulate him and assure him of the
UK’s support.
 Mr Blair said that it was important that Mr Maliki had good, capable
303
people around him, and that the UK stood ready to offer advice and assistance, on both
policy and communications.
527. The Cabinet Office circulated a draft FCO paper on Basra, which had been
produced for DOP(I), to members of the ISOG on 28 April.
 The draft FCO paper
304
stated that:
“Security and governance in Basra are bad and worsening. Attacks on us, and both
criminal and sectarian violence, are rising. Basic services are not being delivered.
Basra is one of the four provinces in Iraq judged by MNF(I) to be furthest away from
transition to full Iraqi control.
“The UK civilian effort in Basra is increasingly hunkered down. We face a lack of
co-operation from the local authorities and severe restrictions on our movement.
Our local staff … suffer growing intimidation. Against this background, much of our
effort – notably the Provincial Reconstruction Team we are standing up in May –
can make little headway.”
528. The FCO paper was not submitted to DOP(I), but did inform discussions on 22 May
between senior officials on how to achieve UK objectives in Basra.
529. Mr Blair held a Cabinet reshuffle in early May 2006. Mr Benn remained
Development Secretary; Mr Des Browne replaced Dr Reid as Defence Secretary; and
Mrs Margaret Beckett replaced Mr Straw as Foreign Secretary.
530. Mr Mark Lowcock, DFID Director General Policy and Programmes, and
Mr Anderson visited Baghdad from 2 to 5 May.
 They reported to Mr Chakrabarti that
305
the new Iraqi Government faced a daunting economic reform agenda. The 100-day plan
contained some of the necessary reforms, but it seemed unlikely that it would garner
wider political support given the fragile political deals underpinning the new Government.
531. Iraq had enjoyed a “massive windfall” from the rising oil price, possibly an
additional US$20bn a year. That dwarfed the amount of aid provided to Iraq. While some
of that windfall had been used to increase the budget:
“… billions – some people say tens of billions – has been lost through large-scale
corruption and other leakage. Who has got the money and what do they plan to do
with it? And how is the Government going to regain control?”
532. Mr Lowcock and Mr Anderson confirmed that DFID should “continue to move
towards more capacity building and … internationalising the effort in Iraq”.
Letter Banner to Siddiq, 28 April 2006, ‘Nouri al-Maliki’.
303
Paper FCO [draft], 27 April 2006, ‘DOP(I): Basra’.
304
Minute Lowcock and Anderson to Chakrabarti, 5 May 2006, ‘Visit to Baghdad 2-5 May’.
305
284

---
10.2 | Reconstruction: July 2004 to July 2009
533. They also stated that the “refocusing” of the US effort from infrastructure to
capacity-building might have (unspecified) implications for DFID.
534. The British Embassy Baghdad reported the following week that, according to a
report issued by the Iraqi Oil Inspector General, some US$4.2bn worth of oil products
had been smuggled out of Iraq in the previous year.
306
Turning Basra around
535. The Basra PRT was established on 14 May 2006, and was expected to be fully
operational within three weeks.
 Its first Head was Mr Mark Etherington (a consultant
307
contracted by PCRU).
536. PCRU funded three new posts in the Basra PRT (its Head, a Communications
Manager and an Office Manager).
 It was otherwise staffed by bringing together the
308
existing US, UK and Danish teams.
309
537. Mr Etherington wrote to a Cabinet Office official on 17 May outlining the challenges
facing the Basra PRT, the most significant of which was a lack of “operational
coherence”:
“Military and civilian lines of activity are not integrated, and the separation between
military headquarters … and the Consulate in Basra Palace [the British Embassy
Office Basra] has made the formulation and execution of sophisticated unitary
approaches … very difficult. Our outputs are hence fragmentary, prone to duplication
and intrinsically wasteful of resources; and neither are they subsumed to an
over-arching strategy.
“This is because no over-arching, integrated strategy has yet been articulated,
although the need for one has been identified … UK ‘policy’ in S[outhern] Iraq is
hence little more than an aggregation of departmental approaches …”
310
538. While the PRT’s work “must focus overwhelmingly upon Basra”, it should have a
“low-key southern Iraq co-ordination role”.
539. Mr Etherington advised that “reporting was fragmented and lines of authority
divided”. He therefore intended to establish a “Basra Steering Group”, bringing together
MND(SE), the British Embassy Office Basra and the PRT. Its aim would be to “create a
eGram Baghdad to FCO London , 9 May 2006, ‘Iraq: Corruption – Inspector General’s Report’.
306
Minute Etherington to Cabinet Office [junior official], 17 May 2006, ‘Basra PRT: Challenges and
307
Opportunities’.
Minute Teuten to PCRU [junior official], 31 July 2006, ‘Visit to Baghdad and Basra, 19 – 25 July’; Minute
308
Etherington to Cabinet Office [junior official], 17 May 2006, ‘Basra PRT: Challenges and Opportunities’.
Minute DFID [junior officials] to Mr Anderson, 31 July 2006, ‘Iraq: Allocation of Governance Resources
309
to PRT in southern Iraq’.
Minute Etherington to Cabinet Office [junior official], 17 May 2006, ‘Basra PRT: Challenges and
310
Opportunities’.
285

---
comprehensive strategy across all lines of activity, to prosecute it in detail and to review
it monthly”.
540. Mr Etherington highlighted the need adequately to fund PRT running and
programme costs. The PRT had been allocated £350,000 for “start-up” costs; a request
for additional funding had been sent to PCRU. Mr Etherington estimated that the cost of
running the PRT (including the cost of the three consultants provided by PCRU) would
be US$1.74m per year. The US had allocated US$15m to each PRT for programme
costs but those funds were unlikely to appear before the summer and would in any
case be insufficient for a province of Basra’s size and challenges. In the meantime,
the PRT might be able to access US CERPs funding and some £190,000 from DFID’s
Governorate Capacity Building Project.
541. Gen Jackson visited Iraq from 15 to 18 May.
 He reported to Air Chief Marshal
311
Sir Jock Stirrup, Chief of the Defence Staff, that there appeared to be some confusion
about the role of the Basra PRT. Mr Etherington believed that its role was to deliver
the “coherent UK cross-government approach” in the South that was currently lacking.
Others believed that the PRT should limit itself to reconstruction. Gen Jackson
commented:
“I sense that we, the UK, have not really thought what we want our PRT to achieve.
If we have, it is not clear in theatre.”
542. Gen Jackson reported that his meetings in Basra had caused him to “reflect
once again on the extent to which our military progress in Iraq is mortgaged against
the economic and political LOO [line of operation]”. The constraints imposed on
the economic line of operation by the UK’s International Development Act were an
“enduring concern”:
“To be involved in two campaigns simultaneously [Iraq and Afghanistan] where one
of our three levers of national power is not sufficiently agile or flexible to deliver
immediate campaign effort seems absurd.”
543. Prime Minister Maliki appointed his Cabinet (minus the Ministers for Interior,
Security and Defence) on 20 May. The remaining Ministers were appointed on 8 June.
Sections 9.4 and 9.5 describe the formation of Prime Minister Maliki’s Government.
544. The 22 May meeting of the ISOG discussed how to draw together a strategic plan
to deliver the UK’s objectives in Basra, in the light of the “serious problems” that the
UK faced.
312
Minute Jackson to CDS, 22 May 2006, ‘CGS Visit to Iraq: 15-18 May 06’.
311
Letter Aldred to Lamb, Cooper & Kavanaugh, 23 May 2006, ‘Basra: The Way Forward’ attaching Paper,
312
[undated], ‘Getting Basra Better: A Strategic Agenda for Action’.
286

---
10.2 | Reconstruction: July 2004 to July 2009
545. Ms Aldred sent a “strategic agenda for action” to UK military officers and officials
working in Basra the following day, seeking advice which:
“
… looks innovatively and ambitiously at options to deliver our strategic
objectives, including potential resources implications; and
clearly indicates … a critical path to success”.
546. Mr Blair met President Talabani and, separately, Prime Minister Maliki in Iraq on
22 May.
 Both men asked Mr Blair whether media reports that the UK was looking to
313
withdraw from Iraq were accurate.
547. Mr Blair’s Private Secretary recorded that Prime Minister Maliki had highlighted the
contribution that “economic reform and prosperity” could make to tackling terrorism and
insecurity.
 Terrorists were exploiting the lack of basic services to create dissatisfaction.
314
Prime Minister Maliki hoped the international community, including Iraq’s neighbours,
would help achieve rapid progress in this area and asked for Mr Blair’s help to mobilise
international support. Mr Blair said that he would be happy to do this.
548. Mr Blair proposed, and Prime Minister Maliki agreed, that one element to
mobilising international support would be to show results in one or two key areas, such
as security and electricity supplies in Baghdad. Prime Minister Maliki said that he was
working with MNF-I and ISF to develop a Baghdad security plan, which would allow an
increase in electricity supply.
549. A joint statement issued by the two Prime Ministers at a press conference after
their meeting stated that they had “discussed the situation in Basra and agreed to work
closely on ensuring greater security and stability there”. A high level Iraqi delegation
would visit Basra soon.
550. The day after Mr Blair left Iraq, Sir Nigel Sheinwald wrote to Mr Straw’s Principal
Private Secretary to set out Mr Blair’s view of priorities for Iraq.
 The key elements
315
were:
“
Drawing up a timetable with conditions setting out the potential path to
MNF withdrawal …
To ensure improved ISF build-up …
Backing the Baghdad security and electricity plans. As the PM [Mr Blair] set
out to Maliki, the new Iraqi Government will need to show early progress on
these priority issues …
Letter Banner to Siddiq, 22 May 2006, ‘Iraq: Prime Minister’s Meeting with Talabani’; Letter Banner to
313
Siddiq, 22 May 2006, ‘Iraq: Prime Minister’s Meeting with Nouri al-Maliki’.
Letter Banner to Siddiq, 22 May 2006, ‘Iraq: Prime Minister’s Meeting with Nouri al-Maliki’ attaching
314
Paper, [undated], ‘Joint Statement about the Visit of the UK Prime Minister’.
Letter Sheinwald to Hayes, 23 May 2006, ‘Iraq’.
315
287

---
Turning around the situation in Basra, following the Prime Minister’s private
conversation with Maliki. This will require
a political understanding with parties representing the spectrum of political
{
{
opinion there;
a package of UK and international reconstruction assistance;
{
{
a larger role and presence for the Iraqi forces, working alongside UK
{
{
forces …
Promoting international support for the new Government …
Ensuring that Arab countries respond positively to requests for assistance from
the new Iraqi Government …
Stepping up our outreach activities to both Sunni and Shia militants … to
ensure that they are given opportunity and incentives to participate in the
political process …
Capacity building for Iraqi ministries. We need a paper setting out our and the
US’s current assistance … and a plan for addressing the gaps.”
551. Sir Nigel’s letter alerted members of DOP(I) that Mr Blair was likely to want to
discuss these issues the next time they met.
552. Mr Dinham told the Inquiry that Mr Blair’s visit took place at a point when
security was deteriorating and “there wasn’t an awful lot that was strongly visible” on
reconstruction.
 Work to build the capacity of the Iraqi Government was progressing
316
but was “below the radar” and DFID’s infrastructure and essential services projects had
taken some time to “get off the ground”:
“So I think what he [Mr Blair] wanted was – I think what we all wanted – was to have
some visible effect.”
553. DOP(I) met on 25 May.
 Mr Blair told the meeting that the UK should focus on:
317
the development of the ISF;
seeing progress in Basra; and
supporting the Iraqi Government’s efforts to restore security and electricity
provision in Baghdad.
554. Minsters commented that:
DFID was seconding two officials to Deputy Prime Minister Salih’s office, to help
with planning and preparation for a donor conference in September.
The key to further progress on electricity production lay in co-operation between
Iraqi ministries and the development of realistic plans, rather than donor funding.
Public hearing, 17 December 2010, pages 65-66.
316
Minutes, 25 May 2006, DOP(I) meeting.
317
288

---
10.2 | Reconstruction: July 2004 to July 2009
Mr Benn had spoken to Mr Paul Wolfowitz, the President of the World Bank, the
previous day and there was now agreement that the World Bank would open
a permanent office in Baghdad. Mr Benn had pressed Mr Wolfowitz to provide
assistance to the energy sector.
555. DOP(I) agreed that the action points set out in Sir Nigel Sheinwald’s letter of
23 May should be pursued.
556. A Cabinet Office official chaired a meeting to discuss Mr Etherington’s letter of
17 May on 25 May.
 The meeting:
318
agreed the “light-touch regional role for the PRT” proposed by Mr Etherington;
endorsed the proposal to create a Steering Group “to discuss strategic issues”.
The scope of the Steering Group would be informed by “wider work under way
on Basra”;
on running costs, agreed that “in principle, [the] FCO could look to fund security
and life support costs … and that PCRU could fund staff costs”;
on programme funding, asked departments to provide details of their current and
proposed programmes to the PRT; and
discussed but did not reach a conclusion on to whom the PRT should report in
Iraq and in London.
557. Prime Minister Maliki and Vice President Tariq Hashemi visited Basra on 31 May.
319
During his visit, Prime Minister Maliki declared a state of emergency in Basra, lasting
one month.
320
558. Mr Patey reported on 2 June that the new Iraqi Minister of Electricity, Dr Karim
Wahid, had asked for UK assistance in funding two power projects in the South, at a
combined cost of US$60m.
321
559. Mr Blair held a private meeting with Mr Browne on 6 June.
 He asked Mr Browne
322
to focus on the situation in Basra, and to:
“… make sure that the political and military strategies were aligned and proceeding
together. This required micro-management. We had been slow to grip the situation
there …”
560. In mid-June, Prime Minister Maliki formally launched the Baghdad Security Plan
(see Section 9.5).
Minute Cabinet Office [junior official] to Aldred, 25 May 2006, ‘Ad Hoc Discussion on PRTs’.
318
Minute Cooper, 1 June 2006, ‘MND(SE) – southern Iraq Update – 1 June 2006’.
319
The Guardian, 31 May 2006, State of emergency for Basra.
320
eGram 21675/06 Baghdad to FCO London, 2 June 2006, ‘Iraq: Meeting with Minister of Electricity’.
321
Minute Sheinwald to Banner, 8 June 2006, ‘Iraq and Afghanistan’.
322
289

---
561. The Cabinet Office produced an update on work on the “review of policy”
requested by Mr Blair following his 22 May visit, “including in response to serious
concerns over the situation in Basra”, for the 15 June meeting of DOP(I).
323
562. On electricity, the Cabinet Office paper stated that following positive early meetings
with the new Electricity Minister, DFID was focusing on “demand issues and planning” by:
getting the World Bank and other donors including the EU and Japan engaged.
DFID was funding a World Bank adviser on energy sector management, and
part-funding the new World Bank Country Office;
leveraging World Bank loans for power projects in response to specific requests
from the Electricity Minister; and
offering a consultant to the Ministry of Electricity to advise on an electricity plan.
563. On international support, US and UK officials were discussing options for a
compact between Iraq and the international community.
564. The UK’s role in the development of the International Compact is described later
in this Section.
565. On capacity building, the UK was supporting a number of key Iraqi institutions but
that effort was “dwarfed by a very large … often overambitious US programme”.
The US had offered to share work it was undertaking to map and improve its
capacity-building effort. That would provide a basis for discussions on a complementary
approach.
566. On Basra, officials had been undertaking a “major review of policy” in MND(SE),
in response to concerns (shared by the US) that Basra was not on track to meet the
proposed transition timelines. The “work plan for Basra” had been organised around
four strands: political framework; security; Rule of Law and governance; and economic
development and reconstruction.
567. On the economic development and reconstruction strand, departments had been
reviewing their programmes to ensure that:
key short-term requirements were met;
plans were in place for the Iraqi Government and the wider donor community
to tackle Basra’s medium- and long-term requirements; and
all projects were delivering a visible dividend to Baswaris.
568. Funding had been found from existing resources for a number of new initiatives,
but departments were still scoping the cost of further short-term measures. An initial
estimate was that an additional £85m might be required.
Paper Cabinet Office, 13 June 2006, ‘Follow-up to the Prime Minister’s Visit, Including Delivering
323
a Step-Change in Basra’.
290

---
10.2 | Reconstruction: July 2004 to July 2009
569. DOP(I) agreed that Mr Browne should take the lead in pulling together a
strategy for Basra, with the support of the Cabinet Office and assistance from other
departments.
 Mr Benn would monitor developments on electricity and power supply.
324
570. Prime Minister Maliki announced on 18 June that Muthanna would transfer to
Provincial Iraqi Control (PIC) on 13 July.
325
571. Mr Browne visited Iraq from 18 to 22 June.
 He wrote to Mr Blair while in transit
326
between Baghdad and Basra:
“There is a tension between, on the one hand, our growing conviction that
reconstruction and better governance must be delivered alongside improved
security, rather than coming a few months down the track, and on the other, the
difficulties our FCO and DFID representatives face in getting out on to the ground
to do this.”
572. The British Embassy Washington reported on 30 June that senior US officials
had confirmed that in response to UK lobbying, the Basra PRT was likely to receive
more than the US$15m allocated to other PRTs.
 The US Embassy Baghdad was
327
considering the exact amount.
573. The US provided US$30m for the Basra PRT in 2007.
 The amounts allocated to
328
other PRTs for that period varied from US$80m (for Baghdad) to US$18m.
574. Mr Browne sent Mr Blair an update on Basra on 4 July.
 Mr Browne advised that
329
he would be asking DOP(I) to agree a number of new projects which would be required
to support the “‘Better Basra Action Plan”, at a total cost of £30.7m for the remainder
of the financial year. That was “a relatively small sum given the strategic importance of
Basra”. The total comprised:
£14.3m for additional UK support for the police (see Section 12.1);
£11.4m for additional UK support for the judiciary, prisons and witness protection
(see Section 12.1); and
£5m for a Rapid Response Fund for the southern Iraq Steering Group, to
support good governance and other priority areas.
Minutes, 15 June 2006, DOP(I) meeting.
324
Minutes, 6 July 2006, DOP(I) meeting.
325
Letter Browne to Blair, 22 June 2006, ‘Update on Visit to Iraq’.
326
eGram 28036/06 Baghdad to FCO London, 30 June 2006, ‘US-Iraq: Basra’.
327
Email Cabinet Office [junior official] to Hendrie, 18 February 2008, ‘US Economic Surge Information’
328
attaching Paper, [undated], ‘Snapshot of PRT Engagement in Iraq’.
Letter Browne to Blair, 4 July 2006, [untitled], attaching Paper, [undated], ‘Background on Additional
329
Basra Work’.
291

---
575. Mr Browne also advised that in response to Mr Blair’s visit to Iraq in late May:
“… the southern Iraq Steering Group has been set up, chaired by [the] Consul
General with participation from across departments and agencies to co-ordinate
delivery of a coherent strategy for southern Iraq, focused on Basra. Much of the
work on governance, rule of law and infrastructure will now be delivered in a
coherent fashion through the new UK-led Provincial Reconstruction Team in Basra,
drawing together inputs from the US, Danes and other international partners.”
576. The Basra PRT was now fully staffed, but lacked funding for project work
and would need funding for running costs from December 2006. US funds had not
yet arrived.
577. The 6 July meeting of DOP(I) discussed Mr Browne’s letter to Mr Blair and agreed
his proposals in principle.
330
578. Mrs Beckett and Mr Benn said that their budgets for Iraq were fully committed,
but were asked to look again at reprioritising their spending to fund the Better Basra
projects.
579. Ministers agreed that there was a need for a comprehensive communications plan
to highlight UK activity on reconstruction to politicians in Baghdad and Basra. The plan
should include other donors’ activity, to give a clear picture of the totality of development
assistance that the UK presence was bringing to southern Iraq.
580. Ministers also recognised the risk to locally engaged staff, who were being
targeted. At least three locally engaged members of staff working for the Coalition had
been killed. FCO and DFID locally engaged staff were being offered the chance to
resign, work at home, or work at a different location.
581. Discussions on funding the Better Basra Action Plan continued into August.
582. A Treasury official advised Mr Stephen Timms, Chief Secretary to the Treasury,
on 15 August that departments had agreed to provide a total of £20.4m from existing
resources to fund the Better Basra Action Plan, now costed at £26.5m (due to the later
start for some of the work).
 The FCO had contributed £12.4m (of which £7m was from
331
the GCPP Reserve), the MOD £4m and DFID £4m. Negotiations had been difficult, with
the MOD offering “considerable resistance” to the need to find its contribution from the
core defence budget.
583. Mr Timms wrote to Mr Browne the same day, welcoming the successful conclusion
of negotiations and agreeing to provide an additional £4m for the Plan from the central
Reserve.
332
Minutes, 6 July 2006, DOP(I) meeting.
330
Minute Treasury [junior official] to Chief Secretary, 15 August 2006, ‘Better Basra Plan’.
331
Letter Timms to Browne, 15 August 2006, ‘Better Basra’.
332
292

---
10.2 | Reconstruction: July 2004 to July 2009
584. Mr Dinham told the Inquiry that the Better Basra Action Plan was a “proper, agreed,
bought-into, cross-Whitehall plan”, which had led to greater unity of purpose across the
UK effort.
 He added that the Plan did not seek to reflect the totality of the UK effort; for
333
example, major DFID projects to increase power supply were starting to come on stream
and contributed to achieving the UK’s objectives.
585. Mr Etherington told the Inquiry that the Better Basra Action Plan was “a set of
aspirations” rather than a plan.
334
586. Mrs Beckett told Cabinet on 13 July that responsibility for security in Muthanna
had been handed from British to Iraqi forces earlier that day.
335
587. On 19 July, the JIC judged that violence was at the highest sustained level since
April 2003, outpacing the Iraqi Government’s ability to respond.
 “Spiralling sectarian
336
violence” was the most immediate threat to Iraq’s progress.
588. Mr Patey’s valedictory report from Baghdad on 20 July opened with the warning:
“Strategic failure in Iraq a distinct possibility but not inevitable.”
337
589. Mr Patey advised that:
“Without progress on security the encouraging start made by DPM [Deputy Prime
Minister] Barham Salih and his economic team will be stillborn. The exodus of
businessmen and the Iraqi middle class continues due to security concerns. They
will take some persuading to return a second time but their entrepreneurial skills
will be vital if the country is to thrive.”
590. Mr Patey’s valedictory report was passed to Mr Blair on 21 July.
338
591. The ISG reflected on reporting from Baghdad, and its implications for the existing
strategy, on 27 July.
 The ISG agreed that although success or failure in Baghdad
339
would be critical to overall campaign success in Iraq and was therefore the coalition’s
highest priority, the “best way for the UK to contribute to the wider military campaign was
to continue to focus our limited resources on MND(SE), in particular, on Basra”.
592. At the meeting, Mr Dinham argued that the UK should focus its future support on
central government and in particular on budgetary management and critical economic
reforms. Iraq was now enjoying increased revenue as a result of higher oil prices and
slowly rising exports; the challenge was to ensure those revenues were redirected from
wasteful and damaging subsidies to investment in public services. The security situation
Public hearing, 17 December 2009, page 67.
333
Public hearing, 9 July 2010, page 26.
334
Cabinet Minutes, 13 July 2006.
335
JIC Assessment, 19 July 2006, ‘Iraq: Insurgency, Sectarianism and Violence’.
336
eGram 31514/06 Baghdad to FCO London, 20 July 2006, ‘Iraq: Valedictory’.
337
Minute Banner to Prime Minister, 21 July 2006, ‘Iraq: Update and Maliki Meeting’.
338
Minute Cabinet Office [junior official] to Sheinwald, 27 July 2006, ‘Iraq Strategy Group, 27 July’.’
339
293

---
meant that undertaking major new infrastructure projects had become impossible. The
ISG agreed that this was:
“… an entirely sound approach, but noted the large gap between what we planned
to offer and Iraqi expectations. This would need careful management.”
593. Dr Rosalind Marsden, the newly arrived Consul General in Basra, reported on
24 August that her first impression of the Basra political scene was of “stasis”.
 The
340
Provincial Government had yet to show itself capable of responding to Basra’s major
security and economic challenges. Local leaders were comfortable blaming each other
and the coalition for the lack of progress, while pursuing their “criminal interests”. The
Better Basra Plan had “most of the ingredients” to break the log-jam, but the UK’s
influence was diminishing.
594. Section 9.5 describes the development in August and September of Operation
SALAMANCA, the operation to implement the military elements of the Iraqi
Government’s Basra Security Plan.
595. Major General Richard Shirreff, who took over as GOC MND(SE) in mid-July,
341
told the Inquiry that Op SALAMANCA comprised three major elements:
“… what we did was select different areas of the city, and … surging with
concentration of force, secure the area, put teams into the police stations to go
through the police stations with a fine-toothed comb, to establish the state of
police stations …
“We surged police training teams in, Royal Military Police and contract policemen
from elsewhere. At the same time we conducted a number of pre-planned
reconstruction and other projects, everything from levelling football pitches to
playgrounds, to refurbishing schools.”
342
596. Mr Martin Howard, MOD Director General Operational Policy, told the 25 August
ISOG meeting that Mr Browne would want to be reassured that “arrangements
for delivering civilian activities” were in place and robust before approving
Op SALAMANCA.
343
597. The British Embassy Office Basra issued a detailed brief on Op SALAMANCA
(which it described as “the security pillar of Better Basra”) by eGram on 12 September.
344
The brief identified the importance of exploiting the conditions created by
Op SALAMANCA. Short-term projects under Op SALAMANCA should be linked to
longer-term initiatives. Funding (primarily Iraqi funding) was available, “most of the right
eGram 36964/06 Basra to FCO London, 24 August 2006, ‘Iraq: Basra: Political Overview’.
340
Report Cooper, 13 July 2006, ‘GOC MND(SE) – southern Iraq Update – 13 July 2006.
341
Public hearing, 11 January 2010, pages 19-20.
342
Minute Blake to Banner, 25 August 2006, ‘Iraq Senior Officials Group’.
343
eGram 42792/06, Basra to FCO London, 12 September 2006, ‘Iraq: Basra: Operation
344
Salamanca/Date Palm’.
294

---
10.2 | Reconstruction: July 2004 to July 2009
people” were in place (the PRT had “marshalled an impressive array of UK and partners’
talent”), and teams in Basra were working together “more closely than ever” through the
southern Iraq Steering Group.
598. The transition to PIC in Dhi Qar province took place on 21 September.
345
599. Maj Gen Shirreff reported on 28 September that Operation SINBAD (the new name
for Op SALAMANCA) had at last begun, after a “tortuous” round of final negotiations
with Iraqi politicians.
346
600. On 5 October, at the request of the FCO, the JIC assessed the performance of the
Iraqi Government, its level of popular support and its prospects over the year ahead.
347
The JIC judged that after five months in office:
“… the faction-based Iraqi Government is proving ineffective … Co-ordination
between and within Government ministries is poor. None of this looks likely to
improve in the near future. Meanwhile, sectarian and insurgent violence is at
a record high, and fuel, water and electricity shortages persist across much
of the country.”
601. The 12 October meeting of DOP(I) received a paper by officials on the
medium-term prospects for Iraq.
348
602. A DFID official advised Mr Benn in advance of the meeting that the paper had
been “inspired by” Mr Patey’s valedictory telegram (which had assessed that strategic
failure in Iraq was a distinct possibility but not inevitable), and was set in the context of
increasing insecurity.
349
603. The official advised Mr Benn that discussions around the paper provided a good
opportunity for DFID to reassure departments – especially the MOD – that it was
“shouldering our share of the burden” in Iraq. DFID’s two current projects in the South,
the IISP and the Governorate Capacity Building Project, were due to finish in March
2007, when DFID would aim to close its office in Basra. Deteriorating security meant no
new projects could be designed or implemented. There was “little/no expectation” from
the MOD or FCO that DFID would continue to invest in infrastructure, given the flow of
US CERPs money and anticipated investments by Japan, the World Bank and the Iraqi
Government itself. The official concluded:
“We have largely won the argument that DFID should shift focus from physical
investments in Basra to technical assistance in Baghdad to maximise our impact,
and the [medium-term] paper reflects this in its recommendations.”
Report Shirreff, 21 September 2006, ‘GOC MND(SE) – southern Iraq Update – 21 September 2006’.
345
Report Shirreff, 28 September 2006, ‘GOC MND(SE) – southern Iraq Update – 28 September 2006’.
346
JIC Assessment, 5 October 2006, ‘Al-Maliki’s Government: Interim Progress Report’.
347
Paper, 10 October 2006, ‘Iraq: Medium Term Prospects and Implications’.
348
Minute DFID [junior official] to Private Secretary [DFID], 6 October 2006, ‘Iraq: Future for DFID
349
Programme from 2007’.
295

---
604. The medium-term prospects paper assessed that Iraq had reached a critical
juncture, with violence at its highest ever level, reconciliation making little headway and
public services still in a parlous state.
 The UK’s existing goal for Iraq was:
350
“A democratic, stable, united and law-abiding Iraq … providing effective,
representative and inclusive government for all its people.”
That was now likely to be the “best case outcome”, and unlikely to be achievable in full.
The best achievable outcome was likely to be:
“… an Iraq which can govern and sustain itself nationally and provincially, and
where sectarian and other violence is contained short of the point where it would
overwhelm Iraq’s institutions and precipitate chaos and/or civil war.”
Achieving that outcome lay primarily in the hands of the Iraqi Government. The UK’s
ability to influence its decisions would continue to decline. The coalition’s current
strategy of direct support combined with building Iraqi capacity remained the only
credible way to exert influence.
605. The paper argued that Iraq’s economic success depended more on the policies
and actions of the Iraqi Government than on the backing of the international community.
High oil prices had bolstered Iraq’s finances, but the Iraqi Government needed
assistance in managing the economy, bringing about structural reforms, and unblocking
domestic investment to improve public services. The implications for the UK were:
The UK’s effort in Basra should be channelled as far as possible through the
PRT, which might need to continue work into 2008 in line with the planned UK
military effort.
DFID’s programme should increasingly be directed at enabling the Iraqi
Government to tackle key challenges at the centre, including reconciliation,
economic management and critical capacity deficits.
606. The DOP(I) meeting touched only very briefly on the paper, as Mr Browne
indicated he would like more time to discuss and agree it formally at a later date.
351
607. DOP(I) discussed the medium-term prospects paper at their next meeting, on
20 October.
 Mr Blair was not present, so Mr Browne chaired the meeting.
352
608. Mr Browne began by saying that the existing goal would be difficult to achieve, but
Ministers had to be certain that there was not more the UK could do before accepting
anything less.
Paper DOP(I), 10 October 2006, ‘Iraq: Medium Term Prospects and Implications’.
350
Minutes, 12 October 2006, DOP(I) meeting.
351
Minutes (revised), 20 October 2006, DOP(I) meeting.
352
296

---
10.2 | Reconstruction: July 2004 to July 2009
609. Mr Browne also said that DFID’s aspiration to move its focus to Baghdad was
well understood, but the UK had a significant stake in the South and needed a clearer
understanding of the impact of such a move on activity there.
610. In discussion, a member of DOP(I) said that most DFID projects in the South were
likely to be completed by spring 2007 and that no new projects could be started under
current security circumstances. The UK’s medium-term legacy depended on getting
economic management and reconciliation going and Baghdad functioning, which meant
building capacity in central ministries.
611. DOP(I) agreed that the UK should keep the existing policy goal, but recognise that
the best outcome achievable might fall short of it.
612. It also agreed that a progressive reduction of UK forces to 4,500 in 2007, in concert
with US and other allies, was possible, with more ambitious reductions being considered
at the end of November.
613. The medium-term prospects paper was discussed again at the 26 October meeting
of DOP, alongside an update from Mr Browne on security developments in Iraq.
353
614. ACM Stirrup advised that Op SINBAD “could not be going better, although
there had been an increase in the number of indirect fire attacks on the Basra Palace
Compound”. The main concern of Basrawis was whether the success of the operation
could be sustained, which “would require engagement and funds from the Government
in Baghdad”.
615. DOP agreed the analysis and recommendations contained in the medium-term
prospects paper.
616. Section 15.1 describes the increasing threat posed by rocket and mortar fire to
Basra Palace Compound (BPC), and the discussions within the UK Government on how
to respond.
617. At the 27 October meeting of the ISG, Mr Simon McDonald, FCO Director Iraq,
reported that the security situation in Basra had deteriorated to the point where Mrs
Beckett had decided it was necessary to withdraw the majority of civilian staff from the
BPC to Basra Air Station (BAS) or out of theatre.
354
618. The BPC housed the British Embassy Office Basra, the DFID Basra Office,
elements of the police and prisons teams, and the PRT.
 MND(SE) was already located
355
at BAS.
619. The lack of hardened accommodation suitable for civilian staff at BAS meant that
not all staff could be relocated immediately.
Minutes, 26 October 2006, DOP meeting.
353
Minute Cabinet Office [junior official] to Sheinwald, 30 October 2006, ‘Iraq Strategy Group, 27 October’.
354
Paper Iraq Policy Unit, 25 October 2006, ‘Iraq: Basra Palace Site’.
355
297

---
620. The PRT withdrew to Kuwait and redeployed to BAS in mid-December, when
sufficient hardened accommodation had been constructed.
356
621. Mr Blair was advised by his Private Secretary later that day that “this move is likely
to be seen as a victory by those attacking us”.
 Dr Marsden and four FCO civilian staff
357
would remain in the BPC, while other staff would relocate elsewhere (the majority to
the BAS).
622. The US Office of the Special Inspector General for Iraq Reconstruction (SIGIR)
published its audit of PRT capability on 29 October.
 The audit, which had been
358
conducted over the summer, concluded that while the creation of 10 PRTs and eight
satellite offices was a “noteworthy achievement”, many obstacles to effective operation
remained. Those included insecurity, delays in providing funding, the difficulty of
recruiting and retaining qualified civilian personnel, and the difficulty of integrating
civilian and military personnel.
623. On the Basra PRT, SIGIR assessed that the unstable security situation meant that
PRT members had not been able to interact personally with their Iraqi counterparts,
significantly limiting the PRT’s ability to achieve its mission. It questioned “whether the
continued deployment of PRT personnel to … Basra … makes operational sense at
this time”.
624. The Inquiry has seen no indications that the UK Government discussed the
SIGIR audit.
625. The 2 November weekly update from GOC(MND)SE, which was sent by
Maj Gen Shirreff’s Chief of Staff, reported that the withdrawal of civilian personnel had
come as a surprise to MND(SE).
 It was expected to have an adverse impact, including
359
by disrupting long-term reconstruction because of the “haste with which the PRT has
been evacuated”.
626. On 7 November, the British Embassy Baghdad and the British Embassy Office
Basra responded to an IPU request for accounts of what life was like for ordinary Iraqi
citizens. Their replies warned that they could offer only an impressionistic view due to
the constraints under which they operated.
627. The Embassy reported that:
“Our protected circumstances constrain our ability to interact with ordinary Iraqis
or even visit Baghdad. Our impressions can only be gleaned through the press,
or piecemeal, anecdotally and at second or third hand.”
360
Report PCRU/DFID, 19 December 2006, ‘Refocusing Civilian Efforts in Basra in the Run Up to PIC’.
356
Minute Banner to Blair, 27 October 2006, ‘Iraq Update, 27 October’.
357
Office of the Special Inspector General for Iraq Reconstruction, 29 October 2006, Status of the
358
Provincial Reconstruction Team Program in Iraq.
Report Everard, 2 November 2006, ‘GOC MND(SE) – southern Iraq Update – 2 November 2006’.
359
Letter Gibson to IPU [junior official], 7 November 2006, ‘Life in Baghdad for Ordinary Iraqis’.
360
298

---
10.2 | Reconstruction: July 2004 to July 2009
628. The British Embassy Office Basra offered a similar view:
“We cannot go into ordinary Iraqi homes, shops and schools or move freely around
the city (or even our own compound). Nearly all our local staff have left because of
death threats and intimidation.”
361
629. The accounts were passed to Mr Blair on 10 November.
362
630. DOP(I) considered the impact of the withdrawal of civilian personnel on
16 November.
 Mrs Beckett and Sir Suma Chakrabarti reported that the impact of the
363
withdrawal of civilian personnel from the BPC on the Better Basra Action Plan and on
DFID’s programmes had been “marginal”.
631. Mrs Beckett summed up that officials should develop some clear and agreed
forward planning on the future of the civilian and military presence in Basra.
632. A December 2006 joint DFID/PCRU report assessed that the impact of the PRT’s
withdrawal from the BPC to Kuwait on its work was “significant but not catastrophic”.
364
Little of its work required face-to-face contact with Iraqi citizens.
633. The relocation of the PRT from Kuwait to BAS was under way, and the benefits of
co-location with MND(SE) were already apparent. The PRT’s access to military partners
went some way to overcoming problems caused by the lack of a common secure
communication system between civilians and the military. Informal contacts were also
helping to build mutual understanding of objectives and aims.
634. A number of witnesses told the Inquiry that the move to BAS led to much greater
contact between UK civilian personnel and Iraqi citizens. Mr Robert Tinline, Deputy
Consul General in Basra, described BAS as a “neutral venue”:
“Because we were next to the airport, which was Iraqi obviously, but close enough
to our security … that meant they [our Iraqi interlocutors] didn’t have to come and
365
see us and we didn’t have to go and see them. So it was actually very good.”
635. Section 9.5 describes the wider implications of the withdrawal of civilian personnel,
including for US/UK relations.
636. Mr Gordon Brown, the Chancellor of the Exchequer, visited Basra on
18 November.
 During that visit, Maj Gen Shirreff expressed his concern that long-term
366
economic and development work was being prioritised above short-term interventions
that would yield more immediate results. He proposed that the UK should establish a
Letter Marsden to IPU [junior official], 7 November 2006, ‘Iraq: Basra; Life for Ordinary Iraqis’.
361
Minute Banner to Prime Minister, 10 November 2006, ‘Iraq Update: 10 November’.
362
Minutes, 16 November 2006, DOP(I) meeting.
363
Report PCRU/DFID, 19 December 2006, ‘Refocusing Civilian Efforts in Basra in the Run Up to PIC’.
364
Public hearing, 24 June 2010, pages 10-11.
365
Minute Treasury [junior official] to Chancellor, 13 December 2003, ‘Basra Visit: Responding to Major
366
General Shirreff’s Concerns’.
299

---
joint (civilian and military) taskforce, under a single (unspecified) command, to plan such
short-term interventions.
637. Section 9.5 describes the development in October and November of the UK’s
Forward Plan, at Mr Blair’s request.
638. Mr McDonald sent a draft Plan to Mr Blair’s Private Secretary on 24 November.
367
Copies of the draft were sent to Mrs Beckett, Mr Browne and SIS, but not Mr Benn.
639. The draft Plan recognised that:
“The wider context … is the growing reality of Iraqi sovereignty. The Iraqi
Government and political class have their own priorities, which are not the same as
ours. Maliki’s highest priority now is accelerating the pace of security transition.”
640. The draft Plan included proposed actions under three headings:
Political accommodation;
Governance and economic development; and
Security.
641. On governance and economic development, the draft Plan identified the “core
problems” as a lack of political will and leadership and weak capacity across the Iraqi
Government to drive forward a reform agenda and spend its budget. The immediate
objective was to impress upon Prime Minister Maliki and his senior Ministers and
advisers that economic management and reform required sustained attention and
visible leadership, as a strategic and security issue. Prime Minister Maliki also needed
to ensure that provincial governments were properly resourced and held to account,
as part of the process of forging a political settlement.
642. Immediate actions that Prime Minister Maliki might take included:
striking a deal on oil revenue sharing and starting to restructure the oil sector
so it behaved more like a business;
striking a deal on fiscal federalism, and getting Iraqi resources flowing to the
provinces to improve services; and
by early 2007, adopting the International Compact as a key part of the Iraqi
Government’s reform agenda.
643. The UK would also press Prime Minister Maliki to:
establish and chair an “economic Task Force” to give strategic direction
on economic management and reform and hold Ministers and provincial
governments to account;
Minute McDonald to Banner, 24 November 2006, ‘Iraq Forward Plan’ attaching Paper [draft], [undated],
367
‘Iraq: Forward Plan’.
300

---
10.2 | Reconstruction: July 2004 to July 2009
appoint effective technocrats to replace the “most egregiously partisan” and
underperforming ministers;
take personal responsibility for Iraq’s engagement with the International
Compact;
secure agreement on a Hydrocarbons Law;
push for a full and effective multilateral presence in Iraq;
start reforming key ministries; and
get Iraqi resources to the provinces to improve local services and create jobs.
644. The draft Plan stated that that was an ambitious and complex agenda. Progress
on reform had so far been limited and the UK needed to be realistic about chances of
“widespread success” in the next six months, although traction was improving in some
areas as the quality of Ministers and political leadership improved.
645. Responding to Mr McDonald, Mr Blair’s Private Secretary reported that he had
described the Forward Plan as “an excellent piece of work”.
 The Private Secretary
368
asked for the Plan to be finalised and implemented.
646. No.10 sent the White House a copy of the Forward Plan on 25 November,
stressing that it remained “work in progress”.
369
647. Maj Gen Shirreff’s weekly report of 30 November offered an assessment of
progress on Op SINBAD (two months into the Operation).
 He reported that a great
370
deal had been achieved:
Over US$50m had been committed to more than 150 short- and medium-term
projects, creating over 12,000 jobs. The projects had been selected with the
relevant Iraqi authorities; that approach had won public and political consent
at the local, regional and national level.
There had been an improvement in the general security situation and in the
confidence and capability of the ISF. Further action was needed to reduce
indirect fire and tackle corruption in the Iraq Police Service.
648. On reconstruction, Maj Gen Shirreff commented:
“… the area that will underwrite the success of Op SINBAD is reconstruction and
economic development. I have previously mentioned the need to fill the gap between
the immediate impact projects of Op SINBAD and whatever longer-term activity is
undertaken by the PRT as well as the requirement to co-ordinate the efforts of the
MOD, FCO and DFID in southern Iraq better, hence recent efforts to breathe life
back into the comprehensive approach before it is completely moribund.”
Letter Banner to McDonald, 27 November 2006, ‘Iraq: Forward Plan’.
368
Letter Sheinwald to Hadley, 25 November 2006, [untitled], attaching Note Blair, 27 November 2006,
369
‘Iraq Forward Plan’ and Paper, [undated], ‘Iraq: Forward Plan’.
Report Shirreff, 30 November 2006, ‘GOC(MND)SE – southern Iraq Update – 30 November 2006’.
370
301

---
649. Maj Gen Shirreff reported that he had agreed with Dr Marsden and the Head of
the DFID Office in Basra that to address that gap, the PRT needed to be directed to
work more closely with MND(SE), and that it needed clearer direction from London to
ensure it focused on delivering short-term projects rather than on long-term projects to
build Iraqi capacity. Those steps might “obviate the need for a JIATF [Joint Inter-Agency
Task Force] under command MND(SE)”.
650. The report was sent to No.10 on 1 December and passed to Mr Blair the
same day.
371
651. Lt Gen Shirreff told the Inquiry that the US had agreed to provide “significant
amounts” of US funding for the reconstruction component of the operation, of which
he spent US$80m.
372
652. Lt Gen Shirreff also told the Inquiry that while MND(SE) worked with the PRT as
much as it could, the PRT was in “some state of disarray” at that time.
 He had “pretty
373
close links” with Dr Marsden and the British Embassy Office Basra, including through a
forward headquarters in Basra Palace, but effective co-ordination was difficult as long as
MND(SE) and the British Embassy Office Basra were not co-located.
653. Lt Gen Shirreff concluded that the “inter-governmental piece” had failed by the time
of Op SINBAD.
654. In response to the concerns that Maj Gen Shirreff had raised with Mr Brown on
18 November, the Treasury convened a meeting with DFID, FCO and MOD officials
on 7 December to consider whether the UK should prioritise short-term economic
interventions in Basra.
374
655. A Treasury official advised Mr Brown on 13 December that the meeting had
concluded that:
Money was not a “binding constraint” in the South. The “potential pool”
comprised US$176m from the Iraqi Government, US$260m from the US and
US$550m in soft loans from the Japanese. Money was available for short-term
interventions: only £1.1m of the £5m Rapid Reaction Fund (part of DFID’s
SIESP) had so far been spent.
The inability to generate good project ideas was a constraint.
Bringing the southern Iraq Steering Group under a single command would be
possible and could be effective but might prove contentious.
Letter McNeil to Banner, 1 December 2006, ‘Iraq: Update’ attaching Report Shirreff, 30 November 2006,
371
‘GOC(MND)SE – southern Iraq Update – 30 November 2006’; Minute Banner to Prime Minister,
1 December 2006, ‘Iraq Update: 1 December’.
Public hearing, 11 January 2010, page 16.
372
Public hearing, 11 January 2010, pages 20-21.
373
Minute Treasury [junior official] to Chancellor, 13 December 2006, ‘Basra Visit: Responding to Major
374
General Shirreff’s Concerns’.
302

---
10.2 | Reconstruction: July 2004 to July 2009
PCRU officials were visiting Iraq to explore how civil/military co-ordination could
be improved.
656. The official commented:
“… it is important to be realistic about what can be achieved and in what timeframe.
The Armed Forces can interpret ‘short-term’ to be 48 hours but for DFID it means
6 months.”
657. The Inquiry has seen no indications that Mr Brown or Treasury officials replied
to Maj Gen Shirreff.
658. Maj Gen Shirreff raised his concerns with Mr Blair at the end of December.
UK plans for 2007, and the US surge
659. Section 9.5 describes President Bush’s decision in late November to deploy
additional US troops to Iraq to conduct a full-scale counter-insurgency campaign in
Baghdad, the UK’s response to that decision, and US concerns over UK plans to draw
down troops in the South.
660. In preparation for the 7 December meeting of DOP(I), officials prepared a paper on
military plans for southern Iraq in 2007 and a paper on the UK’s objectives and presence
in Basra.
661. The MOD paper on military plans for southern Iraq reported that Op SINBAD
could create the conditions to achieve PIC in Basra as early as March 2007.
 The
375
intention was to “re-posture” UK troops from bases in Basra City to BAS at the end
of Op SINBAD. From there, UK forces would perform a “Military Assistance Mission”.
That would lead to a reduction in troop numbers from 7,100 to 4,500 in May 2007, and
possible further reductions later in the year.
662. The Basra paper, which was produced by the FCO, considered the implications
of that re-posturing and of the continuing security threat to civilian operations.
 The
376
FCO paper recommended aiming for PIC in Basra at some point between March and
June 2007. The civilian effort would be led from BAS as there was no prospect of being
able to return to the BPC. Although this meant a limit on the number of civilian staff
and tougher conditions, there would be “significant advantages in co-location with the
military – making possible a more cohesive approach”.
663. The FCO recommended that the main objectives of the civilian effort during 2007
should be to:
help deliver PIC in Basra;
Paper MOD, 5 December 2006, ‘UK Military Plans for southern Iraq in 2007’.
375
Paper FCO, 1 December 2006, ‘Basra: Objectives and Presence in 2007’.
376
303

---
continue political engagement, SSR, and capacity-building in the provincial
government; and
ensure that Baghdad delivered the resources that Basra needed.
664. At the DOP(I) meeting, Mr Benn advised that the UK’s major development projects
were now reaching completion.
 The arrival of a gas pumping plant in the next few
377
days would significantly increase gas supply and leave a positive legacy. Although the
water towers projects had been delayed by security risks, DFID planned to move its
focus to capacity-building. The main challenge now would be ensuring the Provincial
Council received the necessary funds from Baghdad.
665. Mr Benn also said “a silent crisis” was unfolding in Iraq, as Iraqi citizens fled from
sectarian violence. That was putting increasing pressure on Iraqi services. DFID had
provided £1.4m to the International Committee of the Red Cross (ICRC).
666. DOP(I) agreed the overall intent of the MOD and FCO papers.
667. Mr Blair wrote to President Bush on 20 December.
 He emphasised the
378
importance of support for Prime Minister Maliki, through increasing the speed at which
the Iraqi Army was developing, supporting the reconciliation and outreach work, and
helping to create a more effective system for the disbursement of money within Iraq.
668. On 5 January 2007, President Bush briefed Mr Blair ahead of his speech on Iraq
the following week.
 During the call he described a significant increase in US and Iraqi
379
troops, and a number of personnel changes.
669. Mr Blair said that it was vital to break the back of the violence in Baghdad. He
urged President Bush to focus on reconciliation and reconstruction as well as security,
suggesting that it might be helpful to designate individuals who would be accountable for
leading work on those areas.
670. Mr Blair’s Private Secretary wrote to Mrs Beckett’s Private Secretary on 8 January:
“We are entering an important new phase in the Coalition effort in Iraq, as –
following the US review and in the light of our plans in Basra – we and the US
attempt to help the Iraqi Government entrench genuine change and progress in the
areas of security, reconstruction and reconciliation. The Prime Minister judges that
our present level of effort should be stepped up in response. He would like to see
a qualitative change in our ability to monitor progress in these key areas, to identify
blockages to progress, and to take rapid action to fix these.”
380
Minutes, 7 December 2006, DOP(I) meeting.
377
Note [Blair to Bush], [20 December 2006], ‘Note’.
378
Letter Phillipson to Hayes, 5 January 2007, ‘Prime Minister’s Phonecall with President Bush,
379
5 January: Iraq’.
Letter Banner to Siddiq, 8 January 2007, ‘Iraq’.
380
304

---
10.2 | Reconstruction: July 2004 to July 2009
671. The letter asked for detailed reports and weekly updates on key areas, including:
a detailed report on reconstruction; and
a weekly report on political development, security and economic activity
in Basra.
672. Mr Blair and President Bush spoke again on 9 January.
 Mr Blair said that he had
381
asked for changes in the way that the UK system monitored and chased up progress
in Iraq. Information, for example on reconstruction, was incomplete. The US and UK
needed to be sure that everything that could be done on reconstruction was being done.
Mr Blair said that he wanted someone on the UK side “such as a senior military figure” to
travel around Iraq and report on what was actually happening, for example in Najaf. The
US and UK needed to improve delivery of assistance in calmer areas, to demonstrate
that peace brought dividends.
673. An 11 January JIC Assessment judged that:
There continued to be real economic growth in Iraq, but the Iraqi Government
had shown little commitment to economic reform and large-scale job creation
was highly unlikely in the next two years.
The Iraqi Government was not short of funds (the JIC estimated that the
Government had accumulated some US$12bn since 2003 as a result of unspent
budget allocations), but public investment was hampered by weak central
Government ministries and a lack of competent staff at all levels of Government.
The security situation remained the main obstacle to private sector development
and foreign investment.
382
674. President Bush announced the new US strategy in an address to the nation on
10 January:
“The situation in Iraq is unacceptable to the American people – and it is
unacceptable to me …
“It is clear that we need to change our strategy in Iraq.”
383
675. President Bush said that a successful strategy needed to combine robust military
operations with visible improvements in Iraqi neighbourhoods and communities.
As well as providing 20,000 additional US troops and increasing efforts to build the
capacity of the ISF, the US would also increase its efforts to build the capacity of the
Iraqi Government, including by doubling the number of PRTs and giving US military
commanders and PRT leaders greater flexibility in how they used resources for
economic assistance.
Letter Banner to Hayes, 9 January 2007, ‘Prime Minister’s Phonecall with President Bush, 9 January:
381
Middle East Issues’.
JIC Assessment, 11 January 2007, ‘Iraq: Economic Prospects’.
382
The White House Archive, 10 January 2007, President’s Address to the Nation.
383
305

---
676. The result of the new strategy set out by President Bush is often referred to in
contemporary documents as the new Baghdad Security Plan.
677. The British Embassy Baghdad reported on 11 January that the new Iraqi-led
Baghdad Security Plan was under way.
 In contrast to previous plans, there was
384
greater emphasis on reconstruction, with a focus on job creation. Five “mini-PRTs” had
been embedded with troops in Baghdad to assist with reconstruction operations. The
US also planned to inject funds into Iraqi State-owned enterprises to generate rapid job
creation (the Bradley Initiative).
678. The British Embassy Baghdad reported on 26 March that the US had spent
US$1.6bn on 1,678 reconstruction projects as part of the new Baghdad Security Plan.
385
Major General Shirreff’s proposal for a military-led UK effort in
the South
679. In parallel with discussions on the new US strategy, the UK Government
considered and rejected Maj Gen Shirreff’s proposal for a military-led Joint Inter-Agency
Task Force in the South.
680. Maj Gen Shirreff wrote to Mr Blair on 29 December to offer, in response to
Mr Blair’s request during his recent visit to Iraq, “some thoughts on how a Joint
Inter-Agency Task Force would deliver concentrated British effect in SE Iraq and improve
the prospects of achieving strategic success”.
386
681. Surveys indicated that Op SINBAD was having a positive effect, but it could do no
more than:
“… create a window of opportunity that must be filled by mass economic effect,
a Rooseveltian New Deal for Basra. Only thus will the militia be defeated. This
requires the mass injection of Iraqi Government funds …”
682. Maj Gen Shirreff proposed that to achieve that:
the Iraqi Government should establish a reconstruction committee for Basra with
authority and capability to spend central Government money; and
the coalition should establish an organisation capable of providing the right
advice and planning capability.
683. The current arrangement lacked unity of command and purpose. HQ MND(SE) had
the planning muscle, the energy, the staying power and the unity of command to execute
an overarching plan (such as Op SINBAD), but it lacked expertise on reconstruction. The
eGram 1160/07 Baghdad to FCO London, 11 January 2007, ‘Iraq: Reinvigorated Baghdad Security
384
Plan’.
eGram 12261/07 Baghdad to FCO London, 26 March 2007, ‘Iraq: Update on the ‘Economic Surge’’.
385
Letter Shirreff to Blair, 29 December 2006, [untitled].
386
306

---
10.2 | Reconstruction: July 2004 to July 2009
PRT, currently below strength and operating out of a hotel in Kuwait, preferred to focus
on long-term capacity-building. Co-location in the new year, when the PRT moved to the
BAS, would help but would not solve the underlying problems.
684. Maj Gen Shirreff recommended that the UK should establish a Joint Inter-Agency
Task Force (JIATF) with coalition partners, combining military and reconstruction
expertise under single military command.
685. Lt Gen Shirreff told the Inquiry that his proposal for a JIATF under military
command was a response to the fragmented UK effort at the time:
“… this was sort of desperate times and desperate measures. I’m not sure I would
necessarily propose the same solution today … But at the time, it seemed to be the
only way …”
387
686. The ISG discussed Maj Gen Shirreff’s letter on 5 January 2007.
 Vice Admiral
388
Charles Style, Deputy Chief of Defence Staff (Commitments), said the letter did not
reflect the “MOD corporate view”, but that he had some sympathy for the need for better
co-ordination and command: the southern Iraq Steering Group had met only five times
since May 2006, which was not good enough. Co-location at the BAS should solve much
of the problem, and the organisation needed to be tauter and more focused, but not
necessarily military-led.
687. Sir Nigel Sheinwald told the ISF that Iraq was “entering a new phase, which
required a coherent structure under a single point of contact” and asked for the ISOG to
work on new structures.
688. Sir Nigel reported to Mr Blair after the meeting that Maj Gen Shirreff’s views:
“… represent his frustration, shared by the MOD, that the civilian reconstruction
effort is uneven. We all agree that we need to make sure that we have an effectively
led Basra operation for the next year (at least).”
389
689. Sir Nigel advised that co-location of HQ MND(SE), the PRT and the British
Embassy Office Basra at BAS from late February would help co-ordination enormously.
He had asked the departments concerned, led by PCRU, to advise on the right structure
for the British effort. The balance of opinion was that “it should be civilian-led, with strong
military input and follow-up”.
690. Sir Nigel added that both DFID and the FCO were:
“… very fed up with Shirreff’s disparaging comments about the civilian effort
… But the fact is that there have been constant problems between the military
Public hearing, 11 January 2010, page 42.
387
Minute Cabinet Office [junior official] to Sheinwald, 5 January 2007, ‘Iraq Strategy Group, 5 January’.
388
Minute Sheinwald to Prime Minister, 5 January 2007, ‘Iraq: Weekly Update’ attaching Paper Cabinet
389
Office, 5 January 2007, ‘Basra’.
307

---
and civilian people in Basra from the start. We must make a last effort to get
a joined-up operation.”
691. Mr Blair wrote on Sir Nigel’s minute: “Put Shirreff in charge. The Army gets things
done.”
390
692. A No.10 official wrote to Mrs Beckett’s Private Secretary on 8 January, advising
that Mr Blair retained an open mind on how to improve civilian/military co-operation in
Basra.
 He looked forward to receiving advice from officials, and was “if necessary …
391
content that this should be delivered via a task force under military leadership”.
693. At DOP(I) on 11 January, Ministers commented that “unbalanced reporting from the
military in theatre, disparaging the civilian effort” was “extremely unhelpful”.
 It was not
392
the right time to create a new UK military-led structure when the UK was trying to put the
Iraqi Government in the lead.
694. Mr Dinham, who attended the DOP(I) meeting, reported to DFID colleagues
that Mr Benn had spoken strongly against Maj Gen Shirreff’s proposal, arguing that
the UK should let existing, Iraqi-led organisations find their feet, accept that the
Iraq Government might not be that interested in our continued advice and help, and
recognise that the time for further UK bilateral pushes on reconstruction was coming to
an end.
 Mr Dinham added that ACM Stirrup had “agreed absolutely with everything
393
that Hilary [Benn] had said”.
695. After receiving a further update from Basra on 12 January, Mr Blair wrote: “I still
need more info on Basra and have we established the Joint Working yet, led by the
military?”
394
696. The meeting of the ISOG on the same day discussed the problems with civilian/
military co-ordination.
 The ISOG agreed that there were a number of contributing
395
factors, “including personalities, departmental differences in duty of care, and too
infrequent meetings of the southern Iraq Steering Group”. There was a need to revise
structures, to balance the military effort with the civilian, to balance long- and short-term
efforts, and that “a military lead was not the right way to go at this time”. Dr Marsden
and Maj Gen Shirreff, supported by PCRU, were preparing recommendations on a
revised structure.
Manuscript comment Blair on Minute Sheinwald to Prime Minister, 5 January 2007,
390
‘Iraq: Weekly Update’.
Letter Banner to Siddiq, 8 January 2007, ‘Iraq’.
391
Minutes, 11 January 2007, DOP(I) meeting.
392
Email Dinham to DFID [junior official], 11 January 2007, ‘Restricted: DOP(I)’.
393
Manuscript comment Blair on Minute Banner to Blair, 12 January 2007, ‘Iraq Update,
394
12 December’[sic].
Minute Cabinet Office [junior official] to Sheinwald, 12 January 2007, ‘Iraq Senior Officials Group’.
395
308

---
10.2 | Reconstruction: July 2004 to July 2009
697. On 16 January, Mr Blair raised the issue of civilian/military structures in Basra
during a meeting with ACM Stirrup and senior officials from the FCO, SIS, the MOD,
DFID and the Cabinet Office.
396
698. ACM Stirrup said he did not agree with Maj Gen Shirreff’s proposals. It was too
late to establish a JIATF; the UK’s focus should be on building Iraqi capacity to deliver
assistance. The military should not lead that work. Mr Dinham agreed. The No.10 record
of the meeting did not report Mr Blair’s view.
699. Mr Dinham reported separately to DFID colleagues only that Mr Blair had nodded,
“seeming to accept” the argument against a move to a military-led reconstruction
effort.
397
700. Maj Gen Shirreff told the Inquiry:
“… it was pretty clear to me that … looking over the period as a whole of my time
in command – we had a strategy that involved extraction rather than necessarily
achieving mission success. It was, in a sense, an exit strategy rather than a winning
strategy. A winning strategy was going to require significant additional resources.”
398
701. Major General Jonathan Shaw succeeded Maj Gen Shirreff as GOC MND(SE)
in January.
702. At the 25 January meeting of the ISG, Sir Nigel Sheinwald asked the FCO and
Dr Marsden for a note on the new civilian/military structure in Basra for Mr Blair.
399
That note was issued on 2 March.
Preparing for Provincial Iraqi Control in Basra
703. Sections 9.4 and 9.5 describe the sharp rise in sectarian violence after the
bombing of the al-Askira mosque in Samarra in February 2006, and the consequent
displacement of Iraqi citizens along sectarian lines. The Government’s response to that
displacement is addressed later in this Section.
704. Section 9.5 describes the discussions between UK and US senior military officers
and officials on UK plans for the drawdown of UK troops from MND(SE), and continuing
US concerns that UK plans were premature given the security situation in MND(SE).
705. Mr Etherington completed his tour as Head of the Basra PRT in January 2007.
400
Two PCRU officials provided short-term cover as Head of the PRT between January and
April 2007.
Letter Banner to Siddiq, ‘16 January 2007’, ‘Iraq: meeting with officials’.
396
Email Dinham to DFID [junior official], 16 January 2007, ‘ Iraq’.
397
Public hearing, 11 January 2010, page 7.
398
Minute Cabinet Office [junior official] to Sheinwald, 26 January 2007, ‘Iraq Strategy Group, 25 January’.
399
Minute DFID [junior official] to Private Secretary [DFID], 13 March 2007, ‘Iraq: Future of DFID’s
400
Presence and Programme in Basra’.
309

---
706. At DOP(I) on 11 January 2007, Ministers commented that Internally Displaced
People (IDPs) were “principally an Iraqi Government responsibility – it should address
the violence and push forward reconciliation, and had the resources to address the
needs of the displaced”.
401
707. Mr Benn wrote to Mr Blair on 24 January to provide an update on the situation:
“Displacement is causing a de facto geographical separation along sectarian lines,
as different ethnic groups move to areas in which they will be the majority.
“There is clearly a strong political dynamic to the situation and it is essential
that we address both the cause and the symptoms … We should press the Iraqi
Government to address displacement issues as part of reconciliation, and to do
more itself to provide basic services to meet humanitarian needs. The picture is
unpalatable for the Iraqi Government … and indeed for the coalition (hence the
largely silent nature of the humanitarian crisis so far) …
“It is clear that while not letting the Iraqi Government off the hook, we must also
continue to respond to humanitarian needs in Iraq … ”
402
708. The first set of reports requested by Mr Blair’s Private Secretary on 8 January
was passed to Mr Blair on 19 January.
 It included a report from Dr Marsden on
403
developments in Basra.
404
709. On the economy, Dr Marsden reported that the PRT “continues to focus on building
the capacity of the Provincial Council to identify priority investment, secure funding and
spend it in a transparent way”.
710. DFID produced its first fortnightly update on reconstruction for Mr Blair on
25 January.
 The paper, which he welcomed,
 highlighted the need to persuade
405
406
Prime Minister Maliki to see reconstruction as a strategic issue:
“As the sectarian conflict in Iraq deepens, the coalition’s ability to buy consent
through quick impact reconstruction projects is waning. Alongside security, Prime
Minister Maliki’s Government must start providing basic services to help it win back
legitimacy from the militias and other armed groups …
“There are some signs that the Government is at last starting to grasp this agenda.
It has set up an economic committee … and a basic services committee … These
committees, with US support, aim to co-ordinate civil-military action to build local
Minutes, 11 January 2007, DOP(I) meeting.
401
Letter Benn to Blair, 24 January 2007, [untitled].
402
Minute Banner to Prime Minister, 19 January 2007, ‘Iraq Update, 18 January’.
403
Letter Marsden to Aldred, 18 January 2007, ‘Basra: Weekly Report’.
404
Paper DFID, 25 January 2007, ‘Iraq: Reconstruction Update’.
405
Paper DFID, 25 January 2007, ‘Iraq: Reconstruction Update’; Letter Banner to Siddiq, 29 January 2007,
406
‘Iraq’.
310

---
10.2 | Reconstruction: July 2004 to July 2009
support by delivering a reconstruction ‘peace dividend’. As yet, it is too early to judge
how successful this approach is likely to be.”
711. DFID also reported that its aim in the run up to PIC in Basra was to help the
Provincial Council demonstrate that it was in charge and delivering services. The first
step was to secure Baghdad’s approval for Basra’s provincial strategy and associated
budget. The second was to get Baghdad to release the funds. The third was to help the
Council to communicate and deliver services. The US had adopted a similar focus.
712. DFID’s second fortnightly update on 8 February expanded on the problems that
the Iraqi Government had in spending its money.
 With oil prices topping US$60 per
407
barrel, the Iraqi Government was “cash rich”, but in the nine months to October 2006, it
had spent just 14 percent of the US$8.2bn allocated to public investment. The Ministry
of Oil had spent only one percent of the US$3.5bn allocated to it. DFID attributed the
underspend to:
poor security;
poor planning by line ministries (and failure at the centre to demand plans); and
paralysis resulting from distrust between the Ministry of Finance (responsible for
disbursing and accounting for funds) and the Ministry of Planning (responsible
for reviewing plans and agreeing allocations).
713. The Iraqi Government was considering setting up a National Council for
Reconstruction and Development, chaired by the Prime Minister, to accelerate
disbursement. The US was setting up a “Budget Execution Cell” in the Deputy Prime
Minister’s Office, which might increase disbursement in the short term but was unlikely
to be sustainable or to lead to significant improvements in services. DFID commented:
“In reality, there are few quick fixes to improving services in Iraq.”
714. DFID also reported that the World Bank would open an office in Baghdad the
following week. It would have three full-time staff, “supported by DFID and protected
under the [UK] security umbrella”. As the coalition scaled back during 2007, the Bank
was likely to become the Iraqi Government’s “partner of choice”.
715. On the Iraqi Government’s failure to disburse, Mr Blair commented, “we must get
this sorted out”; on Iraqi and US action to increase disbursement, he asked, “can’t we
provide the competence?”.
408
716. Dr Marsden reported on 9 February that the centre of a “revamped” Better
Basra Action Plan would be a political plan for getting Basra to PIC and beyond. That
political plan would be supported by the other lines of operation (“military, police,
reconstruction etc”).
409
Paper DFID, 8 February 2007, ‘Iraq: Reconstruction Update’.
407
Manuscript comment Blair on Paper DFID, 8 February 2007, ‘Iraq: Reconstruction Update’.
408
Letter Marsden to Aldred, 9 February 2007, ‘Basra: Weekly Report’.
409
311

---
717. Dr Marsden commented that it was important to acknowledge that the UK did not
have a sufficiently clear picture of Basrawi politics and their connection to Baghdadi
politics to be confident that any plan was credible.
718. The MOD sent No.10 a report on the effects of Op SINBAD on 16 February, as
background material for Mr Blair’s statement to the House of Commons the following
week.
 It concluded that “quick impact projects, short-term employment, and the
410
demolition of the Jameat police building” had improved consent levels and provided
an opportunity to make progress towards PIC.
719. MND(SE) had spent US$77m on quick impact projects during Op SINBAD,
generating 25,000 short-term jobs. Those economic results had not been decisive;
many of the economic problems in southern Iraq stemmed from a lack of national and
Provincial Government capacity to prioritise and spend resources:
“The Provincial Council need to start leading and delivering projects for decisive
and sustained economic effect to be felt.”
720. Mr Blair told the House of Commons on 21 February that the UK hoped that
Maysan could be transferred to full Iraqi control “in the next few months”, and Basra
in the second half of 2007.
 The transfer of security responsibility would result in a
411
reduction in the level of UK forces from 7,100 to roughly 5,500. With the exception of
those troops which would remain at Basra Palace, UK forces would be based at the BAS
and be in a support role.
721. At the end of February, at Mr McDonald’s request, Dr Marsden produced a second
report on life for ordinary Iraqis in Basra.
412
722. Drawing on over 100 interviews carried out in and around Basra by a member of
the PRT, poll data and other sources, she reported that life was “still grim”. Violence and
lawlessness were Basrawis’ overwhelming concern. Women were increasingly afraid to
leave the house, fearing kidnap, harassment or sexual violence. Many had been forced
to give up their jobs. The police were not trusted, with many interviewees telling stories
of intimidation, kidnapping and death squads.
723. Support for the national Government and Prime Minister Maliki was high, support
for the Provincial Government low. Local politicians were seen as corrupt, unqualified
and linked to militias. No interviewee was able to give an example of something that
the Provincial Government had done to improve the lives of ordinary people. After
security, unemployment was the most commonly cited concern: polling indicated that
some 30 percent of Basrawis were employed. Few interviewees saw any improvements
in basic services: what work had been done was of poor quality. Most Basrawis had
Letter Beadle to Banner, 16 February 2007, ‘The Effects of Op SINBAD 20 September 2006 to
410
14 January 2007’.
House of Commons, Official Report, 21 February 2007, columns 261-280.
411
Letter Marsden to McDonald, 28 February 2007, ‘Basra: everyday life for ordinary Iraqis’.
412
312

---
10.2 | Reconstruction: July 2004 to July 2009
electricity for between seven and 12 hours a day. Mains water was not suitable for
drinking; families that could afford it bought bottled water. Hospitals were dirty and poorly
staffed and equipped. Experienced doctors had left the country or been killed. Medicine
was expensive and in short supply. School standards were low.
724. More positively, Dr Marsden reported that people still rejoiced in their greater
political freedom. Civil society was growing. The better off could enjoy new consumer
goods and the freedom to travel outside Iraq. There were signs of growth in the local
economy and public sector salaries had steadily increased.
725. Dr Marsden sent Ms Aldred the third iteration of the Better Basra Action Plan
(BBP3) on 2 March.
 In her covering letter, Dr Marsden advised that:
413
“For the first time we have got a fully integrated plan that has been drafted jointly
by the Consulate [British Embassy Office Basra], the PRT and MND(SE).”
726. Dr Marsden also advised that BBP3 had also been discussed in detail with the
Head of the US Embassy Regional Office in Basra, who was content with it (though he
did not intend to clear it formally with Washington).
727. BBP3 stated that it was “a comprehensive strategy for bringing Basra to the point
where it can transition to Provincial Iraqi Control (PIC)”. It sought to ensure that all nine
“lines of operation” (political, security, rule of law, the judiciary, prisons, governance,
infrastructure, economic development and strategic communications) were integrated
under a single, overarching political strategy. BBP3 set out for each line of operation, key
benchmarks for March and June 2007, a detailed work plan, and an estimate of the cost
of implementing proposed new projects (which totalled some £21m in 2007/08). Delivery
of BBP3 would be “driven by” the southern Iraq Steering Group (SISG).
728. The political and security lines of operation are described in Section 9.5 and the
rule of law, judiciary and prisons lines of operation in Section 12.1.
729. On governance, BBP3 stated that the UK’s focus would continue to be to help the
Provincial Council to plan for, access and spend resources in a prioritised, transparent
and accountable way, and to develop an effective working relationship with Baghdad to
ensure that Basra got its share of the national budget.
730. On infrastructure, the UK’s objective was to support the Provincial Council to
deliver better services using Iraqi resources, while continuing to use CERPs funding,
where appropriate, for “last mile service provision”.
731. On economic development, the UK’s priorities were to boost job creation, lay
the foundations for more entrepreneurial activity and cross-border trade, support the
agricultural sector, and build the Provincial Government’s capacity to support economic
Letter Marsden to Aldred, 2 March 2007, ‘Better Basra’ attaching Paper Basra Consulate/PRT/
413
MND(SE), 1 March 2007, ‘Better Basra Mark 3: The 2007 plan’.
313

---
development. Activities included the establishment of a Basra Provincial Development
Agency and Development Fund.
732. BBP3 stated that:
“We have to be realistic about what we can achieve. With the time and resources
available, we cannot address all Basra’s problems nor every falling in its
public administration and security forces. ‘Better Basra’ seeks to address those
identified as most critical to making progress against established transition
readiness indicators.”
733. Mr Rob Tinline, Deputy Consul General in Basra from February 2007 to
February 2008 and one of the authors of BBP3, told the Inquiry:
“… one of the great debates was: is it [BBP3] a British plan or is it a coalition plan?
And obviously with GOC MND(SE) saying, ‘Well, if it’s going to be mine, it’s going
to have to be a multi-national plan’, the Consul General saying, ‘Well, hang on,
we can’t clear this through the State Department, it will take forever’, what do
you do? I think I’m right in saying 90, 95 percent of the money that was spent
in Basra was American money. So if we wrote a British plan with five per cent of
the money, well …
“So how you wrote a plan was actually a ridiculously complicated thing, and we
ended up … with a sort of compromise where we’d shown it to the Americans and
they sort of said, ‘Yes, this is more or less right’, but it was a British plan … We
would never have got a multi-national plan for the South through the American
system.”
414
734. A September 2008 review of the Basra PRT undertaken by the Stabilisation Unit,
the successor to the PCRU, offered a view on the Better Basra planning process at
this time:
“There is no [UK Government] wide strategy for Iraq … Although the Better Basra
Plans did go some way towards addressing this absence in 2006 and 2007, these
evolved in an incremental bottom-up way, hampered by a lack of strategic guidance
from Whitehall, and frequent change-over of personnel in theatre, and so eventually
fell by the wayside during the course of 2007.”
415
Public hearing, 24 June 2010, page 27.
414
Report Stabilisation Unit, 3 September 2008, ‘Review of the Basra Provincial Reconstruction Team’.
415
314

---
10.2 | Reconstruction: July 2004 to July 2009
735. Also on 2 March, Dr Marsden and Maj Gen Shaw wrote to Ms Aldred, in response
to Sir Nigel Sheinwald’s 25 January request for a note on civilian/military structures in
Basra.
 They advised that:
416
“The profile of the security concerns in southern Iraq should not obscure the
fundamentally political nature of the end state we are pursuing. Military action must
be supportive of the political and civilian lines of operation.”
736. Consistent with that assessment, the SISG, chaired by Dr Marsden, would oversee
delivery of the strategic objectives identified in BBP3. The SISG would take strategic
direction from and report to the ISG and the ISOG in London.
737. Maj Gen Shaw told the Inquiry:
“… I had inherited a situation where the military commander and the Consul General
had joint ownership of the southern Iraq Steering Group.
“Well, I’ve always adhered to the principle that … if you can’t identify who is in
charge, you are in trouble, and joint ownership strikes me as a recipe for disaster
because you don’t know who is in charge.
“I said to the Consul General [Dr Marsden], ‘Listen, this is a political problem, not
a military one now. We’re supporting you in achieving a political end state for Iraq.
So you are in charge, I’m in support. What do you want me to do?’ …”
417
738. Dr Howells briefed Ministers on the finalisation of BBP3 and the process for
implementing it at the 8 March meeting of DOP(I).
 BBP3 would be circulated out of
418
committee the following day for Ministers “to note”.
739. The 8 March meeting of DOP(I) also considered the deteriorating humanitarian
situation in Iraq.
 The Government’s response to the humanitarian situation is
419
addressed later in this Section.
740. A DFID official advised Mr Benn on 13 March that Mr Tinline (the Deputy Consul
General) would “double-hat” as the PRT Team Leader from 1 April.
 That should ensure
420
better co-ordination between civilian and military elements. PCRU officials had covered
the post since Mr Etherington’s departure in January.
741. Mr Tinline told the Inquiry that, during his time in Iraq, the British Embassy Office
Basra had an (international and local) staff of 100 and the PRT a staff of 30.
421
Letter Marsden and Shaw to Aldred, 2 March 2007, ‘The Comprehensive Approach: Application
416
in southern Iraq’.
Private hearing, 21 June 2010, pages 20-21.
417
Minutes, 8 March 2007, DOP(I) meeting.
418
Minutes, 8 March 2007, DOP(I) meeting.
419
Minute DFID [junior official] to Private Secretary [DFID], 13 March 2007, ‘Iraq: Future of DFID’s
420
Presence and Programme in Basra’.
Public hearing, 24 June 2010, page 106.
421
315

---
742. Mr Benn was also advised that the final component of DFID’s IISP, the Basra
water towers, should be completed in October; that would conclude DFID’s direct
infrastructure work.
743. Maysan transferred to PIC on 18 April. Maysan was the third province within
MND(SE) to transfer, Muthanna and Dhi Qar having done so in July and September
2006 respectively. This left Basra as the only province for which the UK retained
security responsibility.
744. Section 9.5 describes the UK’s focus in early 2007 on encouraging the Iraqi
Government to do more to promote reconciliation in Iraq, against a background of
continuing sectarian violence. The UK saw a Hydrocarbons Law as one element of an
effective reconciliation process.
745. Mr Richard Jones, Dr Marsden’s successor as the British Consul General in Basra,
reported on 19 April that “out of the blue”, a demonstration against Governor Waili
“throws open the political future of Basra”.
 Mr Jones assessed that the demonstration
422
had been motivated in large part by “a straight power struggle” in Basra drawing on
concerns over corruption, and in part by national politics.
746. Mr Robert Tinline, Acting Consul General in Basra, reported on 26 April that the
ongoing power struggle in Basra, centred on Governor Waili, was diverting energy
from other activity.
 Several key meetings on development had been postponed. If the
423
uncertainty dragged on, the UK would begin to lose momentum on key strands of work.
747. Mr Browne briefed Cabinet on 3 May that the political vacuum in Basra threatened
to undermine UK efforts and the gains made by Op SINBAD.
 Governor Waili was
424
assailed on all sides and was ineffective. Militias were vying for political power.
748. On the same day, members of the international community gathered in Sharm
el-Sheikh, Egypt, to launch the International Compact with Iraq.
 It was formally
425
launched by Prime Minister Maliki and UN Secretary-General Ban Ki-moon. The UN
described the Compact as:
“… a five-year national plan that includes benchmarks and mutual commitments
from both Iraq and the international community, all with the aim of helping Iraq on the
path towards peace, sound governance and economic reconstruction.”
749. At the launch, Mrs Beckett announced that the UK would spend at least an
additional £100m on rebuilding Iraq.
426
Letter Jones to Aldred, 19 April 2007, ‘Basra: Weekly Report’.
422
Letter Tinline to Aldred, 26 April 2007, ‘Basra: Weekly Report’.
423
Cabinet Conclusions, 3 May 2007.
424
United Nations, 27 April 2007, Fact Sheet on the International Compact with Iraq.
425
BBC News, 3 May 2007, UK pledges extra £100m for Iraq.
426
316

---
10.2 | Reconstruction: July 2004 to July 2009
750. A DFID official advised Mr Benn that that commitment, added to the
£544m pledged at the Madrid Donors Conference in October 2003 and the
£100m announced by Mr Brown in November 2006 (when it had been thought the
launch of the Compact was imminent), brought the UK’s total “Iraq reconstruction
pledge” to £744m.
 £660m of that had already been spent and £730m was forecast
427
to be spent by the end of 2008. The pledge therefore required only very modest
expenditure on Iraq between the end of 2008 and 2012 (the end of the Compact period).
The International Compact with Iraq, May 2007
The International Compact with Iraq was formally launched by Prime Minister Maliki and
UN Secretary-General Ban Ki-moon on 3 May 2007.
428
Preparatory work on the Compact began in early 2006. The UK hoped that the Compact
would draw in international support (with the UN and World Bank at the centre) to help
Iraq deliver its National Development Strategy.
 Delivery of residual Madrid Donor
429
Conference pledges and non-Paris Club debt relief would complement the Compact.
The UK progressively lowered its expectations. Mr McDonald reported to ISOG on
3 November 2006 that there was a “clash of objectives”, with Iraq asking for funding and
the international community requesting “evidence of progress”.
 ISOG agreed the UK
430
should focus its effort on the period after the launch, to ensure “robust implementation”.
Later that month, a DFID official advised Mr Benn that the Compact was likely to have
“very little developmental value”.
 It did not reflect Iraq’s slide into sectarian conflict, and
431
Iraqi ownership of and commitment to reform was limited.
Deputy Prime Minister Barham Salih discussed the launch of the Compact with
Sir Nigel Sheinwald on 12 April 2007.
 Mr Salih requested the “UK’s leadership” in urging
432
Europe to commit resources to Iraq over the next four to five years. Sir Nigel agreed.
Mr Salih also asked the UK to lobby European partners to agree to write off 100 percent
of Iraqi debt.
Mr Blair was advised the following day that departments were considering what more
the UK and other European countries could do, but that encouraging investment in the
current security climate and in the absence of progress on the reconciliation agenda
would be difficult.
433
751. Mr Blair announced on 10 May that he was standing down as Leader of the Labour
Party and would be resigning as Prime Minister on 27 June.
434
Minute Winterton to Private Secretary [DFID], 27 April 2007, ‘Iraq: Compact launch and UK statement’.
427
United Nations, 27 April 2007, Fact Sheet on the International Compact with Iraq.
428
Minute Asquith to Private Secretary [FCO], 24 May 2006, ‘Iraq: DOP-I: 24 May’.
429
Minute Cabinet Office [junior official] to Sheinwald, 6 November 2006, ‘Iraq Senior Officials Group’.
430
Minute DFID [junior official] to Private Secretary [DFID], 13 November 2006, ‘Iraq: briefing’ attaching
431
Paper DFID, November 2006, ‘Iraq: International Compact’.
Letter No.10 [junior official] to Hickey, 12 April 2007, ‘Iraq: Nigel Sheinwald’s conversation with Barham
432
Saleh, 12 April’.
Minute No.10 [junior official] to Prime Minister, 13 April 2007, ‘Iraq Update, 13 April’.
433
BBC News, 10 May 2007, Blair will stand down on 27 June.
434
317

---
752. Mr Jones reported on 23 May that he understood that the Iraqi Minister of Finance
had instructed the Iraqi Central Bank to freeze all development funds in its Basra
accounts until the conflict between Governor Waili and the Provincial Council had
been resolved.
 He had done so because Governor Waili had written to the Central
435
Bank requesting that those funds be transferred from both his own and the Provincial
Government’s accounts to another, unspecified, bank account. The Provincial Council
had protested. Mr Jones commented that the UK had been working for months to
persuade Baghdad to provide the finance that Basra deserved for development work.
The freeze was another incentive to resolve the political impasse as soon as possible.
753. Mr Jones also reported that:
“All of our contacts speak of deterioration in the security situation … The electricity
supply has also deteriorated … The lack of power has stopped the electric water
pumps from working. Potable water is scarce and 70 percent of the city is without
a mains supply (worst affected are poorer areas such as the Shia flats).”
754. In his evidence to the Inquiry, Mr Jones characterised the poor relations between
Prime Minister Maliki and Governor Waili, and between Governor Waili and the
Provincial Council, as a challenge to UK engagement in Basra but not a constraint.
436
755. On 12 May, Mr Brown’s Principal Private Secretary commissioned advice for
Mr Brown on how the UK might increase support for economic development and
reconstruction in Iraq and, in particular, Basra.
437
756. A Treasury official provided that advice on 24 May.
 Economic growth and
438
job creation had a vital part to play in building sustainable peace and stability and
reconciling Iraq’s divided communities. The three priorities which would do most to
boost economic growth were:
building on existing macroeconomic stability;
improving the efficiency and effectiveness of the public sector; and
expanding and improving the efficiency of the oil industry. That required a
Hydrocarbons Law, improved security and an integrated energy strategy
covering investment and reform.
757. The UK could also consider shorter-term initiatives (although those would become
harder to implement after the drawdown of UK forces), including:
further initiatives on the lines of Op SINBAD; and
initiatives which aimed to revitalise Iraqi industry.
Letter Jones to Aldred, 23 May 2007, ‘Basra: Weekly Report’.
435
Public hearing, 24 June 2010, page 81.
436
Email Treasury [junior official] to Treasury [junior official], 12 May 2007, ‘Iraq – latest situation/economic
437
development’.
Paper Treasury, 24 May 2007, ‘Economic Aspects of Stability in Iraq’.
438
318

---
10.2 | Reconstruction: July 2004 to July 2009
758. The official also advised that there was a limit to the number of jobs that could be
created in the short to medium term and that “whilst more jobs may help to divert some
energies away from conflict, it will only be a small contributory factor to reducing the
violence, whose root causes are multifaceted”.
759. Mr Brown and Mr Browne made a joint visit to Baghdad on 11 June and met
a number of key individuals, including Prime Minister Maliki.
 Mr Brown told Prime
439
Minister Maliki that:
“… the UK was keen to support the Prime Minister on changes to the Constitution,
new laws and reforms and economic infrastructure and support.”
Responding to the displacement crisis
760. Sections 9.4 and 9.5 describe the sharp rise in sectarian violence after the
bombing of the al-Askari mosque in Samarra in February 2006.
761. The International Organization for Migration (IOM) reported that the violence
caused hundreds of thousands
of families to flee their homes; displacement peaked
in June 2006 when over 16,000 families fled their homes.
440
762. A No.10 official sent Mr Blair a UN High Commissioner for Refugees (UNHCR)
update on the situation on 1 December 2006.
 UNHCR advised that approximately
441
425,000 Iraqi citizens had been internally displaced since the Samarra bombing. In
total, there were at least 1.6m Iraqi citizens displaced within Iraq and between 1.6m and
1.8m Iraqi refugees in the region; there were also 50,000 refugees from other countries
in Iraq. The needs of Internally Displaced People (IDPs), returnees, refugees and their
host communities were “dramatic and to a large extent unmet”.
763. On 11 January 2007, the British Embassy Baghdad reported that UNHCR had
launched an appeal for US$60m to meet the humanitarian needs of Iraqi refugees
and IDPs in 2007.
 UNHCR estimated that, of the 1.7m IDPs in Iraq, one million had
442
been displaced before 2003 and up to 490,000 since the Samarra bombing. Obtaining
accurate figures was difficult as many IDPs were living with extended family or not
registering with the Government. UNHCR expected that it would be difficult to raise
funds from donors, given Iraq’s budget surplus.
764. At the 11 January meeting of DOP(I), Ministers commented that IDPs were
“principally an Iraqi Government responsibility – it should address the violence and push
forward reconciliation, and had the resources to address the needs of the displaced”.
443
Letter Bowler to Banner, 13 June 2007, ‘The Chancellor and Defence Secretary’s Visit to Baghdad’.
439
International Organization for Migration, [undated], Iraq Displacement 2007 Year in Review.
440
Minute Banner to Prime Minister, 1 December 2006, ‘Iraq Update, 1 December’ attaching Paper,
441
[undated], ‘UNHCR Update on the Iraq Situation’.
eGram 1267/07 Baghdad to FCO London, 11 January 2007, ‘Iraq: Update on the Situation with
442
Internally Displaced People’.
Minutes, 11 January 2007, DOP(I) meeting.
443
319

---
765. Mr Dinham, who attended the DOP(I) meeting, reported to DFID colleagues that
Mr Benn had said that he would be urging the UN to use unspent donor funds to meet
the UNHCR appeal.
 Mr Browne had favoured pressing the Iraqi Government to
444
contribute to the UNHCR appeal; this was a problem for which the Iraqi Government
was responsible and there was no shortage of Iraqi money.
766. The 11 January report from the British Embassy Baghdad was passed to Mr Blair
on 12 January.
 A No.10 official commented on the report: “We are encouraging the
445
GoI [Iraqi Government] to get its act together, given that these are its citizens.”
767. Mr Benn wrote to Mr Blair on 24 January, providing an update on the humanitarian
situation in Iraq:
“Displacement is causing a de facto geographical separation along sectarian lines,
as different ethnic groups move to areas in which they will be the majority.
“There is clearly a strong political dynamic to the situation and it is essential
that we address both the cause and the symptoms … We should press the Iraqi
Government to address displacement issues as part of reconciliation, and to do
more itself to provide basic services to meet humanitarian needs. The picture is
unpalatable for the Iraqi government … and indeed for the coalition (hence the
largely silent nature of the humanitarian crisis so far) …
“It is clear that while not letting the Iraqi Government off the hook, we must also
continue to respond to humanitarian needs in Iraq …”
446
768. Mr Benn advised that he had therefore decided to contribute £4m to the
International Committee of the Red Cross (ICRC).
769. On 23 February, a No.10 official advised Mr Blair that there had been little
improvement in the humanitarian situation, and that the Iraqi Government remained
“largely silent” on the issue.
 The Iraqi Ministry of Displacement and Migration was
447
trying to help but it had little capacity to respond; its budget was “woefully inadequate”.
Meanwhile, the international community was stepping up its response. DFID continued
to look at ways of unlocking unspent donor funding.
770. The 8 March meeting of DOP(I) returned to the issue of the humanitarian situation
in Iraq.
448
Email Dinham to DFID [junior official], 11 January 2007, ‘DOP(I)’.
444
Minute Banner to Blair, 12 January 2007, ‘Iraq Update, 12 December [sic]’.
445
Letter Benn to Blair, 24 January 2007, [untitled].
446
Minute Fletcher to Prime Minister, 23 February 2007, ‘Iraq Update, 23 February’ attaching Paper DFID,
447
22 February 2007, ‘Iraq: Reconstruction Update’.
Minutes, 8 March 2007, DOP(I) meeting.
448
320

---
10.2 | Reconstruction: July 2004 to July 2009
771. In a briefing paper for the meeting, DFID reported that the number of people
displaced since the Samarra bombing had risen to 650,000.
 UNHCR estimated that
449
the total number of IDPs in Iraq could rise to 2.3m by the end of 2007. The number of
Iraqi refugees in the region had risen from 1.8m to over 2m.
772. The trend was of “increasing polarisation” along sectarian and geographical
lines, which would have a considerable impact on the political landscape and made
a national response more complex. In contrast to previous displacements, the moves
were permanent.
773. In Iraq, security had compromised delivery mechanisms, and weak Iraqi public
services had not been able to keep up with demand. The Iraqi Government had failed
to recognise that this was a strategic issue with long-term political consequences. There
was an increasing risk that militias were being seen by Iraqi communities as guarantors
of local security. The UK’s objective remained to build Iraqi capacity to provide security
and basic services; however:
“It will take years for Iraq to undertake the necessary reforms and develop the
systems for effective service delivery. There is therefore a humanitarian imperative
for the international community to assist in the short term.”
774. DFID stated that it would contribute a further £5m to humanitarian relief operations
in Iraq and the region (bringing DFID’s total contribution to the crisis for 2007 to £9m).
775. Other major contributions were:
Japan had pledged US$104m;
the EC had pledged €20m; and
the US had pledged US$23m.
776. Introducing the DFID paper at the DOP(I) meeting, Mr Benn said that Prime
Minister Maliki remained more focused on security and his own political concerns,
but the UK continued to push the Iraqi Government to allocate adequate resources
to the problem.
450
777. The DOP(I) meeting concluded that the UK should lobby the Iraqi Government,
UN, ICRC and the IOM to step up their actions to address the crisis.
778. DFID made further contributions to the international humanitarian response later
in March and in November, bringing the UK’s total contribution for 2007 to £15m.
451
779. On 18 April, a No.10 official advised Mr Blair that the UN assessed that the refugee
and IDP situation was becoming more acute.
 The Iraqi Government had pledged
452
Paper DFID, 7 March 2007, ‘The Humanitarian Situation in Iraq’.
449
Minutes, 8 March 2007, DOP(I) meeting.
450
Paper DFID, 4 November 2009, ‘Iraq – DFID Timeline and Financial Commitments: 2003 – 2009’.
451
Minute Phillipson to Prime Minister, 18 April 2007, ‘VTC with President Bush – 1800 18 April’.
452
321

---
US$25m to the UN, but that amount was “fairly minimal, given the resources required,
and that it has primary responsibility for the well-being of Iraq’s citizens”.
780. The IOM’s review of displacement in Iraq in 2007 reported that displacement had
slowed over the course of the year, due to improved security in some areas and the
“sectarian homogenization” of previously mixed neighbourhoods: “in other words, there
were fewer and fewer people to force out”.
 Conditions continued to deteriorate for the
453
2.4m IDPs in Iraq.
781. On 12 March 2008, a DFID official advised Mr Douglas Alexander, who had
succeeded Mr Benn as International Development Secretary, that the UN estimated that
there were now 2.2m IDPs in Iraq.
 The Iraqi Government had recently announced
454
a US$40m contribution to the UN’s US$265m Consolidated Appeal (which had been
launched in February), but was doing little to support vulnerable people inside Iraq.
782. DFID contributed a further £29m to the international humanitarian response
in 2008.
455
783. A study by The Brookings Institution-University of Bern Project on Internal
Displacement, published in December 2008, suggested that smaller minority groups in
Iraq comprised a disproportionately large percentage of displaced people, due to the
harassment they had experienced after 2003.
 The study offered a comparison of the
456
estimated numbers of minority groups in Iraq in 2003 and 2008:
Table 1: Displacement of minority groups within Iraq
Group
2003
2008
Christians
1.0 to 1.4m
600,000 to 800,000
Jews
A few hundred
10 to 15
Mandaeans
30,000
Fewer than 13,000
Palestinians
35,000
15,000
Turkomans
800,000 claimed
As low as 200,000
Yazidis
Not known
About 550,000
International Organization for Migration, [undated], Iraq Displacement 2007 Year in Review.
453
Minute DFID [junior official] to PS/Secretary of State [DFID], 12 March 2008, ‘Iraq: Humanitarian
454
Assistance’.
Paper DFID, 4 November 2009, ‘Iraq – DFID Timeline and Financial Commitments: 2003 – 2009’.
455
The Brookings Institution-University of Bern Project on Internal Displacement, December 2008,
456
Minorities, Displacement and Iraq’s Future.
322

---
10.2 | Reconstruction: July 2004 to July 2009
Reconstruction under Mr Gordon Brown’s Premiership
784. Mr Gordon Brown took office as Prime Minister on 27 June 2007. He appointed
Mr Douglas Alexander as Development Secretary, replacing Mr Benn, and Mr David
Miliband as Foreign Secretary, replacing Mrs Beckett. Mr Des Browne remained
Defence Secretary.
785. The most pressing issues facing the UK in Iraq remained the timing of
the withdrawal of UK forces from Basra Palace, and Basra’s transition to PIC
(see Section 9.6).
786. The introductory briefing produced by DFID officials for Mr Alexander described
Iraq as a wealthy country (with oil revenues of US$37bn in the current year) which was
unable to spend or manage its resources effectively to deliver public services because
of poor security, poor political leadership and a lack of technical ability.
457
787. DFID’s priority was to build the capacity of the Iraqi Government to deliver public
services, by providing high-level policy and technical advice in Baghdad on economic
reform. DFID was also looking at options to provide further support for reconciliation,
and providing humanitarian assistance to the four million people displaced in Iraq and
neighbouring countries.
788. In Basra, DFID’s power and water infrastructure programmes would end in late
2007, having delivered improved access to water for over one million people and added
or secured enough power to provide 700,000 people with 24-hour electricity.
789. DFID was also seeking to promote economic growth and private sector investment
in Basra by supporting:
the creation of a Basra Development Commission (BDC);
the creation of a Basra Investment Promotion Agency (BIPA);
the creation of a Basra Development Fund; and
those institutions’ priorities, including a Basra Economic Development Strategy,
investor visits and youth employment initiatives.
790. Mr Alexander’s briefing for a trilateral meeting with Mr Miliband and Mr Browne
in early July highlighted the constraints on reconstruction, including the politicisation
of ministries and deteriorating security:
“The Ministry of Finance does not function effectively and is subject, like many
Ministries, to partisan control. Combined with an almost total lack of transparency,
the Ministry is able to withhold funding to certain ministries.
Paper DFID, [undated], ‘Iraq: Briefing for New Ministers, June 2007’.
457
323

---
“We are increasingly unable to visit key ministries in Baghdad … We need to be
realistic about what is achievable.”
458
791. The briefing also stated that DFID’s budget for Iraq for 2007/08 was £30m, down
from £45m in 2006/07. Officials anticipated a “further tapering” over the next few years,
although that had not yet been announced.
792. Mr Brown spoke to Prime Minister Maliki on 5 July.
 On Basra, Prime
459
Minister Maliki said that he hoped it would be possible to reduce the burden on UK
forces and for Iraqi forces to take the lead within three months.
793. Mr Brown said that he would like to discuss the scope for economic initiatives,
and promised to send suggestions in the next few days. No.10 asked DFID for a draft
letter for Mr Brown to send to Prime Minister Maliki “setting out draft proposals for an
economic initiative”.
794. Mr Brown discussed Iraq with President Bush by video link on 9 July.
 Mr Brown
460
commented that the Iraqi Government was making slow progress. Faster action was
needed on the Hydrocarbons Law and on “democratisation”.
795. In an interview on the BBC’s Today Programme on 11 July, Mr Brown described
the UK’s strategy in Iraq as:
establishing security;
promoting reconciliation; and
“to get people, and this is often forgotten, a stake in the future by helping
the economic development of Iraq”.
461
796. Mr Brown continued:
“… I think one of the failures at the beginning was that we didn’t put the resources
and the help in to economic reconstruction that was necessary … we can do a lot
better in the future.”
797. Mr Brown said that as the UK moved from a combat role to overwatch, it would
bring in the resources that were necessary for economic development.
798. The Overseas and Defence Sub-Committee of the Committee on National Security,
International Relations and Defence (NSID(OD)), the successor to DOP(I) as the
principal forum for Ministerial discussion on Iraq, was scheduled to meet for the first time
on 19 July to discuss transition in Basra.
Minute DFID [junior official] to PS/Secretary of State [DFID], 29 June 2007, ‘Iraq: Briefing for DFID/
458
FCO/MOD Ministerial Trilateral’ attaching Paper DFID, [undated], ‘DFID/FCO/MOD Ministerial Trilateral
on Iraq and Afghanistan’.
Letter Banner to Hickey, 5 July 2007, ‘Conversation with Iraqi Prime Minister’.
459
Letter Henderson to Hayes, 9 July 2007, ‘Iraq/Afghanistan: Prime Minister’s VTC with President Bush’.
460
BBC Radio 4, 11 July 2007, Today Programme.
461
324

---
10.2 | Reconstruction: July 2004 to July 2009
799. In advance of the meeting, FCO and MOD officials produced a joint paper
setting out the latest “assessments and plans on security transition and the associated
re-posturing and drawdown of UK troops in Basra” (see Section 9.6).
462
800. The FCO and MOD assessed that the UK had achieved “only some” of its
objectives in Iraq. Iraq had “the forms of democracy” but the constituent parts of the Iraqi
Government were not working together to a genuine national unity agenda and there
was no commitment to reconciliation. In that context, the paper reported that:
“Ministers treat their Ministries as party and personal fiefdoms, sources of funds
and patronage. The writ of central Government runs weakly outside the Baghdad
International Zone.”
801. The FCO and MOD set out the process by which judgements were reached (by
MNF commanders and Prime Minister Maliki) on whether provinces were ready for
PIC, and an assessment of Basra’s progress against the four PIC conditions (security
conditions and threat levels, ISF capacity, the Governor’s capacity to take responsibility
for security, and the coalition’s ability to re-intervene if necessary). The UK was also
monitoring progress against an additional condition, which it judged to be important:
“capability of the provincial authorities to direct reconstruction, and to spend their
budgets wisely and accountably”.
802. The last UK military base in Basra city was the Basra Palace Compound (BPC),
which the paper described as “the most heavily mortared and rocketed place in Iraq”.
The UK planned to hand over the BPC to the Iraqi authorities, and withdraw UK troops
based there to Basra Air Station (BAS), on 31 August. That would represent the “de facto
handover of responsibility” to the Iraqi authorities, as UK forces would only be able to
intervene from BAS “in extremis”.
803. PIC should take place as soon after the handover of the BPC as possible: a long
gap would place the UK in a difficult position, “responsible for security in Basra city, but
unable to deliver it except at high risk”.
804. The FCO and MOD advised that the UK should stick to its transition strategy,
including PIC in Basra in the autumn.
805. Looking ahead to Basra after PIC, the FCO and MOD advised:
“Our planning should assume that the UK civilian presence in Basra will have to
be wound up shortly before the removal of the UK military envelope which enables
it to operate (though if the US were to decide to move a military presence of their
own to Basra Air Station, and to retain a US civilian presence, we could expect US
pressure for us to maintain some sort of ongoing commitment to the Basra Provincial
Reconstruction Team).”
Paper FCO/MOD, 12 July 2007, ‘Iraq: Transition in Basra’.
462
325

---
806. The FCO and MOD argued for “a long-term UK commitment in Iraq”, which would
include influencing the Iraqi Government and supporting the long-term development of
its capacity, in particular through the provision of advice to ministries in Baghdad.
807. The 19 July meeting of NSID(OD) was cancelled and not reinstated.
463
808. On 11 July, a DFID official sent Mr Simon McDonald, Mr Brown’s Foreign Policy
Adviser, a draft letter for Mr Brown to send to Prime Minister Maliki.
464
809. The draft letter reflected guidance from Mr Alexander that the UK should be
realistic about the role of economic reform and only propose initiatives that had a good
chance of being realised.
465
810. Mr McDonald passed the draft letter to Mr Brown on 27 July, after consulting the
FCO and the British Embassy Baghdad.
 Mr McDonald commented that the approach
466
set out in the draft letter was:
“… sensible and realistic but not particularly ambitious … But the Embassy argue
that, taking into account the security situation and the lack of political will … this is
as much as we would be able to get Maliki to consider.”
811. Mr Brown wrote to Prime Minister Maliki on 29 July.
 While establishing security
467
remained the “abiding priority”, it was vital that people were given a stake in their future.
Mr Brown suggested that the UK could help the Iraqi Government to:
secure a new IMF Stand By Arrangement by the end of 2007;
develop an integrated energy strategy, alongside the World Bank;
reform the banking sector, also alongside the World Bank;
strengthen financial management, by continuing to fund an economic reform
team; and
establish the BIPA to identify and promote investment opportunities throughout
the province. The UK had allocated funds to help establish the Agency. If
successful, it could be replicated in other Provinces and inform the creation of a
National Investment Commission.
812. Mr Brown told the Inquiry:
“… if you can show people that their economic prosperity is possible, then the risks
of returning to violence are seen by people to be too great to put at risk something
that they were now about to enjoy. So I wanted to show in Basra … that the chance
Minute Cabinet Office to NSID(OD) members, 11 February 2010 [sic], ‘Ministerial Meeting on Iraq,
463
Cancellation Note’.
Letter DFID [junior official] to McDonald, 11 July 2007, ‘Iraq: Prime Minister’s Economic Initiative’.
464
Minute DFID [junior official] to PS [Alexander], 11 July 2007, ‘Iraq: ‘Economic Initiative’ – Prime
465
Minister’s Letter to Prime Minster Maliki’.
Minute McDonald to Prime Minister, 27 July 2007, ‘Iraq: Economic Initiative’.
466
Letter Brown to Maliki, 29 July 2007, [untitled].
467
326

---
10.2 | Reconstruction: July 2004 to July 2009
of prosperity was something that people should value and should not put at risk by
allowing the militias to have control in the area.”
468
813. Mr Brown discussed Iraq with President Bush at Camp David on 30 July.
 The
469
meeting note produced by Mr Brown’s Private Secretary recorded only that Mr Brown
welcomed the common ground between himself and President Bush on Iraq and had
outlined the UK’s proposals for a “development agency” in Basra.
814. Mr Asquith called on Prime Minister Maliki on 1 August, to deliver Mr Brown’s
29 July letter on economic reconstruction and to discuss politics in Basra and
nationally.
470
815. Mr Asquith reported that Prime Minister Maliki warmly welcomed Mr Brown’s letter,
which was in line with his desire to deepen co-operation with the UK on issues other
than security and with his own Government’s focus on economic development. Prime
Minister Maliki said that he would approve a request from the Basra Provincial Council
to establish the BIPA.
816. Prime Minister Maliki said that he was also interested in bigger projects in the
Basra region which were national in scope such as the Grand Port project in the oil
sector, which would attract large-scale international investment.
817. Prime Minister Maliki also advised that the “troublesome” Governor Waili had been
legally dismissed but was appealing that decision, causing a delay in his removal.
818. Mr Jones’ weekly report of the same day advised that the Deputy Prime Minister’s
Office had identified bringing Basra International Airport up to international standards
as its top economic priority in the province, and had requested UK advice on how to
achieve that.
Mr Jones was pursuing the issue with the RAF and the US.
471
819. Prime Minister Maliki replied to Mr Brown’s letter on 7 October.
820. Jaysh al-Mahdi (JAM) in Basra called a month-long cease-fire, beginning on
13 August.
 Sir John Scarlett, Chief of SIS, told the Inquiry that:
472
“… the cease-fire for a month on 13 August worked straight away. There was an
immediate falling away of attacks, and it then carried on. It went beyond the month
and it became effectively a permanent feature. So it was remarkably successful.”
Public hearing, 5 March 2010, pages 38-39.
468
Letter Clunes to Gould, 31 July 2007, ‘Prime Minister’s Meeting with President Bush: Iraq […]’.
469
eGram 32637/07 Baghdad to FCO London, 1 August 2007, ‘Iraq: Meeting with Prime Minister Maliki,
470
1 August’.
Letter Jones to Aldred, 1 August 2007, ‘Basra: Weekly Report’.
471
Private hearing, 10 June 2006, page 41.
472
327

---
821. Mr Jon Day, MOD Director General (Security Policy), told the Inquiry that the
cease-fire not only brought a reduction in attacks on coalition forces in Basra:
“But the critical strategic dividend, as far as we were concerned, was that the overall
decline in violence helped encourage the resurgence of real political activity …
“Another consequence, which … was felt to be quite important by those on the
ground at the time … is that prior to the understandings, coalition-sponsored
reconstruction work in Basra had almost come to a stop. The understandings
reduced the threat to military and civilian workers and that allowed work on projects
such as the Basra Children’s Hospital to start up again and to enable us to plan to
do more work elsewhere in Basra.”
473
822. Section 9.6 describes negotiations between the UK and JAM1.
823. Mr Asquith’s 16 August valedictory letter to Mr Miliband focused on security and the
political process, but also reflected on the UK’s role in reconstruction:
“Outside the military contribution, our favoured route has been through providing
expertise. That will remain necessary, but insufficient. The Iraqis prize lasting
legacies … We should consider with an open mind taking a leaf out of the Japanese
book, making use of some of the savings on the defence side to establish a joint or
soft loan financial development fund for specific projects in the education or health
sectors. Easier, and more realistic, would be to establish a large trust fund for a
permanent scholarship scheme to supplement Chevening. Or we should switch our
… focus to an area where we can operate – namely the Kurdish region which we
have consistently and puzzlingly ignored.”
474
824. UK troops were withdrawn from the BPC to BAS on 2 and 3 September.
475
825. DFID advised No.10 on 5 September that since Mr Brown’s 29 July letter to
Prime Minister Maliki, there had been slow but sure progress on Mr Brown’s economic
initiative.
 With the support of the PRT and DFID, the Basra Provincial Council had:
476
Agreed a new Provincial Development Strategy. The flow of funds from Baghdad
was also starting to increase.
Agreed with the central Government the “broad shape and purpose” of BIPA,
which would be to identify investment opportunities, provide advice to business
and government, and implement programmes to stimulate private sector
development. The UK was also helping the Council to take forward plans for the
physical establishment of the BIPA.
Public hearing, 6 January 2010, pages 35-36.
473
Letter Asquith to Miliband, 16 August 2007, ‘Iraq: Valedictory’.
474
Minute Binns to CJO, 6 September 2007, ‘GOC HQ MND(SE) – southern Iraq Update –
475
6 September 2007’.
Paper DFID, 5 September 2007, ‘Basra – Economic Initiative Progress Report’.
476
328

---
10.2 | Reconstruction: July 2004 to July 2009
Agreed to establish and fund the Basra Development Fund, which would provide
investment and credit for small and medium sized enterprises.
Begun work on an investment plan and budget to upgrade Basra International
Airport, using Iraqi funds, to meet international standards.
826. At the national level, the Iraqi Government was establishing a National Investment
Commission and had announced its intention to set up a National Development Fund to
provide loans to small enterprises across the country.
827. General Richard Dannatt, Chief of the General Staff, visited Baghdad and Basra
from 5 to 7 September.
 He reported that the situation in Basra was “tentatively quiet”.
477
There was probably only a very narrow window of opportunity to reinforce the success
that had been achieved on the ground; the emphasis had to shift away from the military
line of operation:
“… sustainability … will only be possible if we now begin to deliver some results
on the ground in terms of reconstruction and development. This effort cannot
be delivered by the Army – the FCO and DFID must now be prepared to rapidly
increase their overall effort, not draw it down …
“Perhaps it is even time to consider whether we should be pushing the FCO or DFID
into a more leading role?”
828. Mr Brown and Mr Miliband, accompanied by ACM Stirrup and officials, met
General David Petraeus, Commanding General MNF-I, and US Ambassador Ryan
Crocker
 on 18 September.
 The discussion focused on PIC in Basra.
478
479
829. Mr Brown said that economic development of the South remained a major UK
priority. Gen Petraeus said there were a number of initiatives on which the UK should
engage, including the clearance of Basra port.
830. At the end of the discussion, Mr Brown highlighted three areas for follow up:
further discussion, including with the Iraqis, of the timeframe for Basra PIC;
an enhanced UK effort on economic development, including the Basra port; and
further US/UK discussion of long-term force requirements.
831. Mr Brown visited Iraq on 2 October.
 The objectives for the trip were to underline:
480
the UK’s commitment to Iraq;
the importance of building on progress on security by making a decision soon
to transfer to PIC in Basra;
Minute Dannatt to CDS, 10 September 2007, ‘CGS Visit to Iraq 5-7 Oct’.
477
Ambassador Crocker took up post as the US Ambassador to Iraq in March 2007.
478
Letter Fletcher to Gould, 18 September 2007, ‘Prime Minister’s Meeting with General Petraeus and
479
Ambassador Ryan Crocker, 18 September’.
Letter Fletcher to Forber, 3 October 2007, ‘Prime Minister’s Visit to Iraq, 2 October’.
480
329

---
the need for progress on reconciliation; and
the need for economic progress and service delivery as a strategic priority.
481
832. DFID’s briefing for the visit stated that the UK’s approach was to help build Iraq’s
capacity to use its own resources effectively.
 DFID was therefore proposing a “three
482
part development ‘package’”, in addition to its water and power projects in the South and
capacity-building work in Baghdad. This comprised:
An additional £5m in response to the humanitarian crisis in Iraq and the region,
bringing the total DFID contribution in 2007/08 to £15m.
Support for a number of initiatives designed to promote public and private
investment in Basra including:
support to establish the BIPA and the Basra Development Fund;
{
{
support to develop Basra International Airport. The PRT, MND(SE) and
{
{
Basra Council had produced a US$40m plan to upgrade the airport to
international standards; the UK was working to secure that funding from
central Government; and
the promotion of free trade between Basra and Kuwait.
{
{
Those initiatives, together worth over £10m, would be implemented through the
Basra PRT.
Continuing efforts to “leverage in” funding for Basra from central Government.
The 2007 budget was expected to include over US$300m for investment in
Basra.
833. DFID was also working with MND(SE), other major donors and central Government
to accelerate the renovation of Umm Qasr port. DFID had successfully lobbied central
government to approve over US$250m in soft loans from the Japanese Government for
port renovation.
834. During his meeting with Mr Brown, Prime Minister Maliki said that 2008 would
be the “year of reconstruction”.
 It was good that the UK was ready to play a greater
483
role on reconstruction. Mr Brown said that Basra should receive adequate resources
from central Government, and identified the Basra Investment Forum as an important
opportunity to promote economic regeneration.
Minute Cabinet Office [junior official] to Brown, 1 October 2007, ‘Iraq Visit: 2 October 2007’.
481
Paper DFID, September 2007, ‘UK Development Package for Iraq’.
482
Letter Fletcher to Forber, 3 October 2007, ‘Prime Minister’s Visit to Iraq, 2 October’.
483
330

---
10.2 | Reconstruction: July 2004 to July 2009
835. After Mr Brown returned from Iraq, his Private Secretary commissioned advice
from the Cabinet Office on:
how best to support a Basra Investment Forum;
securing greater UK resources for the effort on reconstruction and economic
development;
whether the UK should do more to support the clear-up of Umm Qasr port;
how best to maximise pressure on Iraqi political leaders; and
how the UK could offer troops in theatre better access to the internet.
484
836. Ms Kathleen Reid, Head of the DFID Office in Basra from August 2007 to
September 2008, reflected on the impact of Mr Brown’s visit in her evidence to the
Inquiry:
“When he [Mr Brown] came in October 2007, to be honest, we were doing quite a
few of those things, or struggling away at trying to do a lot of those economic things.
Things like the Basra Investment Promotion Agency was something we would have
been working on well before he came and visited. Likewise trying to establish the
Basra Development Fund, some discussions around Iraq/Kuwait borders. But …
there just wasn’t necessarily the environment to be able to do that or the impetus
behind it, and I think he came and gave far more impetus to that. We put more
resources towards it, and … with the … changing security in the following months,
it gave more opportunity to then really deliver some results on the ground.”
485
837. Ms Reid also told the Inquiry:
“Each successive visit from Ministers, from Prime Ministers … gave us more clarity,
certainly in terms of timelines.
“When I arrived [in August 2007], there was no real sense of [whether] the PRT
was going to be there for another six months or four years, and that became much
clearer as time went on and allowed us to do, on the civilian side, our planning.”
486
838. Prime Minister Maliki replied to Mr Brown’s letter of 29 July on 7 October.
487
He welcomed the UK’s interest in supporting private sector development in Iraq and
expressed particular interest in working with the UK in the oil sector, and specifically on
infrastructure repairs, installation development, and the development of an integrated
energy strategy.
839. NSID(OD) met for the first time on 8 October.
488
Letter Fletcher to Forber, 3 October 2007, ‘Prime Minister’s Visit to Iraq, 2 October’.
484
Public hearing, 24 June 2010, pages 13-14.
485
Public hearing, 24 June 2010, page 13.
486
Letter Maliki to Brown, 7 October 2007, [untitled].
487
Minute Cabinet Office [junior official] to Prime Minister, 5 October 2007, ‘NSID(OD) Iraq Meeting –
488
Steering Brief: Monday 8 October 09:30’.
331

---
840. At the meeting, Mr Brown said that there had been little progress on political
reconciliation but economic reconstruction in Basra was making better progress, largely
as a result of the improved security environment.
489
841. According to Sir John Scarlett’s own account of the meeting, Mr Brown:
“… spoke very strongly on the ceasefire in Basra and the dramatic improvement
in the security situation. This represented a huge opportunity.”
490
842. On the afternoon of 8 October, Mr Brown told the House of Commons that the UK
expected to establish PIC in Basra in the next two months.
 The UK planned to reduce
491
the number of UK troops in southern Iraq from spring 2008 to around 2,500.
843. Initial guidance on a new format and process for producing DFID Country
Assistance Plans (CAPs) was circulated to DFID officials on 11 October.
492
844. Ms Barbara Hendrie, DFID Deputy Director Iraq, wrote to DFID Heads of
Department on the same day:
“We have only ever had a ‘rough and ready’ version of an I-CAP [Interim Country
Assistance Plan] for the Iraq programme, which is now well out of date. Minouche
[Dr Shafik] asked the team this summer to think of producing a ‘very light touch’
CAP, as the programme is over £20m. We’ve been in the process of looking at
the CAP guidance and trying to adapt it to the Iraq context (not easy!)”
493
“Hence, the revisions to the CAP process are very welcome …”
845. The following day, Ms Hendrie wrote to a junior DFID official:
“It seems pretty clear that we’re going to need to do some form of strategy
document/CAP … it would be great … for you to hold the pen on this.”
494
846. The Inquiry has seen no indications that work on a new CAP was taken forward.
847. DFID told the Inquiry that the I-CAP produced in February 2004 was not
superseded until February 2011, when DFID Iraq published its ‘Operational Plan
2011-2012’.
 DFID closed its Iraq programme in March 2012.
495
Minutes, 8 October 2007, NSID(OD) meeting.
489
Email C, 9 October 2007, ‘Iraq NSID 8 Oct 2007’ attaching ‘NSID Iraq – 8 October 2007’.
490
House of Commons, Official Report, 8 October 2007, columns 21-25.
491
Email DFID [junior official] to DFID Heads of Department, 11 October 2007, ‘For Information: New CAP
492
Format and Process’.
Email Hendrie to DFID [junior official], 11 October 2007, ‘Action Monday 15 Oct: New CAP format
493
and process’.
Email Hendrie to DFID [junior official], 12 October 2007, ‘Action Monday 15 Oct: New CAP format
494
and process’.
Email DFID [junior official] to Iraq Inquiry [junior official], 12 October 2012, ‘New Queries from the
495
Inquiry’ attaching Paper DFID, February 201, ‘Operational Plan 2011-2012’.
332

---
10.2 | Reconstruction: July 2004 to July 2009
848. DFID also told the Inquiry that it decided not to revise the I-CAP because of:
the consistency in DFID “strategic priorities” and funding between 2005
and 2007;
the high turnover of Heads of DFID Baghdad; and
from 2007, DFID’s move away from producing published CAPs (under
Mr Douglas Alexander).
849. A Cabinet Office official advised Mr Brown on 12 October that Governor Waili’s
appeal against his dismissal from post had been successful.
 The UK planned to
496
“resume low-key co-operation with him in the interests of moving beyond the political
stand-off in Basra” while the Iraqi Government took other steps towards his dismissal.
The security situation in Basra remained “relatively calm”.
850. Major General Graham Binns, GOC MND(SE), reported on 18 October that
Gen Petraeus had agreed Lt Gen Odierno’s recommendation of PIC for Basra in
December.
497
851. In a message to the FCO in London on 23 October, Mr Christopher Prentice,
British Ambassador to Iraq, set out some of the implications of Mr Brown’s 8 October
statement.
498
852. Mr Prentice argued that given the UK’s strategic interests and the scale and cost
of its commitment to Iraq so far, “we [the UK] need to accept now that we are in this for
some years to come”.
853. The UK would be judged by the progress Basra made following PIC. By the end
of 2008, key Basra economic initiatives would only just have started and would need
continuing UK support. There was also a case for the UK “planning a last high profile
project as visible proof for Basrawis of our continuing support and as a lasting UK
legacy”.
854. Mr Prentice reported that the UK was already increasing its emphasis on the
“civilian development agenda”. In the longer term, DFID “understandably wish to
normalise its role in a wealthy oil-producing country i.e. close its programme”. It
would be right to do so – but only when the “whole Iraq project” was on track. Unless
the UK was “surprised by success”, 2009 was likely to be too early to begin to close
the programme.
855. The conditions might be favourable by 2009 to re-establish a UK Trade and
Industry presence in Basra “to pursue the huge commercial opportunities there will
eventually be there”.
Minute Cabinet Office [junior official] to Prime Minister, 12 October 2007, ‘Iraq – Weekly Update’.
496
Report Binns, 18 October 2007, ‘GOC HQ MND(SE) – southern Iraq Update – 18 October 2007’.
497
eGram 43230/07 Baghdad to FCO London, 23 October 2007, ‘Iraq 2009 and Beyond – Unfinished
498
Business’.
333

---
856. Mr Browne visited Iraq between 29 October and 2 November.
 He reported to
499
Mr Brown that it had been “markedly the most encouraging of my seven visits to Basra”.
He continued:
“So progress there has been, but, as you well know, the space we have achieved is
fragile and temporary. We have a window of opportunity in Basra and it is vital that
both we and the Iraqis apply political and economic leadership to make the most of it.”
857. Mr Browne had impressed upon everyone he met in Iraq the need to announce
“a detailed economic plan for Basra” to coincide with PIC in December.
858. Mr Browne concluded: “If we are to deliver, and we must, this will need dedicated
and energetic UK resource in London, Basra and Baghdad.”
859. Mr Browne’s visit prompted Maj Gen Binns to evaluate progress made since the
summer.
 His 1 November weekly report advised that:
500
“We are now subject to far fewer attacks, are constructively engaged with the
Governor … and the Provincial Council, we transit through Basra in force … without
opposition … and are looking to make more of the large amount of reconstruction
work we are responsible for (through US resources) in Basra through good
information and media operations.”
860. Mr Alexander sent Mr Brown an update on the Basra economic initiatives on
9 November.
501
861. Mr Alexander advised that DFID had identified several UK business leaders willing
to help drive forward the work of the BDC, including Mr Michael Wareing, International
CEO of KPMG. The BDC (which Mr Alexander described as the “centrepiece” of the
Basra economic initiatives) would bring together national, regional and international
business knowledge to provide strategic advice to the Iraqi authorities on investment
and growth for Basra’s economy. DFID was planning a launch event for the BDC to
coincide with PIC in Basra.
862. Mr Alexander agreed with Mr Browne’s assessment (in his 2 November letter to
Mr Brown) that dedicated UK resources were required to move the economic initiatives
forward. DFID had:
deployed a Project Manager to the Basra PRT to work on economic initiatives;
and
re-orientated DFID’s Economic and Governance team in the PRT to support
the initiatives, and provided £750,000 to establish the BIPA and the Basra
Development Fund.
Letter Browne to Brown, 2 November 2007, [untitled].
499
Report Binns, 1 November 2007, ‘GOC HQ MND(SE) – southern Iraq Update – 1 November 2007’.
500
Letter Alexander to Brown, 9 November 2007, [untitled].
501
334

---
10.2 | Reconstruction: July 2004 to July 2009
863. DFID continued to support other initiatives that would promote growth and
investment in Basra, including Basra International Airport and leveraging in Japanese
loans. Officials were working closely with the Japanese Embassy in Baghdad to help
progress Japanese soft loans through a “complex” Iraqi Government approval process.
Japan had committed some US$2bn in soft loans to Iraq, of which US$1.2bn was for
Basra-based projects including US$254m for the rehabilitation of Umm Qasr port.
Japanese support for reconstruction
Japan pledged and disbursed more assistance for Iraq’s reconstruction than any country
other than the US.
Japan pledged up to US$5bn at the Madrid Donors’ Conference on 24 October 2003,
consisting of US$1.5bn in grants (increased to US$1.7bn by July 2009) for power
generation, education, water and sanitation, health and employment, and Security Sector
Reform, and up to US$3.5bn in concessional loans.
 By July 2009, Iraq and Japan had
502
signed agreements for 12 loan projects worth up to US$2.43bn, of which US$1.37bn was
for seven projects in the South:
Umm Qasr Port Rehabilitation Project. Up to US$270m to dredge shipping lanes,
remove wrecked ships, rehabilitate port facilities, and provide equipment and
materials.
Samawah Bridges and Roads Construction Project. Up to US$30m to build and
rebuild bridges across the Euphrates River and to build connecting roads in the
vicinity of Samawah, in Muthannna.
Irrigation Sector Loan Programme. Up to US$90m for irrigation drainage pumps,
equipment and materials including in Muthanna.
Basra Refinery Upgrading Project. Up to US$20m to increase capacity.
Khor al-Zubair Fertiliser Plant Rehabilitation Project. Up to US$160m to supply
machinery for the Kohr Al-Zubair Fertiliser Plant in Basra.
Crude Oil Export Facility Reconstruction Project. Up to US$430m for the
construction of an on-shore/off-shore pipeline to export oil and installation of off-
shore loading facilities in al-Faw, Basra.
Basra Water Supply Improvement Project. Up to US$370m to improve the water
supply facilities in and around Basra City.
In November 2005, following the Paris Club agreement on debt relief, Japan agreed to
reduce Iraq’s official debt to it by 80 percent, with a value of US$6.7bn.
From February 2004 to July 2006, Japan maintained an Iraq Reconstruction and
Support Group, comprising some 600 troops, in Samawah.
 The Group was mandated
503
to deliver humanitarian and reconstruction assistance only; Australian and UK forces
provided protection.
Government of Japan, Factsheet, August 2009, Japan’s assistance to Iraq (Fact Sheet).
502
BBC News, 8 February 2004, Japan soldiers begin Iraq mission’; BBC News, 16 July 2006, ‘Japan
503
troops withdraw from Iraq.
335

---
864. NSID(OD) met on 20 November to take stock of the situation in Basra.
 Cabinet
504
Office officials briefed Mr Brown that the main aim of the meeting was “to ensure that
the transfer to Iraqi control in Basra, scheduled for 17 December is not delayed” and
that the meeting would need to assess the security situation in Basra and look at how
to sustain the present reduction in violence, including through possible political or
economic measures.
865. At the meeting, Mr Alexander reported that Mr Wareing had agreed to help drive
forward the work of the BDC. Several of the projects included within the BDC’s 2007
plan had been requested by local militia leaders, which would help “lock them into the
economic and political process”.
866. Mr Browne observed that, from a force protection perspective, it would be
important to keep local militia leaders engaged and bring them into the wider political
and economic process as much as possible. Sir John Scarlett agreed that it would be
important to find ways of broadening the dialogue to address a wider range of political
and economic issues.
867. Summing up the meeting, Mr Brown said that:
the UK should “press ahead” with the transfer of Basra to PIC on 17 December;
economic projects should be agreed through proper discussion with local
representatives, rather than favouring any faction or individual, though that “did
not preclude using a coincidence of interest to draw local militia leaders into the
wider political process”;
Mr Alexander should write with plans for the launch of the BDC; and
the UK should continue to encourage the Iraqi Government to hold provincial
elections as soon as possible.
868. After the meeting, Sir John Scarlett’s Private Secretary produced a summary of
his account of the meeting.
 The summary stated that Mr Alexander had expressed
505
concerns about development projects agreed with JAM1 drawing resources and
expertise away from existing projects. There was general support for resource decisions
to be taken in theatre where conflicts arose between priorities.
869. Mr Jones told the Inquiry that:
“… there had been a debate in advance of PIC as to how we could be sure that the
whole situation in Basra remained stable. The economy was identified as the crucial
thing, and we had many hours of amusement discussing that in Basra with our
military colleagues, the degree to which we could help.”
506
Minute Cabinet Office [junior official] to Prime Minister, 19 November 2007, ‘NSID(OD) Iraq Meeting –
504
Steering Brief: Tuesday 20 November 16:45-17:30’.
Minute PS/C, 21 November 2007, ‘NSID (IRAQ) 20 NOV 2007’.
505
Private hearing, 24 June 2010, page 58.
506
336

---
10.2 | Reconstruction: July 2004 to July 2009
870. Section 9.6 describes negotiations between the UK and JAM1.
871. Mr Miliband was advised on 7 December that Prime Minister Maliki and
Governor Waili had met on 5 December and “cleared the air between them”, paving
the way for PIC.
507
872. Lt Gen Rollo reported on 10 December that with Prime Minister Maliki and
Governor Waili now reconciled, the UK had to focus on how the promises to be made
at the Basra Development Forum would be kept:
“General Petraeus’ challenge, reiterated to each UK visitor, to fulfil our Prime
Minister’s intent has been very clear. Barham Salih [the Deputy Prime Minister]
underlined this point when he spoke to the MOD and FCO Permanent Secretaries
who visited this week along with the DFID Director covering the Middle East. He said
that while long term capacity building remained essential, ‘jump starting’ was now
necessary … That should give us our lead. The way that money has been poured
into Anbar, by both the US and the GOI [Iraqi Government], to reinforce success is
also setting the standard; recognising that in counter-insurgency operations, all the
lines of operation must be properly supported.”
508
873. Prime Minister Maliki and Governor Waili jointly hosted a meeting of the Basra
Development Forum at Basra International Airport on 12 December.
 Mr Alexander
509
represented the UK. Mr Salih formally launched the BDC and Mr Alexander announced
Mr Wareing’s appointment as its co-chair.
510
874. Mr Prentice reported the following day that the Forum had been a “hugely
successful event” which struck “an optimistic note on the governance and economic
agenda to complement the security handover” which was due to take place four days
later.
 The Forum had:
511
focused the attention of local and central Government on Mr Brown’s economic
initiatives, and what needed to be done to implement them;
allowed Prime Minister Mailiki and Governor Waili to publicly bury the hatchet.
At Prime Minister Maliki’s insistence, Governor Waili had pledged to tackle
corruption and improve governance;
showed Basra that Baghdad cared. Prime Minister Maliki had not visited Basra
since July 2006; and
been “authentically Iraqi and Basrawi”, rather than a creation of the PRT.
Minute Paterson to PS/Foreign Secretary, 7 December 2007, ‘Iraq – Basra Developments’.
507
Minute Rollo to CDS, 10 December 2007, ‘SBMR-I’s Weekly Report (280) 9 Dec 07’.
508
eGram 50733/07 Baghdad to FCO London, 13 December 2007, ‘Iraq: Basra Development Forum’.
509
Letter Jones to Aldred, 13 December 2007, ‘Basra: Situation Report’.
510
eGram 50733/07 Baghdad to FCO London, 13 December 2007, ‘Iraq: Basra Development Forum’.
511
337

---
875. Maj Gen Binns reported that at the event, Prime Minister Maliki had described
2008 as “the year of redevelopment and reconstruction”.
512
876. Mr Wareing told the Inquiry he had three roles:
to champion economic development, particularly in Basra and the south;
to champion international investment into Iraq; and
to help set up and to chair the BDC.
513
877. Mr Wareing added that his role was not specifically to promote British investment:
“…the line that I pursued was … to try to push investment, not just from a British or
indeed a European or even a western … point of view, but basically any investment
– and there was a significant amount of investment from the Gulf region.”
514
878. Mr Alexander visited Iraq from 11 to 12 December.
515
879. Ms Hendrie reported that both Gen Petraeus and Lt Gen William Rollo, the Senior
British Military Representative, Iraq, had asked Mr Alexander what more DFID could
do to accelerate economic development in Basra to take advantage of the current
improvement in security. Both had made suggestions for additional projects and for an
increase in people – a “civilian surge”.
880. In response, Mr Alexander had made clear that any discussion of the DFID
programme “should be set within a larger conversation about UK objectives in Iraq”.
881. Ms Hendrie told DFID colleagues on 14 December that Mr Alexander wanted
a robust discussion with other Ministers about the UK’s strategy in Iraq:
“My sense is that he believes, in the absence of clear Ministerial guidance about
what HMG can and should be trying to achieve, [that] DFID are being landed with
pressure to deliver an enormous agenda on economic growth in southern Iraq which
a) we are not necessarily best-suited for and in any case cannot be viewed as the
responsibility of a single department, and b) cannot produce meaningful results in
the context of a ‘broken’ politics at the centre in Baghdad and a highly problematic
security environment. He plans to engage actively in the conversation about
what HMG’s ambitions on the economic front should be and the role of economic
development in relation to security and political reconciliation.”
516
Report Binns, 13 December 2007, ‘GOC MND(SE) Weekly Letter – 13 December 2007’.
512
Public hearing, 16 July 2010, page 3.
513
Public hearing, 16 July 2010, page 12.
514
Minute Hendrie to Wardell, 15 January 2008, ‘BTOR: Secretary of State Visit to Iraq,
515
11-12 December 2007’.
Email Hendrie to DFID [junior official], 14 December 2007, ‘Follow-Up to SoS Iraq Visit’.
516
338

---
10.2 | Reconstruction: July 2004 to July 2009
882. Mr Alexander sent Mr Miliband and Mr Browne an update on progress on
Mr Brown’s economic initiatives on 21 December.
 He advised that the success of the
517
Basra Development Forum was due in part to the reconciliation of Prime Minister Maliki
and Governor Waili, but also reflected:
“… years of often invisible effort in building up capacity of provincial government
to spend Iraqi resources for reconstruction and development … This is the right
approach – helping to set up Iraqi institutions to spend Iraqi resources, and it is
bearing fruit.”
883. Mr Alexander continued:
“My visit also confirmed that we cannot view economic development in isolation
from politics or security. They are inter-related and require an HMG-wide effort. We
should therefore guard against terminology that suggests a civilian or economic
surge will continue to be the driving force in determining Iraq’s stability and
prosperity … We need a conscious broadening of the effort across HMG, the
mechanisms for which need to be discussed; and we need to ensure that our civilian
and military plans for Iraq are co-ordinated. We also need to be clear about what we
are aiming to achieve.”
884. Basra province transferred to PIC on 16 December.
 All of the four provinces
518
within MND(SE) had now transferred to PIC.
885. Mr Brown met Prime Minister Maliki in the UK on 3 January 2008.
 On
519
reconciliation, Mr Brown said that he wanted to see rapid progress on the Hydrocarbons
Law and local elections. On economic reconstruction, he encouraged Prime Minister
Maliki to appoint Iraqi nationals to support Mr Wareing’s work. Prime Minister Maliki
replied that he would speak to Mr Salih; he also confirmed that he would double
Basra’s budget.
886. Lt Gen Rollo reported on 14 January that the Iraqi Minister of Finance had signed
off the first eight Japanese soft loans.
 The UK was working with the US Embassy
520
to ensure that the first loan, which covered Umm Qasr port, was taken forward
immediately. Lt Gen Rollo would continue to track the issue, but he remained of the view
that the “real answer” was a Basra Development Office in Baghdad.
887. The 16 January meeting of the ISG considered a draft strategy for Iraq.
521
Mr McDonald underlined the importance that Mr Brown attached to the economic
Letter Alexander to Miliband, 21 December 2007, [untitled].
517
BBC News, 23 March 2009, Timeline: UK Troops in Basra.
518
Letter Fletcher to Carver, 3 January 2008, ‘Prime Minister’s Bilateral with Prime Minister of Iraq,
519
3 January’.
Minute Rollo to CDS, 14 January 2008, ‘SBMR-I’s Weekly Report (283) 14 Jan 08’.
520
Minute Cabinet Office [junior official] to McDonald, 17 January 2008, ‘Iraq Strategy Group, 16 January’.
521
339

---
initiatives in Basra, and said that Mr Brown wanted to see “tangible progress in 2008 –
for example at the port or airport”.
888. Section 9.6 describes the development of the UK’s Short-Term Strategy for Iraq
between November 2007 and April 2008.
889. Ms Sue Wardell, DFID Director Middle East, said that a choice needed to be
made between maintaining current levels of effort during 2008 or “surging resources
temporarily”. The surge might focus on the agricultural sector, its links with the oil sector,
and regional trade.
890. Mr McDonald asked DFID to present options and recommendations to Ministers.
891. Lt Gen Rollo reported on 3 February that there had been “positive discussions”
with DFID in Basra on the deployment of additional experts to Basra and Baghdad to
support Mr Brown’s economic initiatives.
 He added:
522
“Given that the initiative was originally announced in early October 2007 it would
be good to see decisions in London to turn these into effect. General Petraeus’
enquiries into what hard measures are in place to support the PM’s words have
become pointed and public.”
892. Maj Gen Binns left MND(SE) on 12 February and was succeeded by
Major General Barney White-Spunner.
523
893. Reflecting on progress over the previous six months, Maj Gen Binns commented:
“It has taken me six months to develop an understanding of the Economic and
Political Lines of Operation. I have learned to measure economic redevelopment in
decades, to be patient, to listen to, and take the advice of, specialists in the PRT,
some of whom have been in Iraq for more than 3 years. We should stop beating up
on DFID; those, like me initially, who talk of ‘windows of opportunity’ and ‘economic
surges’ are misguided. Iraq is awash with money. The Iraqis need help in spending it
and overcoming corruption through good governance, which is exactly the approach
taken by our PRT. Of course we will continue to use CERPs money to buy consent
t
for military operations, but let us no
 pretend that this is sustainable development,
because on some occasions it is the reverse. In 10 years time Basrawis will
remember that the US Army Corps of Engineers built their Children’s Cancer
Hospital; they will probably have forgotten Operation SINBAD.”
894. In his formal end of tour report, Maj Gen Binns commented that co-operation
between departments in theatre was “superb”.
524
Minute Rollo to CDS, 3 February 2008, ‘SBMR-I’s Weekly Report 3 Feb 08’.
522
Minute Binns to CJO, 7 February 2008, ‘GOC MND(SE) Weekly Letter – 07 February 2008’.
523
Minute Binns to CJO, 12 February 2008, ‘Op TELIC – GOC 1 (UK) Armd Div Post Operation Report’.
524
340

---
10.2 | Reconstruction: July 2004 to July 2009
895. The ISG discussed a further draft strategy for Iraq on 14 February.
 Mr McDonald
525
again emphasised that Mr Brown was focused on achieving economic effect in 2008,
and that the UK should make every effort to do so in the limited time available.
896. On 18 February, Lt Gen Rollo reported that Gen Petraeus had asked to see
Mr Wareing during his upcoming visit to Iraq.
 The meeting would be a useful
526
opportunity to explain how the BDC would deliver on “what Petraeus sees as a British
commitment to kick-start the economy of the South”. Gen Petraeus believed that
campaign success in Iraq depended on the regeneration of the country’s economy.
897. Lt Gen Rollo assessed that the UK could do more to support Mr Wareing and,
by extension, economic development in the South. This included establishing a Basra
Development Office in Baghdad “to leverage US and Iraqi initiatives and work to remove
the many legal and political obstacles to investment in Basra”.
898. Mr Wareing made his first visit to Basra on 18 and 19 February, to participate in the
first meeting of the BDC.
 Maj Gen White-Spunner described the visit as “excellent”:
527
Mr Wareing had met Governor Waili and had had a genuine exchange of views with his
Iraqi colleagues at the BDC and key opinion formers. The BDC had agreed to produce
a Basra Economic Development Strategy by June 2008, with the aim of stimulating the
economy and fostering private sector development.
899. Mr Wareing was unable to travel to Baghdad to meet Gen Petraeus because of
bad weather.
528
900. Section 9.6 describes the deteriorating security situation in Basra from the end
of January, and the development by the Iraqi Government of plans to confront militias
in Basra.
901. Mr Alexander agreed on 20 February to increase DFID’s security headcount
limit (the number of staff allowed in post at any one time) from seven to nine for Basra
and from five to six for Baghdad.
 The new post in Baghdad would have specific
529
responsibility for facilitating the Basra economic initiatives. A DFID official advised that
the increase:
“… should be characterised as organising ourselves to give the Basra economic
initiatives the best chance of delivering in the shortest timeframe. It is not a ‘surge’
but nor is it business as usual.”
Minute Cabinet Office [junior official] to McDonald, 15 February 2008, ‘Iraq Strategy Group,
525
14 February’.
Minute Rollo to CDS, 18 February 2008, ‘SBMR-I’s Weekly Report (288) 17 Feb 08’.
526
Letter White-Spunner to CJO, 21 February 2008, ‘GOC MND(SE) Weekly Letter – 21 February 2008’.
527
Manuscript comment on Letter White-Spunner to CJO, 21 February 2008, ‘GOC MND(SE) Weekly
528
Letter – 21 February 2008’.
Minute DFID [junior official] to PS/Secretary of State [DFID], 20 February 2008, ‘Iraq: Delivering the
529
Basra Economic Initiatives’.
341

---
902. Mr Browne visited Kuwait and Iraq from 12 to 14 March in conjunction with
Mr Wareing.
 Mr Browne reported to Mr Brown that the mood in Iraq was optimistic,
530
reflecting the improved security situation, political progress and the new focus on
economic regeneration:
“Inevitably in Iraq, the pace of change is slower than we would wish and no-one
believes it is irreversible, but we have an opportunity over the next year or so
to contribute to a step-change in the country’s economy and to put our bilateral
relationship onto a sustainable long-term footing. That does, however mean we need
to redouble our efforts now … to exploit the progress we have already made.”
903. On the economic initiatives, discussions in Iraq had identified three areas where
the UK could do more:
reinforcing the UK team in Basra and Baghdad. Gen Petraeus thought that the
UK was “under-gunned”;
re-doubling the UK effort to unblock the investment and hydrocarbons
legislation, and to encourage international business to invest in Basra; and
a diplomatic initiative, with the US, to encourage a constructive partnership
between Basra and Kuwait.
904. Mr Browne commented that working alongside the US should help improve the
UK’s relationship with the US. Although Gen Petraeus had been polite during their
meeting, and also during his later meeting with Mr Wareing, he had previously been
critical of the scale of the UK’s non-military engagement in Basra.
905. The British Embassy Baghdad reported that Gen Petraeus had spelt out his
concerns in his meeting with Mr Wareing:
“In his [Gen Petraeus] view the UK had not been aggressive enough in trying
to achieve development change in Basra, and we needed to ‘increase our
horsepower’… He felt that the PM [Mr Brown] and the Foreign Secretary
[Mr Miliband] had promised much, but that he hadn’t seen much delivery … he
would make his concerns clear to the PM when he comes through the UK in April.”
531
906. The Embassy commented that Gen Petraeus wanted the UK to set up an office
in the Green Zone in Baghdad to promote Basra, and to increase the UK presence
in Basra.
907. Mr Alexander sent Mr Brown a further update on progress on the economic
initiatives on 31 March, in advance of the planned discussion of the UK’s Iraq Strategy
at the 1 April meeting of NSID(OD).
532
Letter Browne to Brown, 18 March 2008, ‘Visit to Baghdad and Kuwait’.
530
Telegram 10285/08 Baghdad to FCO London, 17 March 2008, ‘Michael Wareing to Baghdad,
531
14 March’.
Letter Alexander to Brown, 31 March 2008, [untitled].
532
342

---
10.2 | Reconstruction: July 2004 to July 2009
908. He advised that DFID had increased the number of full-time equivalent staff
working on the economic initiatives from four in January 2008 to 10. DFID would also
establish a Basra Support Office in Baghdad. DFID was recruiting internally to staff that
office, and was discussing with other departments including the FCO, the MOD and UK
Trade and Investment what role they could play. Mr Wareing had stated that this level of
staffing was “fully adequate” to deliver the initiatives.
909. In his evidence to the Inquiry, Mr Wareing highlighted three major successes within
the Basra economic initiatives:
the youth unemployment programme, which Prime Minister Maliki had
expressed interest in rolling out nationwide;
Basra International Airport and Umm Qasr port, where Mr Wareing had been
able to bring together the UK military, DFID and local Iraqi leaders; and
the establishment of the National Investment Commission and the Basra
Investment Commission.
533
910. Mr Keith MacKiggan, Head of the PRT from September 2008, told the Inquiry that
the economic initiatives had been “very effective”, as evidenced by:
the interest shown by the Iraqi Government in replicating the initiatives
country-wide;
the amount of investment that they attracted into Basra; and
the economic confidence that they had helped to engender.
534
Charge of the Knights, March 2008
911. On 25 March 2008, in response to growing concerns over the security situation in
Basra, Prime Minister Maliki launched a major offensive against Basra militias.
535
912. Section 9.6 considers the genesis and implementation of that military operation,
which came to be known as the Charge of the Knights, and the damage to UK-Iraqi and
UK-US relations.
913. Mr Browne reported to Cabinet on recent events in Basra on 1 April.
 He said
536
that the decision to launch the operation had come as a surprise to everyone. Mr Brown
said that Ministers would have a further discussion of the implications of recent events at
NSID(OD).
914. NSID(OD) met later that day, with Mr Brown in the chair, to consider the UK’s
“continuing role in Basra in 2008/2009, and the timelines and considerations for taking
Public hearing, 16 July 2010, page 55.
533
Public hearing, 7 January 2010, pages 22-23.
534
BBC News, 25 March 2008, Basra’s gun rule risks Iraq future.
535
Cabinet Conclusions, 1 April 2008.
536
343

---
decisions on force level options”.
 The meeting was provided with three papers: a
537
Short-Term Strategy, a draft of Mr Browne’s planned statement to Parliament , and
Mr Alexander’s letter to Mr Brown of 31 March on progress on the economic initiatives.
915. The Short-Term Strategy paper considered four options for drawing down UK
troops in Iraq, set out the civilian and military tasks that the UK could continue to
undertake in each case, and assessed the impact of withdrawing from Iraq on the
UK’s reputation.
538
916. The paper suggested criteria which might be used to evaluate those options, but
did not attempt such an evaluation and made no recommendation on troop withdrawals.
The criteria for evaluation included the ability to deliver Mr Brown’s economic initiatives
and the provision of a secure platform for political and economic work.
917. The paper also identified a number of areas in which the UK should continue to
work in the absence of a significant military presence in Basra. Those included:
Economics. In Baghdad, the UK had carved out a “niche role alongside the
massive US effort”. UK support for building Iraqi Government capacity for
economic policy and public finance/budget management was highly valued by
Iraqi officials and had given the UK a seat at the “coalition policy-making table”,
providing critical leverage to lobby for greater engagement by the World Bank
and other multilateral institutions. In Basra, Mr Brown’s economic initiatives were
making “real progress” under Mr Wareing’s leadership. The paper assessed the
work to be of high importance (because a successful economy was an important
driver of stability), but the UK’s impact to be “low to medium” (because of the
programme’s relatively small scale and the fact that real progress would depend
on the Iraqi Government).
Governance and security/justice sector reform. Both the US and the Iraqi
Government valued the UK’s work to build capacity in these areas. The work
was of medium importance (as DFID’s projects and the FCO policing mission
represented “niche added value”) and the UK’s impact “medium”.
Pressing for more substantive multilateral and regional engagement by the
UN, EU, IMF and World Bank. The work was of high importance (as more
substantive engagement by multilateral organisations would ease the burden
on the US and UK and positive regional engagement was crucial for Iraq’s
long-term stability) and the UK’s impact also “high” (as it had more leverage with
the EU, UN and World Bank than the US).
918. At the meeting, Mr Brown recognised that it was difficult to take firm decisions on
longer-term options until there was a clearer assessment of events in Basra
 It was
539
.
Paper Cabinet Office, 31 March 2008, ‘Iraq’.
537
Paper FCO, March 2008, ‘Iraq: The Short Term’.
538
Minutes, 1 April 2008, NSID(OD) meeting.
539
344

---
10.2 | Reconstruction: July 2004 to July 2009
good that the Iraqi Army had sought to take control, but the way in which it had done so
threatened to have a negative impact on political and economic progress, as well as the
security gains achieved by UK forces. The UK “could not afford to be perceived to be
irrelevant to the situation in Basra”.
919. Mr Browne said that there were now US forces involved in Basra, and they were
unlikely to leave.
920. Ministers agreed that troop levels should remain at 4,100 until the situation
became clearer and that no decision on longer-term military commitment should be
taken at present.
921. Concluding the discussion, Mr Brown said that hopes for political and economic
stability to take hold in Basra had been “set back”. The UK needed to wait and assess
the implications of events “but work to bring our political and economic objectives back
on line”.
922. The Iraqi Government and the US moved quickly to boost reconstruction in Basra
in the wake of the Charge of the Knights.
923. The UK was concerned that the wave of new money, the focus on short-term
projects, and the actions of central Government would undermine existing Provincial
Government structures and systems (which the UK had helped to establish).
924. Mr Prentice attended the Iraqi Ministerial Committee on National Security on
6 April, and reported that the Iraqi Government’s main priority was finding civilian
employment for 25,000 unemployed Basrawis.
 Acting Justice Minister Dr Safa al-Safi
540
had been appointed to co-ordinate the Iraqi Government’s economic efforts in Basra.
925. The British Embassy Office Basra reported on 7 April that a nine-strong US Civil
Military Operating Centre (CMOC) would arrive later that day, and would be operational
within 24 hours.
 The PRT had welcomed their arrival. The CMOC’s focus would be on
541
shorter-term employment schemes (“how to get young men off the payroll of JAM and
other militias”).
926. The British Embassy Office Basra reported the following day that it would be
important that the CMOC shared the UK’s philosophy that “we not do things for the
Iraqis, but with them”.
542
927. A DFID official in Baghdad reported to DFID colleagues on 9 April that the Iraqi
Council of Ministers had agreed to provide US$100m for economic work in Basra.
543
Dr al-Safi had arrived in Basra and had set up a number of committees. In parallel,
eGram 13078/08 Baghdad to FCO London, 7 April 2008, ‘Iraq: Ministerial Committee on National
540
Security, 06 April 2008’.
eGram 13086/08 Basra to FCO London, 7 April 2008, ‘Basra Update – 7 April 2008’.
541
eGram 13285/08 Basra to FCO London, 7 April 2008, ‘Basra Update – 8 April 2008’.
542
Email DFID [junior official] to DFID [junior official], 9 April 2008, ‘Basra’.
543
345

---
the US military was developing its own mass employment schemes and USAID was
considering what more it might do.
928. The official commented that it was possible that the US could “do things” that the
UK had not tried, as it could:
dedicate more people and more money to the task;
change the security environment to secure better civilian access;
operate outside Iraqi structures;
ensure better linkages to US work in Baghdad; and
“apply sufficient clout at the Baghdad end” to secure the Iraqi Government’s
attention.
929. The UK was lobbying the US on the need to engage with local government
and the PRT in order to avoid setting up parallel systems and losing the benefits of
local knowledge and experience. The key risk was that UK programmes (which were
designed to be Iraqi-led, and thus required a considerable amount of Iraqi engagement
and energy) would be “crowded out” as Iraqi counterparts focused on the larger and
more immediate US programmes.
930. A UK official in the Basra PRT agreed with that assessment and commented:
“None of this is going to stop and it is going to be a big distraction for a small PRT
team … trying to force the military to listen to what we have to say, and trying to stop
MNF taking over the show completely … It’s not just on the economic/governance
agenda – it’s the same for our CivPol mission and all the policing work we have
done …”
 544
931. In his weekly report of 10 April, Maj Gen White-Spunner described recent
events as:
“… a real opportunity for Basra and hence our involvement here. The time for any
recrimination … is behind us; we now have a better chance than we have arguably
had for two years to achieve better security and some initial development goals in
the city. We will not have long to do so …”
545
932. Dr Christian Turner, Cabinet Office Overseas and Defence Secretariat, sent
Mr Brown an assessment of the implications of the Charge of the Knights on 11 April,
in advance of Mr Brown’s visit to Washington.
 Dr Turner described the UK’s military
546
options (step up to take full responsibility for MND(SE), steady-state or an accelerated
withdrawal).
Email FCO [junior official] to Hendrie, 9 April 2008, ‘Basra’.
544
Minute White-Spunner to CJO, 10 April 2008, ‘GOC MND(SE) Weekly Letter – 10 April 2008’.
545
Minute Turner to Prime Minister, 11 April 2008, ‘Iraq: Implications of Basra Operations and US Visit’.
546
346

---
10.2 | Reconstruction: July 2004 to July 2009
933. Dr Turner also advised that the UK would need to redouble its effort on the
economy:
“Presentationally, the US effort risks overshadowing UK economic initiatives. The
likelihood is that the US will focus on quick impact projects … Funding will come
from the US military (up to US$70m) and the Government of Iraq (US$100m or
more).
“We will need to ensure our projects are co-ordinated and complementary.
Experience over the past five years in such [quick impact] projects is that they
provide short-term benefits, but are often not sustainable. DFID’s view remains that
economic recovery will require … a resolution to address the deep-seated problems
in the Basra economy and the building of sustainable Iraqi institutions … Our
message to the US will need to be that such work takes time.”
934. In his weekly report of 17 April, Maj Gen White-Spunner advised that MND(SE)
continued to focus on drawing as much US and Iraqi resource into Basra as possible in
order to take advantage of the “unexpected but very welcome changes” that the Charge
of the Knights had brought.
547
935. A DFID official provided a briefing for Mr Alexander on the impact of the Charge of
the Knights on 18 April.
 Street-life in Basra was “noticeably more confident”, with pop
548
music and alcohol on sale. Dr al-Safi had set up a committee to review project proposals
from the Provincial Council, the Governor and local Sheikhs, but had said that he did not
want proposals from the coalition. He was determined that the Iraqi Government should
be seen to be in charge and favoured quick impact projects focused on infrastructure,
implemented through line ministries and tribal leaders. On the US side, “large numbers”
of people were flowing into the US CMOC.
936. The major risk for the UK Government remained that the Provincial Government
would be undermined by the decision to channel funding through line ministries,
tribal leaders and NGOs. The UK continued to engage with the US and Dr al-Safi to
emphasise the advantages of engaging with the Provincial Government, the Provincial
Council and the PRT, rather than creating parallel systems.
937. Mr McDonald told the 28 April meeting of the ISG that: “It was now clear that there
was a shared UK/US operation in the South, and that we would need to decide on their
tasks and the division of labour.”
 The UK needed to focus on its remaining political,
549
economic and military tasks. The first two required provincial elections to take place,
and tangible outcomes from the work of Mr Wareing and the BDC.
Minute White-Spunner to CJO, 17 April 2008, ‘GOC MND(SE) Weekly Letter – 17 April 2008’.
547
Minute DFID [junior official] to Private Secretary [DFID], 18 April 2008, ‘Information Note: Latest
548
Consequences of Iraqi Operations in Basra’.
Minute Cabinet Office [junior official] to McDonald, 28 April 2008, ‘Iraq Strategy Group, 28 April’.
549
347

---
938. Mr Miliband visited Baghdad and Erbil in mid-April.
 He wrote to Mr Brown on
550
29 April:
“However unfortunate its genesis, Maliki’s operation in Basra has created an
opportunity to reshape our approach there and set a new direction towards
transition. 2009 is the year we will need to move from a Basra military strategy to
an Iraq political and economic strategy.”
939. The Iraqi Government was “for the first time since 2003” giving full attention
to Basra. In support of that, the US had committed “serious assets” to strengthen
MND(SE). Those combined US, UK and Iraqi resources would “accelerate the rate of
positive change in Basra”, paving the way for a “proper and respectable end” to the UK’s
role as “lead partner in the coalition” in the course of 2009.
940. Mr Miliband identified seven goals towards which substantial progress would need
to be made if the UK was to make that “final transition”, including:
“reconstruction clearly under way; sturdy green shoots of economic revival;
the BIPA and BDF [Basra Development Fund] well-established;
the airport on its way to be a development and business hub and transport hub;
Umm Qasr port better managed and with development plans in place”; and
the start of “a broad-based and natural relationship with the new Iraq, the ‘whole
Iraq policy’ which we have long wanted”.
941. Maj Gen White-Spunner reported on 1 May that:
“What is becoming increasingly evident, as our situational awareness improves, is
just what a poor state the city is in, with basic services non-existent in some areas
and a serious problem with raw sewage and mounds of rubbish on the streets.”
551
942. Mr Brown hosted a reception at No.10 on 28 April, to raise the profile of southern
Iraq as an investment destination and enhance Iraqi Government interaction with
potential investors.
552
943. Mr Brown was subsequently advised that between 25 and 30 companies, including
BP and Shell, had expressed a serious interest in exploring investment opportunities.
553
944. Mr Brown met Gen Petraeus and Ambassador Crocker in London on 1 May.
554
Mr Miliband, Mr Browne, Mr Alexander and senior officials attended.
Letter Miliband to Prime Minister, 29 April 2008, ‘Iraq’.
550
Minute White-Spunner to CJO, 2 May 2008, ‘GOC MND(SE) Weekly Letter – 1 May 2008’.
551
Minute Cabinet Office [junior official] to Prime Minister, 25 April 2008, ‘Basra Investors’ Reception,
552
No10: 28 April 2008’.
Minute Cabinet Office [junior official] to Prime Minister, 30 April 2008, ‘Iraq: Meeting with Petraeus and
553
Crocker, 1 May 2008’
Minute Cabinet Office [junior official] to Prime Minister, 30 April 208, ‘Iraq: Meeting with Petraeus and
554
Crocker, 1 May 2008’.
348

---
10.2 | Reconstruction: July 2004 to July 2009
945. The Cabinet Office briefing for Mr Brown stated that Gen Petraeus believed that
the UK should mount a civilian surge, and had advocated a more hands-on (rather
than Iraqi-led) approach. Dr al-Safi and Prime Minister Maliki had both recently told
UK interlocutors that they did not think UK-led economic development in Basra was
proceeding quickly enough. Dr al-Safi was “resistant” to UK lobbying in favour of
channelling Iraqi Government funds through the Provincial Government.
946. The DFID briefing for Mr Alexander stated that the US military was becoming
increasingly frustrated with the pace of the Provincial Government’s clear-up of the
streets after the fighting, and warned that the US might be tempted to take control of
the operation themselves.
 That would be a significant step backwards. The PRT was
555
trying to resist, but the pressure to make things happen was strong.
947. The briefing also advised that DFID feared that the Iraqi Government’s
reconstruction money was being used as a way of consolidating central Government or
Dawa party control over Basra. That would represent a patronage-based, unaccountable
way of managing Basra.
948. The Iraqi Army and MND(SE) were now in control of Umm Qasr port
(previously under militia control) and corruption and smuggling had ended. With the
improved security environment, it would be possible to return to US plans for the
commercialisation of the port.
949. Mr Brown’s meeting with Gen Petraeus and Ambassador Crocker covered a range
of political, security and economic issues (see Section 9.7).
556
950. At the meeting, Mr Alexander described the 28 April investors’ reception as a
success, and identified the development of the port and airport and the capacity of
central Government to support Basra as priorities.
951. Summing up the discussion, Mr Brown said that the central UK focus would be
accelerated training of Iraq’s 14 Division, preparations for provincial elections, progress
on handing control of Basra Airport to the Iraqis and economic reconstruction. Decisions
on troop numbers would be taken in the context of completion of these tasks.
952. The record of the meeting did not report any criticism by Gen Petraeus of the scale
or nature of the UK’s engagement on economic development.
953. Mr McDonald advised Mr Brown the following day that the UK would need to
retain around 4,100 troops in southern Iraq for the next six months to complete those
key tasks.
557
Minute DFID [junior official] to Private Secretary [DFID], 30 April 2008, ‘Briefing for Attendance at
555
PM/Petraeus meeting on 1 May’.
Letter Fletcher to Rimmer, 2 May 2008, ‘Iraq: Prime Minister’s Meeting with General Petraeus, 1 May’.
556
Email Fletcher to Brown, 2 May 2008, ‘Iraq Troop Numbers – Note from Simon’.
557
349

---
954. Mr Nick McInnes, UK Trade and Investment (UKTI) Director International Group,
briefed UKTI colleagues on 3 May that there was growing pressure from the British
Embassy Baghdad and the MOD for a larger UKTI presence in Baghdad.
 Their
558
arguments for that were:
the increased interest in Iraq from UK companies;
the likelihood that Mr Brown’s economic initiatives would stimulate further
interest; and
the possibility of sales of UK military equipment to Iraq.
955. Section 10.3 describes the UK Government’s efforts to promote UK businesses.
956. In an Assessment of 14 May, the JIC examined the impact of the Charge of the
Knights on JAM, Prime Minister Maliki, his Government and the Sadrists.
 The JIC’s
559
Key Judgements included:
Prime Minister Maliki was enjoying broad political support following the success
of the Charge.
The Charge had significantly weakened JAM in Basra.
In Basra, expectations were high. Prime Minister Maliki would need to deliver
improvements in public services and job creation “in weeks”.
957. Mr Browne visited Iraq briefly, on his way to Afghanistan, at the end of May,
where he “realised a personal ambition by having a cup of tea downtown”, the result of
“a remarkable transformation of the security situation”.
560
958. A DFID official briefed Mr Alexander on 30 May that, following Mr Browne’s visit
to Iraq, there were growing expectations among some military colleagues that UK
civilians would soon be able to travel “beyond the wire” (outside Basra Air Station).
561
Visits to Basra Palace by PRT and DFID staff were currently being undertaken at night,
by helicopter, and were approved on a case-by-case basis. The situation was not yet
good enough to enable PRT and DFID staff to visit Iraqi Government offices on a regular
basis, but DFID would keep the situation under review.
959. Ms Reid told the Inquiry that shortly after the Charge of the Knights, Dr al-Safi
agreed to meet UK officials but not at the Basra Air Station:
“That basically forced a decision … It [the meeting] was something that was so
important … there was so much pressure coming from Baghdad and from London,
that we need to go and have this discussion with him. And at that point … authority
for me to go went back to my Permanent Secretary to get the okay, because it was
Email McInnes to Haird, 3 May 2008, ‘Resourcing Commercial Work in Iraq’.
558
JIC Assessment, 14 May 2008, ‘Iraq: the Charge of the Knights’.
559
Letter Browne to Brown, 4 June 2008, ‘Visit to Basra’.
560
Minute DFID [junior official] to PS/Secretary of State, 30 May 2008, ‘Iraq: Ministerial Trilateral
561
Discussion, 2 June 2008’.
350

---
10.2 | Reconstruction: July 2004 to July 2009
turning around something that had been in place for so long and there was so much
nervousness about it.
“What that did was started a discussion which was the default can’t necessarily
remain …
“So by the time I left in October [2008], decisions on moves to the Palace could be
made by the head of DFID Baghdad. They didn’t have to go back through a lengthy
chain in London. Decisions on some other road moves would still go through my
boss back in London, but gradually that got moved more and more to theatre,
became much more like the Baghdad experience of Red Zone moves.”
562
960. The 2 June meeting of the ISG focused on economic development.
 Ms Aldred
563
said that “economic deliverables” would form a core part of the narrative that Mr Browne
had asked for following his visit to Basra, and asked DFID to lead on compiling it.
Mr McDonald said that Mr Brown would want to announce economic progress – or, at
the very least, a Basra economic plan – in his planned Parliamentary statement in July.
961. Ms Hendrie reported that Dr al-Safi was making little progress in spending the
Iraqi Government’s reconstruction funds for Basra and that, despite UK lobbying, he
remained reluctant to use established structures. The Basra Support Office in Baghdad
would become operational on 7 June. UKTI had expressed interest in appointing a First
Secretary (Commercial) to Baghdad, but was reluctant to fund or staff the post.
962. A 9 June Current Intelligence Group (CIG) Assessment of Basra’s economy,
commissioned by DFID, judged that the Charge of the Knights had secured “a window
of opportunity to create the conditions for economic growth” but that reconstruction and
development would continue to be constrained by:
the absence of any systemic approach to project and financial management
within the Iraqi Government;
competing political agendas, which meant that reconstruction was subject to
“political manoeuvring”;
corruption, which would remain endemic under the present Government or any
likely successor;
the uncertain legislative environment, which continued to hold investors back.
International oil companies were in negotiation with the Ministry of Oil but they
were unlikely to make long-term investments until a Hydrocarbons Law had
been adopted;
security, which remained fragile;
crime and smuggling; and
Public hearing, 24 June 2010, pages 66 and 67.
562
Minute Cabinet Office [junior official] to McDonald, 2 June 2008, ‘Iraq Strategy Group, 2 June’.
563
351

---
a “brain drain”. Militia violence and intimidation, which specifically targeted
middle-class Basrawis, had prompted many to leave, resulting in a shortage
of capable local entrepreneurs.
564
963. DFID deployed an aviation industry consultant to Basra International Airport on
11 June, with the long-term aim of achieving “international certification” within two
years.
 In the shorter term, the consultant aimed to raise the capacity of the airport
565
from four or five to 15 flights per day.
964. Ms Hendrie and Mr Donal Brown, her successor as DFID Deputy Director Iraq,
visited Iraq from 13 to 22 June.
 Their report to Mr Anderson and DFID colleagues
566
focused on what could be done in the next 12 months (while there was likely still to be
a significant UK military presence) which would constitute “a reasonable package of
‘deliverables’” in Basra. Components of that package included:
Basra International Airport. There was “some confusion” over what the UK
could deliver. International Civil Aviation Organisation (ICAO) accreditation was
done at a country level rather than for an individual airport (so the UK could not
hand over an accredited airport). Support for the airport was a joint DFID/MOD
responsibility.
Completion of Pumping Station 2 and the water towers. The last two of DFID’s
infrastructure projects in the South, their completion would “go some way toward
demonstration that the UK has done something for the people of southern Iraq”.
Mr Brown’s economic initiatives.
The PRT’s economic and governance work. The Cabinet Office and MND(SE)
wanted a youth employment programme.
965. Ms Hendrie and Mr Donal Brown commented that it was “important that the Head
of the PRT has sufficient time allocated [to leading the PRT] alongside her expanding
political work as Deputy CG [Consul General]”.
966. Gen Dannatt visited Basra at the end of June, reporting a “very positive mood
within MND(SE) and a real sense that we may actually be able to deliver success,
although within a realistic timeframe”.
 He remained “unconvinced that the PRT
567
in Basra is demonstrating enough energy, purpose and drive to be able to deliver
meaningful results in the timeframe we require”.
967. Mr McDonald told the 3 July meeting of the ISG that Mr Brown’s statement
to Parliament could highlight three key objectives for the next six months: training
14 Division; successful provincial elections; and handing over Basra Airport to civilian
CIG Assessment, 9 June 2008, ‘Iraq: Basra’s economy’.
564
Minute Hall to PS/Secretary of State [DFID], 30 May 2008, ‘Iraq: Ministerial Trilateral discussion,
565
2 June 2008’.
Minute Hendrie and Brown to Anderson, 27 June 2008, ‘Iraq BTOR – 13
– 22
 June 2008’.
566
th
nd
Minute CGS to various, 4 July 2008, ‘CGS Visit to Iraq and Cyprus – 30 Jun-2 Jul 08’.
567
352

---
10.2 | Reconstruction: July 2004 to July 2009
control.
 An FCO official cautioned against exaggerating Basra Airport’s success –
568
flight numbers had been dropping.
968. NSID(OD) met on 15 July, to discuss a paper prepared by Cabinet Office officials
on UK strategy in Iraq 2008/2009.
569
969. A DFID official briefed Mr Alexander in advance of the meeting that:
Dr al-Safi was drawing the BDC into “party political wrangling”, questioning the
validity of its constitution and the UK’s role in relation to it. Prime Minister Maliki
had recently said that the BDC was “colonialist inspired”.
Meanwhile, the BDC was drawing up a Basra Economic Development Plan
which “in practice … will be based on Wareing’s own ‘Key Goals’ document”.
Dr al-Safi claimed to have allocated US$100m to 200 projects in Basra and to
have hired 15,000 people for public works, but there was little evidence of that
on the ground. DFID was lobbying for the funds to be spent through “transparent
channels”.
“Partners” had raised concerns about the capacity of the Basra PRT. The Deputy
Consul General in Basra also headed the PRT and was “overloaded”. DFID was
working closely with the FCO to improve the capacity of “this FCO-led team”.
570
970. A separate DFID briefing for Mr Alexander stated that Mr Wareing had identified
four issues as “critical” to UK success in Basra:
Basra International Airport. The UK needed to “define objectives for success”
and clarify responsibility within the UK Government for delivery.
UKTI support for the Basra Support Office in Baghdad. UKTI had declined to
fund a post.
Improving the performance of the Basra PRT. The US had suggested that it was
under-performing compared with other PRTs.
Improving Iraq/Kuwait economic ties.
571
971. The DFID briefing also stated that there was:
“… a continuing view amongst some Iraqi politicians (i.e. Dr al-Safi and – to a lesser
extent – Prime Minister Maliki) … that reconstruction and development work is not
proceeding fast enough to capitalise on improved security. We are working through
the Basra Support Office in Baghdad and the PRT … to counter these views …”
Minute Jones to McDonald, 7 July 2008, ‘Iraq Strategy Group, 3 July’.
568
Paper Cabinet Office Officials, 11 July 2008, ‘Iraq’.
569
Minute DFID [junior official] to PS/Secretary of State [DFID], 3 July 2008, ‘Information Note: Update
570
for the Secretary of State’.
Email DFID [junior official] to PS/Secretary of State [DFID], 11 July 2008, ‘Iraq Ministerial Trilateral
571
14 July – Briefing’ attaching Briefing DFID, [undated], ‘Iraq (Trilateral) – 14 July’.
353

---
972. Cabinet Office officials invited Ministers to agree that the UK’s key tasks for
2008/2009 should be:
“
training and mentoring the Iraqi Army’s 14 Division, until it is capable of
independent operations with minimal Coalition support – expected in about
April 2009;
supporting provincial elections, due by the end of 2008; and
supporting economic development in Basra, based on Michael Wareing’s outline
Economic Development Strategy.”
572
973. Officials also invited Ministers to agree that the UK should continue to press for
passage of the Hydrocarbons Law.
974. Officials assessed that Basra’s economy was gaining momentum. Since the
No.10 reception on 28 April, foreign investors had begun to pursue projects with a
potential value of US$4.3bn. The UK had helped Basra Provincial Council to secure
US$400m from central Government for the current year. However, the UK was still
being criticised for not doing enough and local politics was slowing economic progress,
including on the Basra Development Fund and BIPA. The UK needed a focused effort
to deliver and demonstrate UK achievements by early 2009, based on the Economic
Development Strategy being developed by Mr Wareing and the BDC.
975. At the meeting, Mr Alexander reported on Mr Wareing’s draft Economic
Development Strategy.
 Mr Wareing was optimistic: four major companies were already
573
examining investment opportunities in Basra.
976. Concluding the discussion, Mr Brown welcomed the opportunity that his 22 July
statement would provide to set out UK policy publicly. The UK’s key goals for the year
ahead should be to:
push for early provincial elections;
hand over Basra Airport by the end of 2008;
produce an economic plan shortly; and
complete training of 14 Division by the end of May 2009.
977. Mr Brown met Prime Minister Maliki in Iraq on 19 July.
 Prime Minister Maliki
574
gave an upbeat account of progress: IDPs were returning to their homes, children
were returning to school, 650 doctors had returned from abroad and many university
professors were returning to work. There were improvements in the economy,
infrastructure and oil production and factories were working again.
Paper Cabinet Office, 11 July 2008, ‘Iraq’.
572
Minutes, 15 July 2008, NSID(OD) meeting.
573
Letter Fletcher to Hickey, 19 July 2008, ‘Prime Minister’s Meeting with Prime Minister Maliki, 19 July’.
574
354

---
10.2 | Reconstruction: July 2004 to July 2009
978. Mr Brown underlined the UK’s wish to help on key issues, including Basra port,
oil and the steel industry. Mr Brown said that UK forces would not stay longer than was
necessary to “finish the tasks we had started”, specifically:
training 14 Division;
preparing to make Basra Airport operational; and
supporting local authorities with provincial elections.
979. Mr Brown also visited Basra.
 His programme focused on SSR, although he also
575
visited Basra Airport and met key economic figures. The British Embassy Office Basra
reported that Mr Brown was “particularly struck by the need for rapid development of
the airport and ports”.
980. Mr Brown told Cabinet on 22 July that the UK was pursuing four key functions
with Iraq:
UK forces had moved from a combat to an overwatch role. UK troops’ primary
role was training and mentoring Iraqi forces, with a last resort intervention
capability, though that was also gradually being taken over by Iraq.
Pursuing economic development, which was showing some evidence of
success, providing Iraqi citizens with work and a stake in their future.
Local government elections would give former members of the militia the
opportunity to engage in democratic politics.
Working to transfer Basra International Airport from military to civilian control.
576
981. Mr Brown said that the BDC would produce an economic plan in the autumn and
he hoped that local elections would take place by the end of the year; likewise the
handover of Basra Airport. Training of 14 Division should also be completed by the end
of the year, with additional training of headquarters and specialist functions required in
early 2009. Mr Brown “expected that we would be able to make substantial reduction in
the number of British forces next year, but that would depend on circumstances. He was
not going to make an estimate of the numbers now.”
982. Mr Brown concluded that if the UK had left Iraq a few months earlier, the job would
not have been finished; with the improvements in security, momentum for economic
development and a move towards local democracy once the elections were held, the
Iraqi people now felt that they had a stake in the future.
983. In his statement to Parliament on 22 July, Mr Brown described the impact of the
UK’s reconstruction effort:
“British-led” projects in the South had helped to deliver electricity for
800,000 people and water for over one million people.
eGram 28460/08 Basra to FCO London, 20 July 2008, ‘Iraq: Prime Minister’s Visit to Basra, 19 July’.
575
Cabinet Conclusions, 22 July 2008.
576
355

---
UK funding had helped the UN and World Bank to repair and re-equip
1,000 health centres and more than 5,000 schools, and to train nearly
150,000 teachers.
With British training and equipment, Basra International Airport was now
handling more than 20 flights a day.
British mentoring and support had helped the Basra Provincial Council access
US$400m in central Government funds.
577
984. Mr Brown stated that it was right that the UK completed the tasks it had set itself.
It expected the BDC to publish a detailed Economic Development Strategy in the
autumn, and for the Iraqi authorities to “take over development” of Basra International
Airport by the end of the year.
985. Major General Andrew Salmon took up post as GOC MND(SE) in August 2008.
578
986. Mr Nigel Haywood, UK Consul General in Basra from April 2008, told the Inquiry
that:
“When [Major] General Salmon and I jointly went to call on the Governor in his office
in August, that was the first time anybody had called on the Governor’s office for two
years, nobody had been out really operating in the town [since] October 2006.”
579
987. On 24 August, in his first weekly report from Basra, Maj Gen Salmon reported that
he was having “very positive” discussions with the PRT on how to enable the movement
of civilian staff.
 He was also developing with the Consul General a “realistic six to nine
580
month programme of works that will deliver tangible effects, based on Iraqi need”.
988. In his next weekly report, Maj Gen Salmon advised that:
“… the inability of central and provincial government to translate cash into essential
services, jobs and electricity could become a central security issue. A re-oriented
reconstruction strategy accompanied by imaginative information operations should
help mitigate this risk.”
581
989. Maj Gen Salmon also reported that Basra needed a “Business Support Facility” to
cater for the expected rush for potential investors to Basra as security improved: “The
investor phenomenon is accelerating exponentially.”
House of Commons, Official Report, 22 July 2008, column 661.
577
Public hearing, 20 July 2010, page 1.
578
Public hearing, 7 January 2010, page 7.
579
Minute Salmon to CJO, 24 August 2008, ‘GOC MND(SE) Weekly Letter – 24 August 2008’.
580
Minute Salmon to CJO, 31 August 2008, ‘GOC MND(SE) Weekly Letter – 31 August 2008’.
581
356

---
10.2 | Reconstruction: July 2004 to July 2009
990. The Stabilisation Unit (formerly the Post-Conflict Reconstruction Unit – PCRU)
undertook a review of the Basra PRT in August, at the request of the FCO. The aim of
the review was to:
assess whether the PRT’s objectives remained valid in the light of developments
since the Charge of the Knights; and
evaluate the PRT’s performance.
582
991. The “primary purpose” of the review was to ensure that the PRT functioned to its
full potential and delivered “tangible and sustainable benefits” over the next 12 months.
It seemed likely that the PRT would not exist in its current form once British troop levels
reduced in early or mid-2009, and that the US would take over the PRT at that time.
992. The Stabilisation Unit review reported that while all PRTs in Iraq were constrained
by insecurity and a lack of Iraqi capacity, the Basra PRT faced a number of additional
challenges:
“… a part-time leader since January 2007, a dysfunctional structural legacy, limited
resources, and an absence of a long-term strategy due to uncertainty over its future
ever since its creation in April 2006.”
993. Given those constraints, the Basra PRT had performed well in some areas, in
particular in securing Provincial Council ownership of the Provincial Development
Strategy and building Iraqi capacity on budget planning and execution. The PRT had
also responded well to reconfigure itself to support Mr Brown’s economic initiatives.
994. It was, however, clear that the PRT was not performing as well as it could.
It also needed to respond to the priorities set out in Mr Brown’s 22 July statement
to Parliament.
995. The Stabilisation Unit made 26 recommendations, of which one was highlighted
in the review’s Executive Summary: the appointment of a full-time Head for the PRT.
The Stabilisation Unit assessed that while the decision in 2007 to double-hat the
Deputy Consul General as the Head of the PRT had been reasonable, the increased
expectations on the PRT in the light of the improved security situation and from the
US, and the increased willingness of Iraqi citizens to meet members of the PRT both
on and off Basra Air Station, meant that “the PRT and PRT Head … could and should
be busier”. The double-hatting arrangement had led the US to express concern that
the UK did not attach sufficient importance to the Basra PRT, and that the PRT was
too concerned with delivering UK as opposed to coalition goals. The Stabilisation Unit
concluded that the arrangement was no longer credible.
996. Maj Gen Salmon reported on 7 September that, together with Mr Haywood and
the Head of the PRT, he had launched a re-orientated reconstruction programme with
Report Stabilisation Unit, 3 September 2008, ‘Review of the Basra Provincial Reconstruction Team’.
582
357

---
an initial focus on electricity, water, rubbish and sewage, designed to deliver tangible
improvements in essential services and create jobs.
 Resources would come from the
583
US CMOC and the PRT, and delivery would be through task-based Joint Reconstruction
Action Teams (JRATs). The JRATs would be under joint civilian-military leadership (each
having a military head and civilian deputy head or vice versa), and would work with the
appropriate Iraqi authorities.
997. Mr Keith MacKiggan arrived in Basra in late September 2008 to take up post as the
Head of the Basra PRT.
 His arrival signalled the end of the practice of double-hatting
584
the Head of the PRT and the Deputy Consul General. He described the situation in
Basra at that time:
“We were able to get out to meet … clients, NGOs, officials in the local
administration, local businesses and so on. Equally importantly, they were able to
come and visit us because they no longer felt the fear they had previously of being
associated with the Multi-National Force.
“It also meant that we could expand our capacity building work, both in a
geographical sense and also in a functional sense … we were now much more able
to get beyond the city [Basra] to the furthest reaches of the province … and dig
below the level of the Provincial Council to the level of the local Councils and really
start to stitch the different parts of the governance structures in Basra together.”
998. In their evidence to the Inquiry, Maj Gen Salmon, Mr Haywood and Mr MacKiggan
agreed that the UK effort in Basra was well integrated during their time there.
585
999. Maj Gen Salmon told the Inquiry that that integrated approach had emerged in the
context of clear UK objectives (as set out in Mr Brown’s 22 July statement to Parliament)
and a timetable for withdrawal, but in the absence of an overall UK strategic plan agreed
in London.
586
1000. Maj Gen Salmon described how the move to a more integrated approach had
been driven by decisions in Basra:
“Well, we had a set of objectives. There was no comprehensive strategic plan that
I ever saw. So what we decided to do – when I say ‘we’, that is the Consul General,
the Head of the Provincial Reconstruction Team … and to a certain extent the Head
of US Regional Embassy Office … [was] ensure that we had much more collective
consensus, joined-up approach, because nobody was in charge.
“So that was the only way that we could think of working out what the strategy
needed to be and how we were going to prosecute that strategy, run it, steer it,
Minute Salmon to CJO, 7 September 2008, ‘GOC MND(SE) Weekly Letter – 7 September 2008’.
583
Public hearing, 7 January 2010, pages 1, 10-11.
584
Public hearing, 7 January 2010, page 6; Public hearing, 20 July 2010, page 24.
585
Public hearing, 20 July 2010, page 24 and 32.
586
358

---
10.2 | Reconstruction: July 2004 to July 2009
effectively. So we basically got together and decided that’s what we were going to
do and worked it from there.”
587
1001. Maj Gen Salmon told the Inquiry that JRATs were one expression of that
integrated approach, combining personnel from the PRT and MND(SE) working to a
“common plan”.
588
1002. Lieutenant General Peter Wall, Deputy Chief of the Defence Staff (Commitments),
updated the 11 September meeting of the ISG on the emerging plan for UK military
drawdown and transition to US command in southern Iraq.
 He said that:
589
At the end of November 2008, command of Maysan, Muthanna and Dhi-Qar
provinces would transfer to an expanded MND(C), under US command.
At the end of March 2009, command of Basra would transfer to a new
Basra-based US division, bringing UK forces there under US command.
At the start of May 2009, US forces would begin to deploy to Basra.
By the end of June 2009, the UK departure would be complete.
1003. Mr Brown and Mr Browne met the Chiefs of Staff and Sir Bill Jeffrey, MOD
Permanent Secretary, on 18 September.
 ACM Stirrup reported that “remarkable
590
progress” had been made in Iraq over the past 18 months, though it was “fragile and
reversible”. In the South, the biggest risk was stalled economic progress.
1004. Mr Brown said that it would be important to have projects that helped with
employment in place before the UK left Basra, and to establish a UKTI presence there.
The main obstacle was not security but the business climate.
Transition to a normal bilateral relationship with Iraq
1005. Mr Alexander visited Baghdad and Basra on 6 November.
 The British Embassy
591
Baghdad reported that, in his meeting with Mr Alexander, Prime Minister Maliki had
continued to insist that the UK had done little for Basra, and questioned whether the
Basra Development Forum had led to any tangible progress. Prime Minister Maliki
welcomed Mr Alexander’s assurances that the UK wanted to move towards a more
normal bilateral relationship including closer economic, cultural and educational links.
1006. Mr Alexander also met Ambassador Crocker. The two men agreed that the US
would take over the leadership of the Basra PRT as part of the UK/US transition in Basra
Public hearing, 20 July 2010, pages 27-28.
587
Public hearing, 20 July 2010, pages 34-35.
588
Minute Cabinet Office [junior official] to McDonald, 15 September 2008, ‘Iraq Strategy Group,
589
11 September’.
Letter Catsaras to Rimmer, 18 September 2008, ‘Prime Minister’s Meeting with Defence Chiefs,
590
18 September’.
eGram 45112/08 Baghdad to FCO London, 12 November 2008, ‘Iraq: Visit by Secretary of State for
591
International Development to Baghdad and Basra, 6 November’.
359

---
in 2009. Ambassador Crocker said that the US would value some continued UK support
in a US-led PRT.
1007. Mr Alexander and Ambassador Crocker also agreed that the World Bank should
be lobbied “at the highest levels” to increase its presence in Iraq.
1008. The Embassy also reported that Mr Alexander had set out DFID’s plans to
withdraw from Basra in mid-2009 and move to a “whole of Iraq” approach, delivered
through support to central Government, in line with Prime Minister Maliki’s wishes.
1009. In Basra, Mr Alexander attended the launch of the Basra Investment Commission –
formerly known as the Basra Investment Promotion Agency (BIPA).
1010. The 7 November meeting of the ISOG discussed a draft post-drawdown strategy
(in advance of an NSID(OD) discussion the following month).
 The meeting asked for
592
departments to take action on a number of issues, including:
“DFID to consider whether a presence only in Baghdad supported by a
communications strategy and programme funding in the south, would be sufficient to
sustain our legacy there, protect our reputation and ensure the US did not win credit
for progress that we had engineered.”
1011. Mr Alexander wrote to Mr Brown on 20 November to provide an update on
progress in Basra and to set out how he saw DFID’s role changing in the context of the
UK’s “change of mission”.
593
1012. He reported that DFID had already facilitated 18 investor visits by 14 companies,
with proposals worth over US$9bn submitted to, but not yet processed by, the Iraqi
Government. The Iraqi Government’s inability to process those proposals was the main
obstacle to international investment in Basra.
1013. DFID’s infrastructure projects would be completed by the end of 2008, and its
work with the Basra provincial administration would come to a “natural conclusion”
by mid-2009. The key to achieving a positive legacy for the UK was securing
inward investment. Given that the key obstacles to such investment were in central
Government, DFID would focus its effort there. That was in line with Prime Minister
Maliki’s wish for the UK to support the whole of Iraq, not just Basra.
1014. Mr Wareing visited Basra in late November, to launch the Basra Economic
Development Strategy.
594
Minute Cabinet Office [junior official] to Aldred, 10 November 2008, ‘Iraq Senior Officials Group,
592
7 November’.
Letter Alexander to Brown, 20 November 2008, [untitled].
593
Minute Cabinet Office [junior official] to Prime Minister, 28 November 2008, ‘[redacted] Iraq: Update’.
594
360

---
10.2 | Reconstruction: July 2004 to July 2009
1015. Mr Brown met ACM Stirrup on 4 December for a “personal and confidential”
discussion.
 On Iraq, Mr Brown said that it would be important for the UK to show
595
that the withdrawal of UK troops was happening because the UK had completed all
the tasks it had set out. A “last push” on economic development was needed, along
with a communications plan for the next few weeks.
1016. The 9 December meeting of NSID(OD) discussed a Cabinet Office paper
on arrangements for transition in Iraq.
 The paper, which is considered in detail in
596
Section 9.7, included an annex listing the components of the UK’s future bilateral
relationship with Iraq and how they would be resourced. In addition to the diplomatic/
political and defence relationships, the components were:
“Economic/development: Influence Iraqi economic policy, including improving the
climate for foreign investment, help improve World Bank and IMF engagement
in Iraq, capacity-building on public finance management, continued support
for the Prime Minister’s [Mr Brown’s] economic initiatives and support to other
departments’ work on investment, trade and higher education.” Work would be
funded from DFID’s existing Iraq programme (£20m in 2009/10 and £10m in
2010/11) and, potentially, from the Stabilisation Aid Fund. Staffing levels would
be established according to programme needs, with all in-country staff based
in Baghdad.
“Energy: ensure security of Iraq’s oil supply and long-term increase in oil output
through political lobbying on hydrocarbons legislation and national energy policy
and regional support.” Work would be undertaken primarily by FCO staff.
“Commercial: support for trade missions, UK investor visits and political lobbying
to ensure a level playing field for UK experts/investors.” A new, short-term
International Business Specialist would provide recommendations in early 2009
on exactly what resources were needed.
“Educational: increased collaboration with Iraqi educational institutions, civil
society, student exchanges and English language training, to be funded by the
British Council.”
1017. At the meeting, Mr Brown outlined “strong progress” on the UK’s four key tasks
(training the Iraqi Army, promoting economic development, readying Basra Airport for
transfer to Iraqi control and preparing for provincial elections).
597
1018. Mr Brown concluded that more should be done to improve economic development
and prospects for investment, including with ministries in Baghdad.
A visit by Lord
Mandelson, Secretary of State for Business, Enterprise and Regulatory Reform, would
be welcome. It would also be important to make progress with the Hydrocarbons Law.
Letter Catsaras to Rimmer, 4 December 2008, ‘Prime Minister’s Meeting with Chief of Defence Staff,
595
4 December’.
Paper by Cabinet Office Officials, 8 December 2008, ‘Iraq: Arrangements for Transition’.
596
Minutes, 9 December 2008, NSID(OD) meeting.
597
361

---
Mr Brown would raise those points with Prime Minister Maliki when he visited Iraq later
in the month.
1019. NSID(OD) agreed that agreement to the UK’s new Long-Term Strategy for Iraq
would be sought out of committee.
1020. Following the NSID(OD) meeting, and in advance of Mr Brown’s visit to Iraq, a
DFID official wrote to No.10 detailing four investment proposals, together worth over
US$5bn, which were currently awaiting agreement from the Iraqi Government.
 The
598
letter did not state why there had been a delay in agreeing the proposals.
1021. Mr Brown met Prime Minister Maliki in Baghdad on 17 December.
 Prime
599
Minister Maliki repeated his call for a wider long-term relationship, including investment
and economic co-operation, and stronger cultural and educational links. He added
that UK companies should invest in all Iraq, not just Basra. Mr Wareing briefed Prime
Minister Maliki separately on the main investment proposals for Basra and handed over
DFID’s letter detailing the investment proposals awaiting an Iraqi Government response.
1022. Mr John Tucknott, Deputy Head of Mission British Embassy Baghdad from
November 2007 to July 2009, described the change in the UK’s relationship with Iraq
and the challenge it presented to the UK Government:
“I think Basra remained important … but the messaging that was coming out of
London, which we were conveying to the Iraqis, was that we wanted to move, and
this was the message that Gordon Brown gave to Maliki in December 2008 when
he visited. You know, we are talking about a whole Iraq policy now. We want to do
things with you which we haven’t been able to do before. We want to move on to a
proper footing … a less military footing.
“The problem that we had in the Embassy was persuading some parts of Whitehall,
some Government departments, to recognise that we were moving to this, that we
wanted to increase trade, that it was important that visas were issued to students.
Part of Prime Minister Maliki’s education scheme was to send 10,000 postgraduates
or undergraduates to go to overseas universities to study. We need to provide a
proper visa regime, not the one that we cobbled together.
“So that was a difficulty we faced, actually getting that message out to the wider
Whitehall machinery, that Iraq is moving forwards, and if we want to play an
important role in this process, we had to move with it.
“Messages did get through in the end. We have got a trade and investment section
now … poor old DFID were doing their best in their absence …”
600
Letter DFID [junior official] to Fletcher, 12 December 2008, [untitled].
598
Letter Catsaras to Gould, 18 December 2008, ‘Prime Minister’s Meeting with Iraqi Prime Minister,
599
17 December’.
Public hearing, 24 June 2010, pages 116 and 117.
600
362

---
10.2 | Reconstruction: July 2004 to July 2009
1023. Section 10.3 describes the growing pressure on UKTI from spring 2008 to post
a Commercial Officer to Baghdad, in response to the increased interest in Iraq from
UK companies.
1024. Mr Brown’s Assistant Private Secretary wrote to Mr Richard Abel, Mr Mandelson’s
Principal Private Secretary, on 18 December informing him that Mr Brown believed,
following his visit to Iraq the previous day, that there were opportunities in Iraq and
interest from British companies that were not being exploited.
 Mr Brown was
601
convinced that there was an urgent need for a significant UKTI presence in both
Baghdad and Basra, both to consolidate security gains and to ensure that UK investors
had every chance to benefit from commercial opportunities in Iraq. Mr Brown asked
UKTI to start planning immediately for a long-term presence in Iraq, consulting
Mr Wareing and DFID.
1025. Mr Abel replied to No.10 on 16 January 2009, advising that an International
Business Specialist would deploy to Iraq later that month and would make
recommendations on UKTI’s future footprint in Iraq by the end of March.
 Mr Abel
602
added: “There will be no gap in our commercial representation in Iraq.”
1026. The International Business Specialist arrived in Baghdad at the end of January.
603
He was joined by a second UKTI consultant on 12 February.
604
1027. Iraqi authorities took control of Basra Airport in January 2009; transferring
control of the airport by the end of 2008 had been one of the UK’s key goals for 2008.
903 Expeditionary Air Wing had operated Basra Airport since 2003.
605
1028. Mr Brown was informed on 14 December 2008 that the transfer of control
was “effectively completed”.
 Since July, the Iraqi civil authorities at Basra Airport
606
had taken on control of air-traffic control, the airport fire brigade, and other services.
The final stage would be a formal transfer of legal responsibility for Basra Airport to
the Iraqi Government.
1029. Control of Basra Airport was formally transferred to the Iraqi Government on
1 January 2009.
607
1030. During the period that Basra Airport was operated by the UK military, it received
significant funding from a variety of military and civilian sources (including US
CERPs and the UK’s Stabilisation Aid Fund). The Inquiry has not been able to form
Letter APS/Prime Minister to Abel, 18 December 2008, ‘UKTI presence in Iraq’.
601
Letter Abel to Catsaras, 16 January 2009, untitled.
602
Report DFID, 1 February 2009, ‘Weekly Update: 1
 February 2009’.
603
st
Report DFID, 15 February 2009, ‘Weekly Update: 15
 February 2009’.
604
th
Report Salmon, 15 May 2009, ‘COMUKAMPHIBFOR OP TELIC 12/13 (HQ MND(SE) Post Operational
605
Report (POR)’.
Minute Lyon to Prime Minister, 14 December 2008, ‘Visit to Iraq, 17 December’.
606
Report Salmon, 15 May 2009, ‘COMUKAMPHIBFOR OP TELIC 12/13 (HQ MND(SE) Post Operational
607
Report (POR)’.
363

---
a comprehensive picture of the support provided to Basra Airport by the UK and other
international partners.
Long-Term Strategy for Iraq, February 2009
1031. Mr Miliband’s Private Secretary circulated a draft strategy for “UK policy towards
and relations with Iraq following military drawdown” to No. 10 and the Private Offices
of NSID(OD) Ministers on 13 January 2009.
 The draft strategy had been agreed by
608
officials from all interested departments and by Mr Miliband.
1032. The draft strategy, which is described in detail in Section 9.7, stated that the UK
had a “strategic national interest in a strong, stable and non-hostile Iraq that:
acts in accordance with international law and does not threaten its neighbours;
provides a counterweight against Iran, ideally as a pro-Western state …;
is able to deny AQ-I [Al Qaida in Iraq] and other terrorist groups a safe haven in
its national territory;
contributes positively to stable world energy markets by maximising its potential
as a producer and exporter of oil and gas, and increases EU energy security
through developing new supply routes.”
1033. The draft strategy identified a number of “essential” and “highly desirable” factors
for achieving the UK’s strategic interest of a “strong, stable and non-hostile Iraq”. The
essential factors included a “functioning economy”, which would require agreement on
the Hydrocarbons Law. Highly desirable factors included:
that Iraq should be “a broadly democratic state”;
that Iraq should address critical humanitarian issues, in particular the large
number of refugees and displaced people; and
that Iraq should develop a strong and open market economy.
1034. The draft strategy listed a number of elements of a future Iraq/UK relationship,
including:
Economic: the UK would help build Iraqi capacity to deliver economic growth
and opportunity (DFID to lead).
Energy: the UK would help Iraq to bring greater volumes of oil and gas to the
market (FCO and the Department of Energy and Climate Change (DECC) to
lead, with MOD).
Commercial: the UK should ensure a level playing field for UK firms in Iraq
(UKTI/FCO to lead).
Education and culture: increased educational and cultural exchanges would
underpin other elements of the relationship.
Letter Hickey to Catsaras, 13 January 2009, ‘Iraq: Strategy’, attaching Paper [draft], [undated],
608
‘Iraq: a Review of Strategy’.
364

---
10.2 | Reconstruction: July 2004 to July 2009
1035. The draft strategy stated that much of DFID’s work in Basra would come to a
“natural conclusion” by mid-2009. DFID would respond to changing conditions on the
ground, but anticipated “drawing down from Basra” by that date. It would continue to
provide some support to programmes through the Basra Support Office in Baghdad.
DFID resources for Iraq would reduce from £25m in the current financial year (2008/09)
to £20m in 2009/10 and £10m in 2010/11.
1036. The Stabilisation Aid Fund (SAF) and the FCO’s Peace-Keeping Budget (PKB)
were essential sources of funding for UK programmes in Iraq. There was unlikely to be
any PKB funding for Iraq in 2009/10. MOD, DFID and FCO officials were reprioritising
the £15m SAF allocation for Iraq for 2009/10, to support “initiatives which support key
Prime Ministerial deliverables” and the Rule of Law.
1037. Mr Alistair Darling, Chancellor of the Exchequer, Mr John Hutton, the Defence
Secretary, and Mr Alexander confirmed their agreement to the strategy.
609
1038. Mr Donal Brown informed the 4 February meeting of the ISG that the US would
take over the Basra PRT on 31 March.
 The US had agreed to retain programmes that
610
were important to UK objectives.
1039. On 9 February, Mr Brown’s Assistant Private Secretary told the Private
Secretaries to Mr Miliband and Lord Mandelson that Mr Brown had endorsed
the strategy, which was consistent with the approach described to Parliament on
18 December.
611
1040. Mr Brown remained “keen to ensure maximum savings as we move to a normal
bilateral relationship”, but agreed that:
“… the UK will retain an important strategic interest in the emergence of a stable and
prosperous Iraq, able to contribute to regional stability and global energy security;
and that we will have important bilateral interests in Iraq which need to be secured
and promoted …
“In particular, the Prime Minister continues to believe that improving trade and
investment in Iraq is key both to consolidating the security gains that have been
made, and ensuring UK investors are able to benefit from the opportunities in
Iraq … We also need to ensure that investors in Basra continue to be supported
as our military hands over to US.”
1041. A planned visit by Prime Minister Maliki to the Invest Iraq Conference in London
at the end of April would be “an important milestone for showcasing progress in the
transition to a new relationship with Iraq”.
Letter Jordan to Hickey, 26 January 2009, ‘Iraq Strategy’; Letter Ferguson to Catsaras,
609
29 January 2009, ‘Iraq: Strategy’; Letter Wright to Catsaras, 5 February 2009, ‘Iraq Strategy’.
Record, 4 February 2009, Iraq Strategy Group meeting.
610
Letter Catsaras to Hickey and Abel, 9 February 2009, ‘Iraq Strategy’.
611
365

---
1042. Lord Mandelson visited Iraq on 6 April, at the head of a delegation of
23 companies.
 The objectives of the visit included:
612
underlining the UK’s commitment to building a new broad-based, long-term
partnership with Iraq, with a strong emphasis on economic and trade
co-operation;
countering Iraqi complaints (from Prime Minister Maliki and others) about the
lack of interest from UK business, while assisting the business delegation
to build contacts with Iraqi Ministers and members of the Iraqi business
community; and
supporting UK companies pursuing business in Iraq.
1043. In Baghdad, Lord Mandelson and the delegation met Prime Minister Maliki.
613
Mr Prentice reported that the meeting had been “entirely positive” and a “powerful
demonstration of the new civilian focus to our bilateral relationship”.
1044. In Basra, Lord Mandelson and the delegation attended an investment conference
at Basra Airport.
 Mr Haywood reported that the event had been “timed perfectly” so
614
that the UK could “demonstrate that whilst the military were drawing down, the UK’s
commitment to Basra continued”. The mood at the event had been “optimistic”, reflecting
the mood in Basra: recent polling showed that over 80 percent of Basrawi businesses
thought that the economic environment had improved over the past year and would
continue to improve.
1045. The Iraqi National Investment Commission, with support from DFID, hosted the
Invest Iraq Conference in London on 30 April.
 Mr Prentice described the Conference
615
as the UK’s “headline initiative … demonstrating in a practical way our desire for a new
and normalised bilateral relationship”.
1046. Mr Brown made a statement to Parliament on the UK’s involvement in Iraq on
15 June.
 He reported that the objectives set out in his statement of 18 December,
616
including “to promote the reconstruction of the country, economic growth and basic
services”, “were being achieved”. On reconstruction, Mr Brown said:
“Since 2003, the UK has spent more than £500m in Iraq – for humanitarian
assistance, infrastructure and promoting economic growth. Support to the health
sector has included 189 projects in Basra, including the refurbishment of Basra
general hospital and the building of Basra children’s hospital. As a whole, the
Briefing, [undated], ‘Visit of the Rt Hon Lord Mandelson to Bahrain, Kuwait, Iraq, Abu Dhabi and Dubai,
612
5 – 8 April 2009’.
eGram 12764/09 Baghdad to FCO, 8 April 2009, ‘Iraq: Lord Mandelson’s Visit to Baghdad,
613
06 April 2009’.
eGram 12607/09 Basra to FCO London, 7 April 2009, ‘Iraq: Lord Mandelson’s Visit to Basra, 6 April’.
614
eGram 15041/09 Baghdad to FCO London, 28 April 2009, ‘Iraq: Invest Iraq Conference, London –
615
30 April – 1 May.
House of Commons Official Report, 15 June 2009, columns 21-23.
616
366

---
10.2 | Reconstruction: July 2004 to July 2009
international community has rehabilitated more than 5,000 schools. Despite high
unemployment and the scale of the global recession, economic growth in Iraq this
year is predicted to be nearly seven percent.
“Significant challenges remain, including that of finding a fair and sustainable
solution to the sharing of Iraq’s oil reserves, but Iraq’s future is now in its own
hands …
“At the core of our new relationship … will be the diplomatic, trading and cultural
links that we are building with the Iraqi people, supporting British and other foreign
investors who want to play a role in the reconstruction of southern Iraq.”
Resources available for reconstruction
1047. The table below sets out UK expenditure on humanitarian assistance and
development assistance (reconstruction) by UK financial year.
Table 2: UK expenditure on humanitarian and development assistance (£m)
2002/03
2003/04
2004/05
2005/06
2006/07
2007/08
2008/09
2009/10
Total
Humanitarian and development assistance
621
Humanitarian assistance
19
110
21
5
10
20
16
8
209
Development assistance
99
27
82
39
20
17
13
297
Imputed share of multilateral
aid
11
11
6
14
9
14
8
73
Sub-total
19
220
59
93
63
49
47
29
579
1048. DFID provided £297m for reconstruction and a further £209m for humanitarian
assistance in Iraq between 2002/03 and 2009/10. Iraq was DFID’s largest bilateral
programme in 2003/04, when DFID spent a total of £220m. That included a
£110m contribution to the humanitarian relief effort following the invasion and a
£70m contribution to the World Bank and UN Trust Funds (which would be spent by the
World Bank and UN in subsequent years). The size of DFID’s programme decreased
over the following years.
1049. In addition, UK forces in MND(SE) spent £38m from UK funds on Quick Impact
Projects (QIPs).
618
1050. It is not possible, from the information available to the Inquiry, to produce a
definitive breakdown of the allocation of DFID funding between national programmes
and programmes in the South. The Inquiry calculates that, from 2003/04 to 2007/08,
Letter Cabinet Office [junior official] to Aldred, 1 July 2011, ‘Iraq Inquiry: request for further information
617
on funding’.
Paper DFID, January 2010, ‘DFID Non-Humanitarian Spend by Region’.
618
367

---
between 76 percent and 52 percent of DFID funding was allocated to programmes in the
South.
 DFID’s expenditure in the South peaked in 2005/06.
619
1051. UK forces also had access to significant amounts of US funding from the
Commander’s Emergency Response Program (CERPs) to spend on urgent relief and
reconstruction needs.
1052. The Government has not been able to provide a full breakdown of the amount of
CERPs funding used by UK military commanders, but it appears to have been greater
than the total amount provided by the UK for reconstruction. The US allocated US$66m
from CERPs to MND(SE) in 2005/06.
 In the same year, in MND(SE), DFID spent
620
some £35m on infrastructure and job creation
 and the MOD spent £3m on QIPs.
621
622
1053. By April 2009, the US had spent or allocated to ongoing projects US$351m from
CERPs in MND(SE), and spent or allocated to ongoing projects some US$3.3bn from
all sources in MND(SE).
 Over the same period, in MND(SE), DFID spent at least
623
£100m
 and the MOD spent £38m on QIPs.
624
625
1054. UK funding was also available for Iraq from the Global Conflict Prevention Pool
(and subsequently the Stabilisation Aid Fund and the Conflict Pool). Most of that funding
was allocated to Security Sector Reform (see Section 12). The table below sets out
expenditure from the Pools.
Calculation excludes DFID funding for humanitarian assistance, the World Bank and UN Trust Funds,
619
and programme support cost such as security, accommodation and communications. It is not possible
to produce a reliable estimate of the proportion of the funding provided for those purposes that related
to the South.
Briefing, October 2006, ‘PQ06267S: CERP Funds FY06 (1 Oct 05 – 30 Sep 06)’.
620
Calculation excludes DFID funding for humanitarian assistance, the World Bank and UN Trust Funds,
621
and programme support cost such as security, accommodation and communications. It is not possible
to produce a reliable estimate of the proportion of the funding provided for those purposes that related
to the South.
Paper DFID, January 2010, ‘DFID Non-Humanitarian Spend by Region’.
622
Special Inspector General for Iraq Reconstruction, Quarterly Report and Semiannual Report to the
623
US Congress, 30 July 2009.
Calculation excludes DFID funding for humanitarian assistance, the World Bank and UN Trust Funds,
624
and programme support cost such as security, accommodation and communications. It is not possible
to produce a reliable estimate of the proportion of the funding provided for those purposes that related
to the South.
Paper DFID, January 2010, ‘DFID Non-Humanitarian Spend by Region’.
625
368

---
10.2 | Reconstruction: July 2004 to July 2009
Table 3: UK expenditure from the Conflict Pools (£m)
2002/03
2003/04
2004/05
2005/06
2006/07
2007/08
2008/09
2009/10
Total
Interdepartmental Conflict Pools
630
GCPP
5
16
15
20
16
72
Stabilisation Aid Fund
19
19
Conflict Pool
11
11
Total
5
27
32
35
22
26
12
159
1055. SIGIR reported in July 2009 that, as at June 2009, a total of nearly
US$140bn had been allocated for the relief and reconstruction of Iraq.
 That
627
comprised:
US$71bn from Iraqi capital budgets and the Development Fund for Iraq (DFI);
US$52bn from the US; and
US$17bn from other international donors.
1056. The US allocation included US$21bn from the Iraq Relief and Reconstruction
Fund (IRRF), US$18bn from the Iraq Security Forces Fund, US$4bn from the Economic
Support Fund and US$3.6bn from the CERPs.
Reflections on the impact of the UK’s reconstruction effort
1057. From the available information, it is not possible fully to assess the impact of the
UK’s reconstruction effort.
1058. One difficulty is that the Government never defined what contribution
reconstruction should make to achieving broader UK objectives and so what would
constitute success or failure.
1059. The environment in Iraq made reconstruction very difficult. For almost all of the
period covered by the Inquiry, insecurity was the major constraint. Other constraints
were:
the lack of capacity within the Iraqi Government, both in Baghdad and the South,
to support and lead reconstruction;
the form and implementation of de-Ba’athification;
the politicisation of Iraqi institutions, and corruption;
the series of relatively short-lived Iraqi administrations between 2004 and 2006
(with limited remits to initiate reform and an inevitable churn of Ministers and
senior officials);
Letter Cabinet Office [junior official] to Iraq Inquiry [junior official], 1 December 2011, ‘Iraq Inquiry:
626
Funding’.
Special Inspector General for Iraq Reconstruction, Quarterly Report and Semiannual Report to the
627
US Congress, 30 July 2009.
369

---
an international community which, because of the circumstances of the invasion,
was not fully invested in the reconstruction of Iraq; and
the persistent lack of co-ordination between the Iraqi Government and
international partners, and between international partners.
1060. Staff and contractors developed a number of approaches to managing the risks
inherent in working in such an environment:
using innovative techniques to deliver projects, such as working through local
Iraqi contractors, using the military (who were more frequently able to visit
project sites) to manage and monitor projects, and helping the Ministry of
Finance to set up an office inside the International Zone in Baghdad within
which international consultants could work;
systematically tracking poor performance;
adapting delivery methods to reduce fiduciary risk; and
building clear exit strategies into projects, including dedicating significant effort
to bringing in other donors.
1061. The Inquiry recognises the dedication and skill of the staff and contractors who
worked in Iraq, often in discomfort and at personal risk.
1062. Witnesses to the Inquiry and contemporary documents identify three areas in
particular where the UK had made a significant contribution to Iraq’s reconstruction:
building Iraqi capacity at the centre of government (including the Prime
Minister’s Office and the Cabinet Office), and strengthening the linkages
between Baghdad and the provinces;
building the capacity of the provincial administration in Basra; and
building the capacity of successive Iraqi Governments to manage the economy
(including the launch of a new Iraqi currency in 2003) and engage effectively
with the IMF.
1063. The Inquiry met a number of senior Iraqi politicians and officials, and asked
them for their views on the UK’s reconstruction effort. DFID’s focus on building Iraqi
Government capacity to plan and manage was recognised and welcomed. That was
contrasted with short-term activities, including building schools and hospitals, which Iraq
could do for itself.
1064. In Basra, the Inquiry was told that there was little to show for the UK’s
reconstruction effort. A small number of projects were identified as continuing to have
a positive impact, including:
training in the UK delivered by the PRT;
job creation programmes supported by DFID; and
improvements to the sewerage system supported by the UK military.
370

---
10.2 | Reconstruction: July 2004 to July 2009
Key economic and social indicators
1065. It is possible to consider the impact of the international community’s
reconstruction efforts in Iraq by looking at the changes in a number of key indicators.
The table below presents selected economic and social indicators.
1066. In relation to the economy:
Electricity production fell from around 4,000 megawatts (MW) per day before
the invasion to 500MW in May 2003 (immediately after the invasion), before
recovering to around 4,000MW in June 2004 (the transition to a sovereign Iraqi
Government).
 By July 2009, production was around 6,000MW.
628
Oil production fell from around 2.9m barrels a day (bpd) before the invasion to
around 0.3m bpd in May 2003, before recovering to 2.3m bpd by June 2004.
By 2009, production remained below pre-conflict levels.
1067. The under-five mortality rate fell from 42 to 38 (per 1,000 live births) between
2003 and 2009. Other key social indicators remained stable.
1068. Perceptions of corruption in Iraq worsened between 2003 and 2009. Iraq fell
from 113th out of 133 countries surveyed for Transparency International’s Corruption
Perceptions Index in 2003, to 176th out of 180 countries surveyed in 2009.
1069. The UN’s 2009 Common Country Assessment concluded that, while Iraq had
fulfilled its constitutional mandate requiring 25 percent of Parliamentary seats to be
filled by women, women remained under-represented at higher levels within the
public sector and government.
 Women also had higher illiteracy levels than men,
629
participated in smaller numbers in the labour force, were paid less and were segregated
into certain occupations. A disproportionate number of households in poverty were
headed by women.
Brookings, Iraq Index, Electricity.
628
UN, 2009, Common Country Assessment: Iraq.
629
371

---
Table 4: Iraq: selected economic and social indicators
1989
2002
2003
2004
2009
GDP at market prices (current
US$bn)
65.6
n/a
n/a
36.6
111.7
634
GDP per capita GDP (current US$)
3,850
n/a
n/a
1,391
3,725
635
Electricity production (megawatts)
500 –
636
3,958
3,456
4,030
5,700
Oil production (million barrels per
day)
2.90
2.02
1.31
2.01
2.39
637
Under-five mortality rate
55
43
42
42
38
638
Primary school enrolment, both
sexes (%)
90
n/a
94
93
92
639
Employment (%)
43
43
43
43
44
640
Corruption
n/a
n/a
113/133
129/146
176/180
641
World Bank, Data, [April 2016], Iraq: GDP at market prices (current US$).
630
World Bank, Data, [April 2016], Iraq: GDP per capita (current US$).
631
Brookings, Iraq Index, Electricity. Figure for 2002 is a estimated pre-war level.
632
US Energy Information Administration website. Iraq Crude Oil Production by Year.
633
World Bank, Data, [April 2016], Iraq: Mortality rate, under-5 (per 1,000). Under-5 mortality rate is
634
a leading indicator of the level of child health and overall development in countries.
World Bank, Data, [April 2016], Iraq: Net enrolment rate, primary, both sexes (%). Figure for 2009
635
relates to 2007 survey.
World Bank, Data, [April 2016], Iraq: Labor force participation rate, total (% of total population
636
ages 15-64).
Transparency International, Corruption Perceptions Index (CPI). Iraq was not included in the CPI before
637
2003. The CPI draws on multiple data sources.
372