SECTION 13.2
CONCLUSIONS: RESOURCES
Contents
Introduction and key findings ....................................................................................... 570
Estimates of the cost of the UK’s involvement in Iraq .................................................. 570
The decision to take military action against Iraq .......................................................... 572
Arrangements for funding military operations and civilian activities ............................. 575
Resources and strategy ............................................................................................... 580
Lessons ........................................................................................................................ 581
569

---
The Report of the Iraq Inquiry
Introduction and key findings
1. This Section addresses analysis and findings in relation to the evidence set out in
Section 13.1, on the allocation of resources for military operations and civilian activities
in Iraq.
2. This Section does not address how government departments used the resources
available to them. Specifically:
•
the provision of military equipment is considered in Sections 6.3 and 14;
•
the UK’s support for reconstruction is considered in Section 10; and
•
the UK’s support for Security Sector Reform is considered in Section 12.
Key findings
•
The direct cost of the conflict in Iraq was at least £9.2bn (the equivalent of
£11.83bn in 2016). In total, 89 percent of that was spent on military operations.
•
The Government’s decision to take part in military action against Iraq was not
affected by consideration of the potential financial cost to the UK of the invasion or
the post‑conflict period.
•
Ministers were not provided with estimates of military conflict and post‑conflict costs,
or with advice on their affordability, when decisions were taken on the scale of the
UK’s military contribution to a US‑led invasion of Iraq, and on the UK’s role in the
post‑conflict period. They should have been.
•
There was no articulated need for additional financial resources for military
operations in Iraq that was not met.
•
The arrangements for funding military Urgent Operational Requirements (UORs) and
other military costs worked as intended, and did not constrain the UK military’s ability
to conduct operations in Iraq.
•
The controls imposed by the Treasury on the Ministry of Defence’s (MOD’s) budget
in September 2003 did not constrain the UK military’s ability to conduct operations
in Iraq.
•
The Government was slow to recognise that Iraq was an enduring operation, and
to adapt its funding arrangements to support both military operations and civilian
activities.
•
The arrangements for securing funding for civilian activities could be slow and
unpredictable. Some high‑priority civilian activities were funded late or only in part.
Estimates of the cost of the UK’s involvement in Iraq
3. It was the responsibility of departments in the first instance to:
•
produce estimates of the costs of activities for which they were responsible;
•
discuss those estimates with the Treasury; and
•
make them available to Ministers and, if appropriate, Cabinet to inform their
discussions.
570

---
13.2 | Conclusions: Resources
4. The Treasury began considering the potential cost of UK involvement in Iraq in
June 2002, and produced the first estimated figure for the cost of military action in Iraq
(£2.5bn) in September 2002.
5. The MOD sent “some indicative breakdowns” of the cost of military action to the
Treasury on 11 October
 and “ball‑park figures” for the cost of military action (up to £2bn)
1
to Mr Blair on 15 October, to inform his decision on whether to offer a large scale land
force to the US.
2
6. Mr Geoff Hoon, the Defence Secretary, sent a detailed estimate of contingency
planning costs (£1.65bn) to Mr Gordon Brown, the Chancellor of the Exchequer, in
mid‑December. A copy of the letter was sent to Mr Blair. That estimate covered the
cost of preparing, deploying and retrieving a military force, but not of any war‑fighting
or post‑conflict activities.
7. The MOD produced its first estimate of military post‑conflict costs in February 2003,
just one month before the invasion. It also increased its estimated figure for the cost of
military action (to between £2.5bn and £3bn).
8. The Treasury produced detailed analyses of the implications of a conflict in Iraq for
public expenditure in September and October 2002.
9. Treasury officials’ advice to Mr Brown on military cost estimates and the implications
for public expenditure was timely and accurate. It repeatedly highlighted the risk that
the UK would have to maintain a significant military force in Iraq in the medium term
and challenged the MOD’s assertion that the UK could limit its financial liability for Iraq’s
post‑conflict security and reconstruction.
10. The MOD should have produced detailed estimates of military conflict and
post‑conflict costs sooner, in order to inform consideration of options for the UK’s
engagement.
11. Both the Treasury (from September 2002) and the Department for International
Development (DFID) (from January 2003) produced detailed and robust analyses of
potential humanitarian assistance and reconstruction costs in Iraq. Both departments
concluded that the costs could be substantial.
12. Treasury officials’ advice to Mr Brown highlighted the risk that the UK might have to
make a significant contribution to Iraq’s reconstruction, as a key member of the Coalition
and in particular in the absence of UN cover. The UK Government expected that UN
cover would be necessary if other international partners were to provide significant
contributions to the post‑conflict effort.
Minute Nye to Chancellor, 11 October 2002, ‘Iraq: Decisions Nearing’.
1
Minute Hoon to Prime Minister, 15 October 2002, ‘Iraq: UK Military Options’ attaching Paper MOD,
2
14 October 2002, ‘Iraq: UK Contingency Planning’.
571

---
13. In February 2003, Treasury officials provided Mr Brown with the first comprehensive
estimate of military and civilian costs for the conflict and post‑conflict period. The cost of
a military campaign was estimated at £3.4bn over three years, with a further £1bn in the
first year after a conflict for post‑conflict military operations. The cost of a UK contribution
to humanitarian assistance and reconstruction was estimated at up to £0.75bn in the
first year after a conflict (representing 10 percent of the cost of the total international
effort). The Treasury indicated that costs for military operations beyond 2004/05 and for
humanitarian assistance and reconstruction beyond 2003/04 were unknown.
14. Treasury officials advised Mr Brown that their estimate reflected the “biggest
commitment” that the UK could make in the post‑conflict period – taking military
responsibility for a geographical area of Iraq.
 The costs of such a commitment would be
3
substantial and could extend into the long term.
15. Given the uncertainties over the scale of the UK’s military presence in post‑conflict
Iraq, and the inevitable uncertainties over the scale of any post‑conflict humanitarian
crisis and reconstruction challenge, the Treasury’s February 2003 estimates were
remarkably accurate.
16. Mr Paul Boateng, the Chief Secretary to the Treasury from 2002 to 2005, told the
Inquiry that the Treasury’s analyses of the impact of war on the UK’s public finances
were not conducted with the intention of “second‑guessing” Ministers, but to enable the
Treasury to contribute to planning and policy discussions.
4
17. The Inquiry agrees that the Treasury’s analyses should have contributed to planning
and policy discussions.
18. Mr Brown told the Inquiry that, in his discussions with Cabinet colleagues in
the months leading up to the invasion, he made it clear that the Treasury would not
“interfere” by suggesting that cost should be a factor in choosing one military option over
another:
“That was not our job ... At every point, I made it clear that we would support
whatever option the military decided upon with the Prime Minister and the
Cabinet ...”
5
The decision to take military action against Iraq
19. Section 6.5 addresses the Government’s failure to establish a unified
planning process across the four principal departments involved – the Foreign and
Commonwealth Office (FCO), the MOD, DFID and the Treasury – or between military
and civilian planners, in the pre‑conflict period.
Minute Treasury [junior official] to Chancellor, 19 February 2003, ‘Update on Iraq’ attaching Paper
3
Treasury, 19 February 2003, ‘Iraq Conflict – Public Expenditure Impact’.
Public hearing, 14 July 2010, page 22.
4
Public hearing, 5 March 2010, pages 25‑26.
5
572

---
13.2 | Conclusions: Resources
20. In the absence of a Cabinet Minister with overall responsibility for Iraq, leadership
on strategy rested with Mr Blair.
21. The version of the Ministerial Code that was current in 2003 stated that it was the
responsibility of the initiating department to ensure that proposals involving expenditure
or affecting general financial policy were discussed with the Treasury before being
submitted to Cabinet or a Ministerial Committee. The result of the discussion together
with an estimate of the cost should be included in the memorandum submitted to
Cabinet or a Ministerial Committee.
Mr Brown’s discussions with Ministers on the likely
costs of the UK’s involvement in Iraq
In the months before the invasion, Treasury officials produced a series of detailed
analyses of the likely cost of intervention in Iraq, and the effect on public expenditure, for
Mr Brown. In the context of that advice, Treasury officials urged Mr Brown to intervene in
discussions on the scale of the UK’s involvement in the military campaign and on the UK’s
role in a post‑conflict Iraq.
Mr Brown had many meetings with Cabinet colleagues, including Mr Blair, in the run‑up
to the invasion. Those meetings were often one‑to‑one, and no record was taken. In the
absence of those records, the Inquiry is unable to determine whether or in what way
Mr Brown raised the issues highlighted by his officials.
22. The detailed estimates for military conflict and post‑conflict costs produced by the
MOD and the Treasury, and the analyses of the implications of a conflict in Iraq for public
expenditure produced by the Treasury, were not sent to Mr Blair or to Ministers outside
the originating departments.
23. Ms Clare Short, the International Development Secretary, wrote to Mr Blair on
5 February, 14 February and 5 March 2003, highlighting the potential cost of a UK
contribution to an international humanitarian assistance and reconstruction effort, and
the potential cost of pursuing an exemplary approach to the provision of humanitarian
assistance in the UK’s Area of Responsibility (AOR) in southern Iraq. She also raised the
issue in Cabinet on 27 February.
24. On 14 March, in response to Mr Blair’s request that Mr Brown should draw up a
funding plan for Iraq, the Treasury provided a paper setting out the potential cost of a
UK contribution to an international humanitarian assistance and reconstruction effort.
25. Detailed estimates of military costs and the analyses of the implications of a conflict
for public expenditure should have been available to Ministers on three occasions which
shaped the UK’s involvement in Iraq:
•
In advance of Mr Blair’s decision on 31 October 2002 that the UK should
offer a large scale land force to the US for planning purposes.
573

---
Mr Blair had, over the previous month, expressed his concern to Mr Hoon over
the additional costs associated with providing a large scale land force as part of
a UK contribution to a US‑led invasion of Iraq, and asked whether those costs
had been discussed with the Treasury.
The MOD and the Treasury had, by the middle of October, developed broad
estimates of the cost of providing a large scale land force. Mr Brown had also
been provided with detailed analyses of the implications for public expenditure of
a conflict in Iraq.
At the meeting where the decision to offer a large scale land force was taken,
Admiral Sir Michael Boyce, Chief of the Defence Staff, stated his belief that
providing a large military contribution to the campaign would mean that the
UK would be under less pressure to make a large contribution to post‑conflict
reconstruction.
•
In February and March 2003, when the Government considered whether to
take on military responsibility for a geographical area of Iraq in the post‑conflict
period.
The MOD and the Treasury had, by February, developed detailed estimates of
the potential cost of such a commitment (although there remained a number of
unknown factors).
When the Government acceded in April to the US request that it assume
leadership of a military AOR encompassing four provinces in southern Iraq, it did
so without a robust analysis either of the strategic implications for the UK or of
the military’s capacity to support the UK’s potential obligations in the region. A
step of such magnitude should have been taken deliberately, having considered
the wider strategic and resource implications and contingent liabilities.
In the event, the UK was responsible for security in its AOR for six years,
initially as an Occupying Power and, from June 2004, in support of the Iraqi
Government.
•
In advance of Cabinet’s decision on 17 March 2003 to issue an ultimatum
to Iraq and ask the House of Commons to endorse the use of military action
against Iraq if necessary.
26. The extent to which cost should be a determining factor in reaching a policy decision
is for Ministers to judge based on the circumstances of each particular case. But it is
essential that those taking collective responsibility for a decision have the ability to make
an informed judgement about the likely costs and risks.
27. Neither Cabinet nor any of the Ministerial meetings convened to discuss military
options and the UK’s role in a post‑conflict Iraq were provided with detailed cost
estimates for the various policy options for the UK’s involvement in Iraq, and their
implications for public expenditure.
574

---
13.2 | Conclusions: Resources
28. Those meetings were therefore unable to reach informed judgements on the
financial risk associated with those options.
29. The leading role played by No.10 in the decision to support US‑led military action
against Iraq may have contributed to that omission.
30. In relation to decisions of such gravity as invading another sovereign country, it is
particularly important that the Prime Minister ensures that the Ministerial Code is met.
31. But Mr Brown, as Chancellor of the Exchequer, should have ensured that estimates
of the likely overall cost of a UK intervention in Iraq, for military and civilian activities
during the conflict and post‑conflict period, and the wider implications for public
expenditure were identified and available to Ministers and Cabinet.
Arrangements for funding military operations and
civilian activities
32. The Government used the existing – separate – arrangements for funding military
operations and civilian activities to fund the UK’s involvement in Iraq.
33. Military operations were funded through well‑established procedures which enabled
the MOD to incur costs and then reclaim them from the Reserve. Those claims were
(in line with the agreed procedures) subject to a relatively light level of scrutiny by
the Treasury.
34. DFID and the FCO funded their activities in Iraq in the first instance by reprioritising
within their existing departmental settlements and, if and when that proved insufficient,
by bidding to the Treasury for additional funding from the Reserve. Those bids were
closely scrutinised by the Treasury.
35. The Treasury pressed DFID and the FCO hard to reprioritise within their existing
departmental settlements to fund new activities in Iraq, before agreeing to provide
additional funding from the Reserve. An FCO official, writing in 2005, described the
Treasury as playing “hard ball” and setting departments against one another in order
to see off potential and actual claims to the Reserve.
6
36. The MOD, DFID and the FCO also had access to a small, inter‑departmental
fund – initially the Global Conflict Prevention Pool (GCPP) – intended for conflict
prevention activities. The GCPP had been established to encourage and support a more
co‑ordinated approach across Government.
37. DFID had a larger departmental settlement than the FCO, including a large
allocation for funding programmes. Programme allocations could be used flexibly in
response to emerging priorities. DFID therefore had more scope than the FCO to find
funding for new programmes in Iraq.
Minute Crompton to Sawers, 4 May 2005, ‘Iraq: Reflections’.
6
575

---
38. Sir Suma Chakrabarti, DFID Permanent Secretary from 2002 to 2007, told the
Inquiry that DFID’s funding for Iraq was found by reallocating funding from DFID
programmes in other middle‑income countries, rather than from programmes in
low‑income countries.
7
39. Sir Mark Lyall‑Grant, FCO Policy Director from 2007 to 2009, summarised the
situation in his evidence to the Inquiry:
“… you have the MOD which can call on the Reserve for unforeseen military
expenditure. You have DFID, who have a large amount of programme money ...
and you have the Foreign Office that doesn’t have any money.”
8
40. The Treasury’s priority throughout the period covered by the Inquiry was to
avoid any suggestion that other departments should have access to the Reserve on
the same basis as the MOD. In February 2007, a senior Treasury official advised
Mr Stephen Timms, Chief Secretary to the Treasury from May 2006 to June 2007:
“Arguably this [the different arrangements for funding military operations and civilian
activities] can lead to perverse outcomes ... if it incentivises decision‑makers to
prefer military responses to civilian ones. But it is a useful safety net for us and not
to be given up without careful thought.”
9
41. The arrangements for funding military operations (including Urgent Operational
Requirements – UORs) worked as intended, and did not constrain the military’s ability to
conduct operations in Iraq.
42. All the MOD’s claims on the Reserve in respect of UORs and other additional
military costs were met.
43. There are no indications that Mr Brown, Mr Boateng or Treasury officials acted to
delay or distort the provision of funding for UORs and other additional military costs.
44. There are no indications that DFID’s activities in Iraq were constrained by a lack of
resources. The constraints imposed by the disproportionate cost of providing security for
civilian staff and contractors in Iraq are addressed in Section 15.
Public hearing, 22 January 2010, pages 38‑40.
7
Public hearing, 20 January 2010, page 35.
8
Minute Quinault to Chief Secretary, 13 February 2007, ‘DOP Meeting on Iraq and Afghanistan,
9
14 February’.
576

---
13.2 | Conclusions: Resources
Funding for humanitarian assistance
Ms Short and Sir Suma Chakrabarti both told the Inquiry that DFID’s ability to plan to
deliver humanitarian assistance had been constrained by the Treasury’s reluctance to
provide additional funding from the Reserve.
By the end of January 2003, DFID officials had developed a detailed (but still draft)
assessment of potential UK contributions for humanitarian relief and reconstruction in Iraq,
under a number of scenarios.
Ms Short did not approach Mr Brown or the Treasury with a specific bid for additional
resources until 21 March (although she was aware that Mr Brown was likely to support it).
She did write to Mr Blair on 5 February, 14 February and 5 March, advising him of the cost
of potential UK contributions for humanitarian relief and reconstruction (up to £440m a
year), and seeking direction on the role of the UK in delivering the humanitarian response.
She also raised the issue in Cabinet on 27 February.
Given the scale of UK resources that might have been required, it was reasonable to seek
clear direction from Mr Blair on the UK’s role in the humanitarian response. But that did
not preclude an early bid to the Reserve. Indeed, a detailed bid may have focused the
Government’s attention on the need to define the UK’s role more clearly.
By the end of March, DFID had earmarked £210m for humanitarian assistance in Iraq,
comprising £90m from DFID’s own resources and £120m that it had secured from the
Reserve. In addition, the Treasury had agreed that the UK military could spend £30m on
providing humanitarian assistance in the UK’s Area of Operations.
The humanitarian crisis that had been feared did not materialise. By the beginning of May,
DFID had reallocated the balance of the £210m allocated for humanitarian assistance that
remained uncommitted – approximately £90m – to reconstruction.
45. Given its limited programme funds, the FCO found it particularly difficult to identify
funding for new activities in Iraq. It was successful in making bids for funding from
the Reserve to pay for security costs for personnel deployed to Iraq and diplomatic
representation, but other bids were rejected in full or in part.
46. The FCO’s difficulty in securing additional funding was due in part to the quality of
its bids to the Reserve, and in part to the Treasury’s perception that the FCO had not
made sufficient effort to reprioritise from within its existing resources. The Inquiry has not
assessed the accuracy of that perception.
47. In their efforts to secure funding, departments stretched the scope of the GCPP to
accommodate activities as diverse as military equipment for the Iraqi Security Forces
and the Basra Poetry Festival. But the Pool was small (only £7.5m for Iraq in 2003/04)
and the process for securing funding was slow. Sir Mark Lyall‑Grant told the Inquiry that
decisions about how to spend relatively small sums of money had led to “huge disputes
577

---
between Government departments” which had consumed significant amounts of senior
officials’ time.
10
48. Departments found it particularly difficult to find funding for activities that emerged
“in‑year” or appeared to fall between the boundaries of departments’ responsibilities
(such as activities to promote political outreach or support the Iraqi media). A number
of civilian activities that Ministers had identified as a high priority – including, in 2003,
support for the Iraq Media Network and, in 2006, the first Better Basra Action Plan –
were funded late, and only in part.
49. Departments recognised in mid‑2003 that the arrangements for funding civilian
activities were not working well. In September, the Treasury rejected a proposal from
departments for a new pool for funding non‑military activity in Iraq, on the grounds that it
might lead to an increase in claims to the Reserve.
50. The UK’s deployment into Helmand province, Afghanistan, in 2006 prompted
departments, led by the FCO, to revisit the arrangements for funding civilian post‑conflict
activities. Initial proposals focused on enhancing or complementing the GCPP (on the
assumption that the Treasury would not allow access to the Reserve for non‑military
activities).
51. At the same time, MOD claims on the Reserve for UORs increased significantly as
security in Iraq deteriorated, expenditure on Afghanistan increased, and the Government
provided new equipment for the Armed Forces.
52. The Treasury continued to agree the MOD’s claims against the Reserve, but by
April 2007 had concluded that the UOR programme had become a straightforward
supplement to the MOD’s Equipment Programme rather than a response to urgent and
specific requirements in a theatre of operations.
53. In July 2007, the MOD and the Treasury agreed a new arrangement for funding
UORs designed to shift the focus of the MOD’s Equipment Programme towards current
operations. The new arrangement was expected to be cost neutral for the MOD.
54. There were also changes to the arrangements for funding non‑military activities.
In July, the Treasury announced the creation of a new Stabilisation Fund (later
renamed the Stabilisation Aid Fund – SAF) to fund immediate civilian support to
military operations (activities which had previously been funded from the GCPP).
The GCPP was combined with the Africa Conflict Prevention Pool to form the Conflict
Pool. New governance arrangements sought to link more closely expenditure from the
SAF and the Conflict Pool with UK strategy.
55. The changes to the arrangements for funding UORs did not affect operations in Iraq,
which were by this time generating fewer demands for UORs.
Public hearing, 20 January 2010, pages 36–37.
10
578

---
13.2 | Conclusions: Resources
56. There are no indications that the new arrangements for funding civilian activities
affected the civilian effort in Iraq, which was by that time reducing.
57. The Government continued to develop its arrangements for funding reconstruction
and stabilisation operations.
58. The Inquiry has not evaluated in detail the effectiveness of the new arrangements
that were introduced in 2007. They do exhibit some important and welcome features:
•
a dedicated and substantial pool of resources for civilian activities in
environments such as Iraq and Afghanistan; and
•
a requirement that allocations should be based on an inter‑departmental
strategy.
59. The Government should have recognised earlier that Iraq was an enduring
operation, and adapted its arrangements for funding the military operation and civilian
activities accordingly in order to:
•
ensure that the UOR programme retained its focus on addressing urgent and
specific requirements in theatre; and
•
address the difficulties in securing funding for civilian activities.
The imposition of Treasury controls on the MOD
In the light of the publicity surrounding the funding and management of the defence
programme in 2003 and 2004, the Inquiry examined two related questions:
•
whether the size of the MOD’s core budget imposed constraints on operations
in Iraq; and
•
whether the imposition of controls on the MOD’s management of its resources
by the Treasury in September 2003 had an impact on operations in Iraq.
Several witnesses told the Inquiry that, in the MOD’s view, the 1998 Strategic Defence
Review, which signified a major shift towards expeditionary armed forces, had not been
fully funded.
With respect to military operations in Iraq, there are no indications that there was an
unmet, articulated need for additional financial resources. All the MOD’s claims on the
Reserve in respect of UORs and other additional military costs were met.
The Inquiry concludes in Section 14.2 that there were known military capability gaps in
Iraq, and that the availability of funding was not a direct barrier to the identification and
deployment of solutions to those gaps.
During September 2003, the MOD’s additional cash requirement for 2003/04 rose from
£490m to £1,152m. The MOD intended to meet that cash requirement by making a
transfer from its non‑cash budget. The Treasury took the view that that increase signalled
a complete lack of budgetary control within the MOD, and on 26 September imposed
controls on the MOD’s management of its resources.
579

---
The size of the MOD’s proposed transfer from its non‑cash budget reflected a deliberate
attempt by the MOD to exploit the opportunities offered by the Government’s transition
from cash accounting to Resource Accounting and Budgeting.
The increase in the size of the MOD’s cash requirement during September reflected the
inability of the MOD to produce reliable estimates of its cash requirement.
There are no indications that the controls imposed on the MOD by the Treasury in
September 2003 constrained the military’s ability to conduct operations in Iraq.
Resources and strategy
60. Section 9.8 describes the Government’s repeated reassessments of its strategy
for Iraq. Those strategies tended to focus on describing a desired end state, rather
than how it would be reached.
61. None of those strategies considered the resources that the Government would
need to commit to achieve those end states and (at a strategic level) how those
resources should be allocated.
62. In the absence of a strong strategic framework, spending on military operations in
Iraq was driven by a series of decisions on UK force levels and on the equipment that
should be provided to the Armed Forces.
63. The Inquiry concludes in Section 9.8 that, from July 2005 onwards, decisions in
relation to resources for Iraq were made under the influence of the demands of the UK
effort in Afghanistan.
64. Allocations for civilian activities were driven by the FCO’s and DFID’s willingness
and ability to reprioritise from within their departmental budgets and their ability to secure
additional funding from the Reserve and the GCPP.
65. The direct cost to the UK Government of its intervention in Iraq between 2002/03
and 2009/10 was at least £9.2bn in cash terms (the equivalent of £11.83bn in 2016),
comprising:
•
£8.20bn (89 percent of the total direct cost) on military operations;
•
£0.58bn (6 percent) on humanitarian and development assistance;
•
£0.30bn (3 percent) on diplomatic representation; and
•
£0.16bn (2 percent) from the inter‑departmental pools.
66. There are no indications that the Government questioned the balance of funding
between military operations and civilian activities, or considered what the most effective
balance of effort might be to achieve the UK’s strategic objectives.
67. Lord Boateng told the Inquiry that the imbalance in funding between military
operations and civilian activities had arisen “partly as a result of the funding mechanism
580

---
13.2 | Conclusions: Resources
deployed, in the sense that the Ministry of Defence had an access to the Reserve that
was on a different scale from the others [DFID and the FCO]”.
 He continued:
11
“... did anyone sit down and say, ‘Well, this is the sum of money that we have, this
ought to be the balance?’ No, I don’t think they did. Should they have done? Maybe,
but actually it is ... very difficult to do.”
Lessons
68. The direction in the Ministerial Code that the estimate of a cost of a proposal should
be included in the memorandum submitted to Cabinet or a Ministerial Committee applies
equally to military operations. When evaluating military options it is appropriate to
consider financial risk alongside other forms of risk. While governments will rarely wish
to preclude options solely on the basis of cost, they must also recognise that, over time,
cost may become an issue and make it difficult to sustain a military operation over the
longer term.
69. Section 9.8 addresses the difficulties that the Government faced in converting
successive UK strategies into action, in part because those strategies tended to focus
on describing the desired end state rather than how it would be reached. On none
of the occasions when UK strategy was reconsidered was a robust, costed plan for
implementation produced.
70. Strategies and plans must define the resources required to deliver objectives,
identify the budget(s) that will provide those resources, and confirm that those resources
are available.
71. In developing strategies and plans for civilian/military operations, a government
should address the impact of the different mechanisms used to fund military operations
and civilian activities and the extent to which those mechanisms provide perverse
incentives for military action by making it easier to secure funding for agreed military
operations than for civilian activities.
72. A government should also address its explicit and implicit financial policy that, while
there should be no constraint on the provision of funding for military operations, it is
reasonable that for the same civilian/military operation, departments should find funding
for new civilian activities from within their existing budgets, which are likely to be fully
allocated to existing departmental priorities.
73. A government is likely to embark on major civilian/military operations such as Iraq
only rarely.
74. A government should recognise that, in such operations, the civilian components
(including diplomatic activity, reconstruction and Security Sector Reform) will be critical
for strategic success, may be very substantial, and must be properly resourced.
Public hearing, 14 July 2010, page 41.
11
581

---
75. One arrangement would be to create a budget for the civilian components of the
operation, under the direction of a senior Minister with lead responsibility and in support
of a coherent UK strategy. Once allocations were made from that budget to individual
departments, the allocations would be managed within departments’ legal and policy
constraints. Such an arrangement should:
•
ensure that UK strategy was resourced;
•
promote joint working;
•
minimise the potential for gaming;
•
be able to respond to in‑year priorities; and
•
reduce the amount of time that Ministers and senior officials need to spend
arguing about funding individual activities.
76. The Inquiry recognises that, since 2003, significant changes have been made to the
UK’s strategic and operational approach to reconstruction and stabilisation, including to
the arrangements for funding such operations.
582